EE PLANNING PROCESS

| PLANNING PHASES | KEY ACTIVITY | SUBACTIVITY | PERSONS INVOLVED | TIME FRAME | ASSUMPTION | OUTCOME |
| --- | --- | --- | --- | --- | --- | --- |

| Phase One Preparation | 1. Presentation on EE Planning process at Broad Management Forum | EE and D Office do presentation on rolling out of EE planning and factors impacting on the process | -EE Office -Members of the BMF | 26 March 2007 | All the senior managers who should initiate EE planning in their environments are informed of the commencement of the process | Start of the EE planning process |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2. Communicate to all staff in faculty/directorate | -Senior manager ensures communication and involves staff in planning process | Members of the BMF | 27 March 2007 | -Inform and involve all staff of the forthcoming EE planning process and how it is going to unfold | -Foster a culture of ownership for the Plan throughout the Faculty/Directorate -Staff made aware of forthcoming audit of workforce profile |
|  | 3. Conduct workforce profile audit | -Follow the Procedure to complete a workforce audit (to be provided) | -EE Office -Senior managers -HR | April 2007 | -Senior managers formally request all their staff to participate Audit will provide a workforce profile an updated and accurate starting point -Secretaries and PA’S assist with dissemination and collection of EEA1 form -HR Officer accurately enters information on database -EE office verifies data after match and place finalized | -Updated and accurate HR database on required EE information -Verification of data after finalization of match and place |
|  | 4. Training | -Training provided in employment equity planning and awareness | -EE Office -CCPD | April / May 2007 | Senior managers and faculty / directorate representatives are trained in the EE planning process | Employment Equity Awareness and Planning training provided to those who will work on the Plans. |
|  | 5. Assign responsibility to line managers | -KPA linked to EE | -Senior Management -Deans/Directors -Heads of Departments | Subject to Match & Place exercise being completed | Now able to broaden the accountability and responsibility for the development of an EE plan to: -Heads of Departments -Directors -Line managers | -Responsibility and accountability assigned -KPA’S aligned with EE |
|  | 6. Consultative forum established within faculties/departments | -Training provided on the development of an EE Plan | -EE Office -Senior manager -Exco/Consultative forum | Subject to Match & Place exercise being completed | -All occupational categories within that Faculty/Directorate represented | -Compliance with the Act, i.e. representivity and consultation with staff on development of Plan |

| PLANNING PHASES | KEY ACTIVITY | SUBACTIVITY | PERSONS INVOLVED | TIME FRAME | ASSUMPTION | OUTCOME |
| --- | --- | --- | --- | --- | --- | --- |

| Phase Two Implementation | 7. Set targets and time frames | -Obtain current and updated workforce profile from MIS -Faculty/Directorate EE planning committee consult on current profile & its challenges -Faculty/Directorate set achievable targets in line with TUT’S institutional targets as a guideline | -Senior manager -Faculty /Directorate EE committee (or Exco) -Heads of departments | Subject to Match & Place exercise being completed | -EE targets are set for available posts that result from resignations and retirements -Remedial steps for meeting the targets specified (e.g. Succession planning -Time frames linked with business and faculty planning dates (minimum of 3 years, maximum 5 years) -Targets must be reviewed twice yearly | Realistic & achievable targets are set |
| --- | --- | --- | --- | --- | --- | --- |
|  | 8. Compile EE Plan | -Use guideline and template provided -Include consulted on targets, barriers, challenges and affirmative action measures in Plan -Staff in Faculty/Directorate are consulted on the Plan -Copy of Plan provide to EE Office | -Senior managers -Faculty /Directorate -EE committee (or Exco) -EE Office | Subject to Match & Place exercise being completed | -Plan that conforms to prescribed format approved -Faculty / Directorate staff consulted broadly | EE Plan written & agreed upon Plan that belongs to entire Faculty/Directorate |
| PLANNING PHASES | KEY ACTIVITY | SUBACTIVITY | PERSONS INVOLVED | TIME FRAME | ASSUMPTION | OUTCOME |

| Phase 3 Monitoring | 9. Evaluate progress | -Evaluate the Plan in January and July -Copy of Plan provided to EE office -Provide progress report to EE Office for the DVC: Strategic Planning & Operations | -Senior managers -Faculty /Directorate EE committee (or Exco) -DVC: Strategic Planning & Operations -EE Office | Subject to Match & Place exercise being completed | -Reasons are given for lack of progress -Achievements are celebrated | Effective monitoring procedures in place |
| --- | --- | --- | --- | --- | --- | --- |
|  | 10. Compile progress report | Provide report to: -Faculty / Directorate Committee -To staff in faculty/directorate -EMC via DVC: Institutional Planning and Operations -EE Office -EETC | -Senior managers -EMC -DVC: Institutional Planning & Operations -EE Office -EETC | Twice annually in July and December | Progress is well communicated to all stakeholders | Plan that complies with the Employment Equity Act No 55 of 1998 |