TUT Culture 	Change Management Plan

AIM 1:	Establishing a sound and solid basis for implementing the Culture Change Management Plan

| Description |  | Management |  |  |
| --- | --- | --- | --- | --- |
| Objective | Activities | Responsible | Planned | Indicator |
| - To analyse the previous organisational cultures | - Conduct assessment of previous organisational cultures - surveys, interviews and discussion groups - Conduct analysis of data 1.1.3 Conduct climate study (Wellness program) | Project Leader CI-Specialised Team Staff Development | March 2004 ongoing | - An understanding of the existing cultures - Audit report on existing organisational cultures - # of surveys, interviews and discussion groups - 1 Report |
| - To determine the desired corporate culture for TUT | - Conduct workshops, interviews and discussion groups with management and staff members - Inform staff members of the new TUT culture - Determine what parts of the organisational culture need to change to suit new TUT culture | Vice Chancellor Corporate Relations CI-Specialised Team Project Leader | July 2004 ongoing | - Core TUT culture components identified in Tswaragano Briefings - # of line briefings - core organisational culture components identified |
| 1.3 To define a change management strategy for the new organisational culture for TUT | 1.3.1 research and develop project management strategy for implementation 1.3.2 consult various stakeholders such as HR, Corporate Relations, Staff Development, Unions etc. | Project Leader Culture Change Team | April 2004 | - Change management strategy completed - EMC approval |
| 1.4 To create a sense of urgency and ownership for the new organisational culture | 1.4.1 Create a strong awareness for the need for a new organisational culture - Inform all staff members of the proposed organisation culture change - Conduct workshops to impact information to create awareness among leaders and staff for the need for change | Project Leader Corporate Relations Line Managers | June 2005 | - 75% of the organisation persuaded that the status quo is unacceptable - # of workshops/meetings |
|  | - Enable staff to understand and accept the need for a new organisational cultural change - Align Project with TUT Strategic goals | Project Leader Corporate Relations | September 2004 | Project aligned with TUT strategic gaols |
| 1.5 To establish and develop the project’s management infrastructure and capacity | - Establish project infrastructure - Appoint project leader - Educate the project leader, project team members and executives on change management principles, processes and techniques | DVC -HR | March 2004 | - Project leader appointed - Training conducted |
|  | - Identify the Specialised Team or Project Team. - Conduct presentations and training for committee | DVC HR | May 2004 | - Specialised committee identified - Orientation of the Specialised committee |
|  | 1.5.4 Allocate resources and support | Project leader EMC | May 2004 | Resources allocated |
|  | 1.5.5 Enlist counselling and therapy to assist staff through transition | HR - EAP | July 2004 | EAP services |
| 1.6 To develop a strategy to direct the project | 1.6.1 Develop a strategy to help direct the project effort 1.6.2 Create appropriate action plans and budgets for units in support of the organisation culture change project | Project Leader CI-Specialised Team | July 2004 | - Culture Change Strategy - HR Plan - Communication Plan - Training Strategy |
| 1.7 To communicate the mission and strategy of the project | 1.7.1 Identify stakeholders and involve them through an appropriate communication strategy | Project Leader Corporate Relations | June 2005 | - # of stakeholders identified - # of workshops |

AIM 2:	Institutionalising the New Organisational Culture

| Description |  | Management | Timing |  |
| --- | --- | --- | --- | --- |
| Objective | Sub-activities | Responsible | Planned | Indicator |
| 3.1 Anchoring the Drivers of for the new organisational culture | 3.1.1 To develop a clear motto, vision, mission and values of the future | Council EMC | Dec 2004 | Motto, vision and mission statements Norms and values identified |
|  | 3.1.2 To communicate the vision, mission and values of TUT. | Corporate Relations Line Managers | ongoing | Branding strategy and communication # of Tshwagarano briefings |
|  | 3.1.3 To establish and communicate the TUT brand | EMC Corporate Relations Line Managers | Dec 2004 | TUT logo |
|  | 3.1.4 To develop actionable goals and objectives for TUT. | EMC Strategic Planning | February 2004 | Corporate goals and objectives identified and approved by Council. |
|  | - To develop, formulate and plan the strategic position of TUT at departmental level | Line Managers | August 2004 | Departmental business plans completed |
|  | - To develop and approve the Institutional Operating Plan (IOP) for TUT. | Strategic Planning | Dec 2004 | Final IOP for 2005 – 2009 approved by all parties, Senate and Council. |
|  | 3.1.7 To communicate and clarify the strategy of the institution which will unify efforts across the institution. | Strategic Planning Line Managers | Dec 2004 | IOP distributed to all parties |
| 3.2 Developing Models which give form to our thinking; | Align all HR organizational systems to support needed cultural change. These include; - performance management system, rewards and recognition, - disciplinary approaches, - compensation, - career plans and promotions - Employment and selection | Human Resources | June 2005 | All HR organisational systems aligned |

| Description |  | Management | Timing |  |
| --- | --- | --- | --- | --- |
| Objective | Sub-activities | Responsible | Planned | Indicator |
| 3.3 Adoption of new ways of “doing things” or cultural practices in order to inform the TUT culture. | 3.3.1 Identify norms and desired behaviours that inform the new culture | EMC Culture Change Team Line Managers | Dec 2005 | Norms and behaviours identified |
|  | 3.3.2Communicate desired norms and behaviours | Corporate Relations Line Managers | Ongoing | Culture Hand Book |
|  | 3.3.3 Ensure that the desired behaviours are role-modelled by the change agents | HR | June 2005 | # of workshops |
| 3.4 To establish enablers for planting and growing a new culture | 3.4.1 Establish organisational structures that are aligned with the vision and strategy of TUT. To develop clear defined responsibilities that everyone can understand. | EMC Line Managers HR | Dec 2004 | Council approval of new TUT structure Clear defined responsibilities |
|  | 3.4.2 Ensure that Leaders are passionate about the vision and values and who engage and mobilise people to realise the vision. | EMC |  | Leadership Charter signed and “lived” by all leaders |
|  | 3.4.3 To empower broad based action for implementation: - Identify departmental change agents - Conduct skills audit to assess competency levels of change agents - Outline roles and responsibilities of change agents | Culture Change Team Line Managers HR | June 2005 | Change agents identified Skills audit Roles and responsibilities of change agents outlined |
|  | Assets and Resources |  |  |  |
|  | 3.4.4 To invest in educating staff members to inoculate them in the new culture. 3.4.5 Establish infrastructure for managing and monitoring cultural change process. 3.4.6 To establish functional committees 3.4.7 To provide resources for the various change initiatives e.g. organisational design, performance management system, skills development etc. | EMC Human Resources/Staff Development Line Mangers |  | Training and development Project Team Functional committees in place Resources made available |

|  | Learning Processes (Training and development) |  |  |  |
| --- | --- | --- | --- | --- |
|  | 3.4.8 To educate staff members to inoculate them in the new culture | Corporate Relations Human resources CCPD |  | Culture awareness workshops |
|  | 3.4.9 Build & Align Leadership by building leadership skills and transforming existing leadership paradigms into a consistent leadership style throughout that enterprise that encourages the desired behaviour among subordinates. | CCPD |  |  |
|  | 3.4.10 Develop competent leaders throughout the enterprise for the tough assignment of implementing transformation. | CCPD |  | Training for change agents |
|  | 3.4.11 To provide every new employees during orientation with a true sense of the core values, vision, strategies and objectives of TUT. | CCPD Line Managers |  | Effective orientation process in place that is being consistently executed |
|  | - To provide employees with the right skills to ensure empowerment. | CCDP | ongoing | Skills Training Report |
|  | 3.4.13 Conduct training of line managers and change agents to ensure the practical implementation of change at the operational level | CCDP Line Managers | Dec 2005 | Training workshops |
|  | Communication Infrastructure |  |  |  |
|  | 3.4.14 To recruit managers and front-line managers to communicate the same message to their subordinates. | EMC Corporate Relations |  | Tswharagano briefings |
|  | 3.4.15 To establish and implement mechanisms that enable staff to provide feedback and make suggestions | Corporate Relations Line Managers | Dec 2005 | discussion forums to facilitate discussion and upward communication established |

AIM 3:	To monitor and measure progress

| Description |  | Management |  |  |
| --- | --- | --- | --- | --- |
| Objective | Sub-activities | Responsible | Planned | Indicator |
| 4.1 To audit and monitor the culture in relation to the espoused values and ‘thinking models. | 4.1.1 Administer wellness surveys using the Wellness Instrument on a regular basis to enable the provision of appropriate interventions, and to track progress. | CCDP Line Managers | Ongoing | Wellness Reports and recommendations Submitted to relevant committees (Culture Change, EMC) |
|  | 4.1.2 Identify cultural issues within other processes such as grievances, disciplinary procedures, EAP, client satisfaction survey, HR road shows etc. | Human Resources | Ongoing | Cultural issues identified and reported to relevant committees |
| 4.2 To monitor and ensure implementation of culture change management plan | 4.2.1 Monitor culture change management plan and compile progress reports/recommendations to relevant committees | Culture Change Team | ongoing | Progress reports and recommendations submitted to EMC and relevant committees |
|  | 4.2.2 To oversee the implementation conducted at departmental and separate employee levels | Line Managers | Ongoing | Progress reports |
| 4.3 Monitor visible cultural elements such as symbols and icons | 4.3.1 Ensure that Symbols & Icons are visible | Corporate Relations Line Managers |  | Logos, Vision & Mission Statements |
| 4.4 To generate short term wins to foster commitment to the new organisational culture | 4.4.1 To recognise and celebrate visible performance improvements within culture framework - Alignment of culture change issues with performance management system (PMS) | EMC Culture Change Team HR Line Managers | June 2005 | Category added to Excellence award policy Cultural issues incorporated into PMS |
|  | 4.4.2 Provide managers with evidence that the change process is on track | Culture Change Team Corporate Relations | ongoing | Progress reports to relevant committees Communication |