ADDENDUM

TO

INSTITUTIONAL OPERATING PLAN

(2006 – 2010)

SUBMISSION TO DOE

MARCH 2006

INDEX

# INTRODUCTION   ……………………………………………………………………………………..………………	   3

# SECTION A – CURRENT SITUATION (2005/6)   ………………………………..……………………………….	3

A.    CONSOLIDATED PROGRAMME AND QUALIFICATION MIX (PQM) …………………………………….	3

B.    STUDENT ENROLMENT PLANNING…………………………………………………………………………..	4

C.    ACADEMIC STAFF PROFILE AND PERSONNEL EXPENDITURE………………….……………………..	5

D.    FINANCIAL IMPLECATIONS ………………………………………………………………………….………..	5

SECTION B – PREFERED SCENARIO (B) …………………………………………………………………………	8

A.    PROPOSED NEW PROGRAMME AND QUALIFICATION MIX (PQM) 2006 – 2010 …………………….	9

B.    PROPOSED STUDENT ENROLMENT PROFILE ……………………………………………………………..	9

C.    PROPOSED HUMAN RESOURCE PROFILE AND SALARY EXPENDITURE …………………………….	10

Benchmarks and Projected Expenditure ………………………………………………………………………………	10

SECTION C – IMPLEMENTATION PLAN AND FINANCIAL PROJECTIONS …………………………………..	13

A.    IMPLEMENTATION TOWARDS STANDARDISATION OF SERVICE LEVELS …………………………...	13

1.   Backlog on maintenance and upgrading of buildings and facilities ……………………………..…….	13

- Backlog on alterations and expansions of buildings and facilities if the status quo prevails…………….	14

3.   Backlog on equipment and infrastructure upgrading ……………………………………………………....	14

4.   Financial summary on backlogs relating to the current topography ……………………………………..	15

5.   Financial projections …………………………………………………………………………………………..	15

B.    IMPLEMENTATION OF SCENARIO B – SHORT TERM (3 – 5 YEARS)…………………………………….	15

1.  Financial needs to fund the changes in the topography ……………………………………………………	16

2.  Basic assumptions ………………………………………………………………………………………………	16

3.  Preliminary cost estimates ……………………………………………………………………………………..	16

4.  Financial Projections ……………………………………………………………………………………………	17

SECTION D:  FINANCIAL PROJECTIONS …………………………………………………………………………..	18

- PROJECTED FINANCIAL STATEMENTS FOR THE PERIOD 31 DECEMBER 2006 –2010…………………………………………………………………………………………………………	18

B.  RESOURCE ALLOCATION AND PROJECTED EXPENDITURE …………………………………………….	19

SECTION E ………………………………………………………………………………………………………………	20

TABLES 1 & 2: Consolidated PQM (Contact & Distance)………………………………………………………..	21-23

Notes to consolidated PQM………………………………………………………………………………………..	24-26

TABLES 3 & 4:  Proposed PQM (Contact & Distance)…………………………………………………………	 26-29

Notes to proposed PQM….……………………………………………………………………………………………30-32

TABLES 5 – 18:  Headcount and FTE enrollments………………………………………………………………..	33-36

TABLES 16 & 17:   Staff profile ……………………………………………………………………………………...	37

FINANCIAL PROJECTIONS:  SCHEDULES 1 – 5………………………………………………………………..	38-44

PLANNING FRAMEWORK 2006……………………………………………………………………………………….	45

ADDENDUM TO IOP

SUBMISSION TO DOE

INTRODUCTION

The Tshwane University of Technology (TUT) is presenting supplementary information to the Institutional Operation Plan (2005 – 2009) which was submitted to the DoE on the 1st of December 2005. The purpose of this submission is to respond to certain queries and requests indicated by the representatives of the Merger Office. Additional information is being presented in a descriptive format.

The document will briefly indicate the current situation as evident in 2005/6. Referral will be made to the IOP confirming or correcting data which was presented in the IOP and queried by the representatives.  The strategic direction of TUT to become an established University of Technology as presented in Chapter three is still applicable. However the adjustments that need to be made over the next five years to reach this desired position will be clearly indicated. TUT has proposed three scenarios to reach this desired state (see Chapter one, four and five) of which Scenario B is the preferred scenario. This document will indicate the various actions to be taken, processes and targets will be referred to, and the financial implication of the actions to be taken will be given.

TUT wish to demonstrate that the envisaged changes are realistic, sustainable and financially viable.

### SECTION A – CURRENT SITUATION (2005/6)

This section will briefly describe the current situation as in 2005/6, which is portraying the state of affairs two years into the merger.

Currently eleven faculties and 99 departments offer a total of 812 undergraduate and postgraduate programmes across six delivery sites which still reflect duplication.  Consolidation of the 11 faculties towards a single site philosophy will be implemented in a phase-in approach from 2007. Duplication of programmes will thus be eliminated within a three - five year period. Actions that are being taken towards implementation are indicated in Section C.

Academic programmes represent career focused qualifications in economics, management; humanities; education, arts; natural and health sciences; agricultural, engineering; ICT and tourism. Quality aspects have been addressed through an integration process that standardised inter alia the admission requirements, study materials, assessment methods, examination processes and procedures.

All policies have been reviewed and developed to adapt to TUT’s new environment. The Council approved a large number of policies and procedures in November 2005 which means that, for the first time, TUT has a consolidated policy framework in place and only one set of rules.

A.    CONSOLIDATED PROGRAMME AND QUALIFICATION MIX (PQM)

- Alignment process and consolidated PQM

The PQM’s of the three merged institutions have been aligned and consolidated into a programme grid and qualification schedule (list) that was presented in the IOP, page 115 – 174. The consolidated PQM grid has been revised after consultation with the DoE and the revised grid is included (See Tables 1 & 2).  Programmes that are not approved (especially relating to twenty-one doctorate programmes as indicated by the DoE representatives) were indicated with a numerical one (1) (see p. 170 -174). Verification of approval of Doctoral programmes has been conducted and it can be proven that TUT has approval for D.Tech programmes in the following CESM categories – 01, 03, 04, 05, 07, 08, 09, 10, 12, 15, 16, 21 and 22. TUT agrees that the following CESM’s are not approved for Doctoral programme offerings: CESM 02, 06, 11, 19 (see notes to revised Consolidated PQM). The non-approved Doctorate programmes do appear on the Qualification list due to pipeline students that still needs to complete, however there are no new intakes within programmes that are not approved.

An academic audit was conducted during 2005. A programme viability model was used to determine the cost-effectiveness (financial viability) of programmes. The template that was used indicated the income (subsidy relating to teaching input and teaching output units, tuition fees), direct expenditure (salaries, operational, capital) and indirect expenditure (staff, students and space) per programme. This in return gave an indication of the student inflows (teaching input units generated), student outflows (teaching output units generated) as well as the staffing of each programme.  The outcome indicated that currently from 370 Programme clusters only 58.9% of TUT’s academic programmes are NOT duplicated and also Cost effective; 32,2 % are duplicated (of which some are cost effective), and 8,9% are not cost effective but seen as strategic important programmes (see p. 92).

B.    STUDENT ENROLMENT PLANNING

- Student enrolment

Table’s a-k (p.109 – 111) represents HEMIS data for 2004 that were submitted during 2005 to the DoE and correspond with the Institutional Data Profiles (2000 – 2004) provided by the DoE. The classification of the B.Tech programme in Table d as a postgraduate qualification is an oversight. As the B.Tech is an undergraduate programme, TUT recognizes that the institution has currently an undergraduate enrolment shape of 95% undergraduate of the total Headcount or 97% within the contact mode.

The total enrolment growth of 7% between 2003 and 2004 is indicated in Table a (p109), which represents a growth of 11% in Distance Education offerings. TUT is managing its enrolment to the ministerial capping of 60 000 by decreasing the intake of students in the teacher distance programmes towards a 3000 Headcount enrolment in 2009 as explained on page 22. A phase out plan for the programmes, M. Tech: Education Management and B.Tech Education Management on distance mode, is available for confirmation. The effects of the enrolment growth; change in enrolment shape; and the way TUT will manage it, are explained in Section B as part of the Turn Around strategy.

TUT is also in a process to develop its planned enrolments for 2006-2010 which have to be submitted to the DoE by end of March 2006.  The future shape of 40% FTE enrolments in SET and five priority areas will be reflected in the data. TUT is also projecting a future growth of 8 % towards postgraduate enrolments (contact) to be reached in 2010. However this will be done in line with applicable human resource expertise and increase of the staff qualification profile towards a 15 % doctorate in staff qualifications which is currently at 9%. Therefore the rational of TABLES 3-5 (p.180 – 182) is still applicable but will be corrected by using the correct HEMIS data for 2004 and 2005 for the data profile of 2006-2010, as these tables were prepared during 2004 and based on live data of the merged ITS system. (See revised Tables 5 – 20).

- Student Performance

TUT is aware of the low success rate of 66% and a graduation rate of 15% during 2004. A new educational intervention is formulated as an “Academic Development Support Strategy” (see IOP 3.7, p. 36-42). This strategy will be supported by a consolidated structure as indicated in Scenario B, page 100 and 102.

The low success rate of 54% on Postgraduate level is influenced by the performance of the teacher distance programmes (49%). This will be addressed through the phasing out of the M.Tech Educational Management as stated earlier. Professional staff development interventions are currently been implemented of which a capacity building programmes on supervision skills is a priority. Other interventions to increase the research output are indicated in Section B as part of the Turn Around strategy.

C.    ACADEMIC STAFF PROFILE AND PERSONNEL EXPENDITURE

The current staff profile was presented in Tables g-k (p.110, 111) of the IOP, as submitted to the DoE.  This statistics formed part of the HEMIS submission for 2004. Table i is reflecting data that were drawn from ITS data and should therefore not have been included. Tables 10 and 11 (page 187) have provided projections based on the proposed 1:25 FTE staff student ratios. TUT has proposed a 1:25 FTE staff : student benchmark to be reached in  2009, which is in line with the national targets, as well as to align its salary expenditure to the national benchmark of 62.5%. However, it is clear that the current salary expenditure of 71% does not provide TUT with substantial income to increase its staff complement.  TUT has agreed towards new benchmarks of 1:30 FTE staff : student ratio and a salary expenditure of 65% to be reached in 2010. Various actions, that are affordable and sustainable, are proposed to create the change in Staff profile. The staff profile that will support the proposed PQM is portrayed in Tables 16 and 17.  This will be discussed in Section B as part of the Turn around strategy.

D.    FINANCIAL IMPLICATIONS

The following Financial statements are an indication of TUT’s financial status for the period ended 31 December 2005. A proposed budget for 2006 is also indicated.

- Consolidated Income statement

- Cash Flow statement

- Balance Sheet

| BALANCE SHEET AT 31 DECEMBER 2005 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2nd REVISED BUDGET 2005 | YEAR TO DATE 2005 |  |  |  |  |  |  | BUDGET 2006 |  |  |  |  |
|  |  |  |  |  | R'000 |  |  |  |  | R'000 |  |  |  |  |
| ASSETS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROPERTY, PLANT & EQUIPMENT |  | 793,535 |  |  | 701,902 |  |  |  |  | 694,242 |  |  |  |  |
| INVESTMENTS |  | 110,231 |  |  | 110,231 |  |  |  |  | 197,453 |  |  |  |  |
| Fixed Deposits & Funds On Call |  | 0 |  |  | 34,728 |  |  |  |  | 87,222 |  |  |  |  |
| Listed Co.: Sanlam Ltd |  | 1,557 |  |  | 1,637 |  |  |  |  | 1,557 |  |  |  |  |
| Old Mutual PLC |  | 895 |  |  | 1,123 |  |  |  |  | 895 |  |  |  |  |
| Investment Policies |  | 76,965 |  |  | 52,143 |  |  |  |  | 76,965 |  |  |  |  |
| Retention Money |  | 570 |  |  | 122 |  |  |  |  | 570 |  |  |  |  |
| Foundation Investments |  | 865 |  |  | 796 |  |  |  |  | 865 |  |  |  |  |
| Guaranteed securities fund |  | 4,000 |  |  | 4,000 |  |  |  |  | 4,000 |  |  |  |  |
| Redemption fund investment |  | 25,379 |  |  | 15,682 |  |  |  |  | 25,379 |  |  |  |  |
| LOANS |  | 285 |  |  | 285 |  |  |  |  | 285 |  |  |  |  |
| CURRENT ASSETS |  | 104,813 |  |  | 127,799 |  |  |  |  | 103,745 |  |  |  |  |
| Inventory |  | 7,052 |  |  | 7,076 |  |  |  |  | 7,501 |  |  |  |  |
| Trade and Other Receivables |  | 96,968 |  |  | 119,931 |  |  |  |  | 95,453 |  |  |  |  |
| Deposits and Cash |  | 792 |  |  | 792 |  |  |  |  | 792 |  |  |  |  |
| TOTAL ASSETS |  | 1,008,863 |  |  | 940,217 |  |  |  |  | 995,725 |  |  |  |  |
| EQUITY AND LIABILITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FUNDS EMPLOYED |  | 328,241 |  |  | 229,745 |  |  |  |  | 328,092 |  |  |  |  |
| Accumulated funds |  | -68,924 |  |  | -168,200 |  |  |  |  | -69,853 |  |  |  |  |
| Specifically Funded -restricted |  | 25,482 |  |  | 25,482 |  |  |  |  | 25,482 |  |  |  |  |
| Property, plant and equipment funds |  | 375,028 |  |  | 375,808 |  |  |  |  | 375,808 |  |  |  |  |
| Utilised Funds |  | 383,039 |  |  | 322,061 |  |  |  |  | 322,061 |  |  |  |  |
| Unutilised Funds |  | -60,978 |  |  | 780 |  |  |  |  | 780 |  |  |  |  |
| Unutilised Funds - Restricted |  | 24,788 |  |  | 24,788 |  |  |  |  | 24,788 |  |  |  |  |
| Debt Redemption Funds |  | 28,179 |  |  | 28,179 |  |  |  |  | 28,179 |  |  |  |  |
| Residences Fund Restricted |  | -3,345 |  |  | -3,345 |  |  |  |  | -3,345 |  |  |  |  |
| LONG TERM LIABILITIES - INTEREST BEARING |  | 192,985 |  |  | 243,707 |  |  |  |  | 265,233 |  |  |  |  |
| LONG TERM LIABILITIES - NON INTEREST BEARING |  | 333,615 | 313,576 |  |  |  |  |  |  |  |  |  |  | 313,576 |
| CURRENT LIABILITIES |  | 154,022 |  |  |  | 153,189 |  |  |  | 88,824 |  |  |  |  |
| Trade and Other Payables |  | 57,645 |  |  |  | 94,253 |  |  |  | 43,488 |  |  |  |  |
| Overdrafts |  | 96,378 |  |  |  | 58,936 |  |  |  | 45,336 |  |  |  |  |
| Short Term Portion of Long Term Loans |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  |  |
| TOTAL EQUITY AND LIABILITIES |  | 1,008,863 |  |  |  | 940,217 |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | 995,725 |  |  |  |  |
| # RATIOS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Equity : Funds Employed / Total Assets |  | 32.5% |  |  |  | 27.5% |  |  |  | 32.3% |  |  |  |  |
| Funding : Debt (interest-bearing)/ Funds Employed |  | 58.8% |  |  |  | 83.1% |  |  |  | 66.2% |  |  |  |  |
| Solvency :Total Assets/Total Liabilities |  | 2.907 |  |  |  | 2.555 |  |  |  | 2.537 |  |  |  |  |
| Liquidity : Current Assets/Current liabilities |  | 0.681 |  |  |  | 0.834 |  |  |  | 0.519 |  |  |  |  |
| Financing : Interest Cost / Interest Bearing Liabilities |  |  |  |  |  | 9.5% |  |  |  | 13.7% |  |  |  |  |
| Interest Bearing Liabilities/Total Assets |  | 19.1% |  |  |  | 22.9% |  |  |  | 21.4% |  |  |  |  |
| Non-Interest Bearing Liabilities/Total Assets (Staff obligations) |  |  |  |  |  |  |  |  |  | 28.3% |  |  |  |  |

| # CASH FLOW STATEMENT FOR THE PERIOD ENDED 31 DECEMBER 2005 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2nd REVISED BUDGET 2005 |  | Unaudited YEAR TO DATE 2005 |  | BUDGET 2006 |
|  |  |  | R'000 |  | R'000 |  | R'000 |
| CASH FLOW FROM OPERATING ACTIVITIES |  |  |  |  |  |  |  |
| Cash Receipts from Students and Government |  |  | 1,343,776 |  | 1,502,374 |  | 1,482,010 |
| Cash Paid to Suppliers and Employees |  |  | -1,296,607 |  | -1,463,673 |  | -1,333,637 |
| Cash Generated From Operations |  |  | 47,169 |  | 38,700 |  | 148,373 |
| Investment Income |  |  | 9,534 |  | 12,419 |  | 11,932 |
| Finance Charges |  |  | -35,876 |  | -20,414 |  | -34,028 |
| Net cash from operating activities |  |  | 20,827 |  | 30,705 |  | 126,277 |
| CASH FLOW FROM INVESTING ACTIVITIES |  |  |  |  |  |  |  |
| Proceeds on disposal of property, plant & equipment |  |  |  |  |  |  |  |
| Additions to Property, plant & equipment |  |  | -61,440 |  | -42,133 |  | 0 |
| Debt Redemption Investments |  |  | 0 |  | -4,127 |  | 0 |
| (Increase) / decrease in long term investments |  |  | 0 |  | 0 |  | -87,222 |
| Change in non-current receivables |  |  | 0 |  | 0 |  | 0 |
| Cash utilised in investing activities |  |  | -61,440 |  | -46,260 |  | -87,222 |
| CASH FLOW FROM FINANCING ACTIVITIES |  |  |  |  |  |  |  |
| Proceeds from interest-bearing borrowings |  |  | 0 |  | 0 |  | 0 |
| Long Term Loans redeemed |  |  | -7,343 |  | -20,414 |  | 0 |
| Redemption of Long Term Staff Liabilities |  |  | -25,455 |  | 0 |  | -25,455 |
| Cash from financing activities |  |  | -32,798 |  | -20,414 |  | -25,455 |
| Increase/(Decrease) in Cash and Cash Equivalents |  |  | -73,412 |  | -35,970 |  | 13,600 |
| Cash and Cash Equivalents at beginning of period |  |  | -22,966 |  | -22,966 |  | -58,936 |
| Cash and Cash Equivalents at end of period |  |  | -96,378 |  | -58,936 |  | -45,336 |

CONSOLIDATED INCOME STATEMENT FOR THE PERIOD 31 DECEMBER 2005

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2nd REVISED BUDGET 2005 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Unaudited YEAR TO DATE 2005 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET 2006 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL INCOME |  | Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,320,516 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,504,961 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,418,242 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECURRENT INCOME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,312,784 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,497,443 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,404,660 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Government subsidy | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 707,445 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 709,418 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 807,300 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 700,102 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 701,020 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 771,300 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Upgrading of residence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 36,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interest & Assessment Rates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7,343 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8,398 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Own Income | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 595,805 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 775,606 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 585,428 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tuition Fees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 429,962 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 399,856 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 417,586 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resident & Restaurant Fees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 79,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 76,573 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 85,253 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Donations, Research, Bursaries & Projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 23,500 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 175,986 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 26,226 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sale Of Goods & Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 35,917 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 50,473 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 36,432 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Miscellaneous |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 27,426 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 72,718 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 19,932 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Investment Income | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 9,534 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12,419 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 11,932 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NON RECURRENT INCOME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other Designated Fees income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7,732 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7,519 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13,582 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL EXPENSES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,319,674 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,602,615 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,407,116 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECURRENT ITEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,268,757 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,550,534 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,303,932 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Personnel | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 724,112 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 926,309 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 736,034 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General Operating | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 383,214 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 472,063 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 494,254 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Short Courses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 33,529 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 50,473 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 33,700 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Residence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 90,911 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Depreciation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 6,509 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 81,274 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7,661 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finance Costs | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,482 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20,414 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 32,284 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SURPLUS/(DEFICIT) BEFORE NON RECRUITMENT ITEMS 51,759 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -45,573 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 114,309 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NON RECURRENT AND DESIGNATED ITEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 50,917 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 52,081 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 103,184 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accrued Leave Pay Provision |  |  |  |  |  |  |  |  |  |  |  | 3,752 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 26,927 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12,763 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Pension Deficit Funding |  |  |  |  |  |  |  |  |  |  |  | 5,065 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12,402 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8,770 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health Care Liabilities |  |  |  |  |  |  |  |  |  |  |  | 17,446 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,234 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 25,448 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other Designated Fees expenses |  |  |  |  |  |  |  |  |  |  |  | 24,654 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7,519 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20,203 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Upgrading of residence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 36,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SURPLUS/(DEFICIT) FOR THE YEAR |  |  |  |  |  |  |  |  |  |  |  |  |  | 842 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -97,655 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 11,126 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RATIOS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finance Cost /Total Income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2.3% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.4% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2.3% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Surplus Before Appropriations /Total income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3.9% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3.5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7.3% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Surplus (shortage) for the year /Total Income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.1% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -6.5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.8% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Personnel Expenses/Total Income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 54.8% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 61.6% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 51.9% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Subsidy / Total Income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 53.6% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 47.1% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 56.9% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Fees / Total Income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 38.5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 31.7% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 35.5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## SECTION B - PREFERED SCENARIO (B)

TUT has agreed on Scenario B as the preferred Scenario. This was approved by Council during November 2005. The rational and principles of Scenario B are portrayed in Chapter 5 of the IOP (p. 92).

- Tshwane region

It was approved by Council (November 2005) that the current 11 Faculties will be consolidated to 7 Faculties and each Faculty will be located on a specific learning site (see p. 93). To ensure cost effectiveness and eliminate duplication of departments and academic programmes, a set of quantitative and qualitative criteria were applied to consolidate some of the departments. The number of current academic units will be consolidated to 65. This process will be scrutinised to identify even further consolidation under the leadership of the newly appointed Executive Deans and should be finalised by April 2006 (see Planning Framework for 2006). The effect and impact of the consolidation and reduction of academic entities will be noticeable only after a five year period. However, a financial forecasting will be conducted to determine the immediate and long term financial gain and impact.

- Mpumalanga province based learning sites

Scenario B also proposes a change in profile for the Witbank and Nelspruit learning sites to be phased in from 2007. These learning sites will fulfill and support the regional focus of each learning site, which are Industrial related in the case of Witbank, and Services related in the case of Nelspruit. Synergy will be ensured between the two learning sites as well as with the NIHE.

The new focus areas for the Witbank and Nelspruit learning sites within the new Faculty structure are as follows: Witbank - Engineering and ICT; Nelspruit - Economic Sciences and Social Sciences. It was agreed that programmes offered by the Management Faculty will be shared between the two learning sites. Witbank will offer Office Management Technology and HR Management, Nelspruit will offer Marketing and Tourism (is also seen as a focus area for Nelspruit campus).

A future scenario will be developed during 2006 and will be based on the Provincial Growth and Development Strategy of the Mpumalanga Province as well as the Provincial Human Resource Development Strategy. TUT is aware of the launching of the NIHE during 2006, but need clarity on the ramifications of implementation.  A workshop is arranged for the 22 March 2006.

- Limpopo Province based learning site

In order to contribute to the economic development strategy of the province, the Polokwane learning site can become a centre of excellence in higher education providing programmes that are relevant to local businesses and government’s human resources needs. The focus will be on providing undergraduate programs in the focus area of Social and Management Sciences with the following as priorities: Public Management and Safety & Security (Policing);  Human Resource development; A possible introduction of the ND Tourism; Internal Auditing, Finance and Accounting; and ICT type of programmes.

A future scenario will be to focus on potential economic development areas for the Province.

- Support services

It was evident that all support and administrative services had to be aligned to the Academic Structure (p99).  Duplicated functions and services were identified and consolidated (implementation of consolidation to be finalized in February and March 2006 – see planning framework 2006). Decentralized services to the learning sites were identified and the relocation of centralized management functions to a specific learning site was agreed. Re-location of central management functions has to be within the space constraints of the applicable learning site and will only be implemented when the plan indicating the movement of relocation has been approved by Council in September 2005.

The distribution of the 21 Central management functions between the Pretoria, Soshanguve and Ga-Rankuwa learning sites are as follows: Pretoria - 11; Soshanguve - 5; Ga-Rankuwa – 5 (see IOP  p. 99 – 102).

The organizational structure, as presented in Diagram 14 (IOP p 104), has been approved with immediate effect from January 2006. Levels 1-4 is designed to reduce the status quo number of 75 to 21 officials with 4 officials on level 2, 12 on level 3 and 5 on level 4 and a cost saving of R20.9 million.

A.	PROPOSED NEW PROGRAMME AND QUALIFICATION MIX (PQM) 2006 - 2010

The proposed new programmes as indicated in Table D and the proposed PQM for 2005 – 2007 as indicated in TABLE 2a, p 175-179) were reviewed (February 2006) and are therefore not applicable anymore. It is proposed that TUT will introduce seven new programmes in new cells and fourteen (14) programmes in cells that TUT are already active in during 2006 – 2010. Eleven (11) programmes will be phased out (see notes to proposed PQM). Six programmes have been identified as possible new areas, but are subject to a thorough labour market analysis where upon a business plan will be developed. It is also proposed that these programmes will be curriculated toward the new HEQF. The six Programmes that were not approved by the DoE will be resubmitted again, with an understanding of the impact on the infrastructure and human resources needs.

The outcome of the Student enrolment planning process was informed by the new identified Enrolment Planning Statements which will be submitted to the DoE by the end of March 2006. These will be incorporated into the Academic Plan that will be submitted to the Council in June 2006. (See Planning Framework 2006).

The proposed PQM will be aligned to the rationale of Scenario B (see IOP, p. 92) especially relating to the learning sites in the Mpumalanga Province (see IOP, p 95).

The new proposed PQM for TUT 2006 – 2010 is portrayed in SECTION E and indicates the growth priority areas in CESM’s 07, 09, 15 and on post graduate level in CESM 04. The detailed tables will be submitted to the DoE as a comprehensive document on TUT’s Enrolment planning statements.

B.	PROPOSED STUDENT ENROLMENT PROFILE

Agreement was reached on the following priority areas which will be submitted to the DoE as TUT’s Enrolment planning statements:

- Teacher education (Science, Mathematics and Technology) in the contact mode, as well as Teacher training in the GET band.

- Tourism;

- Biotechnology (life sciences) with special focus on the chain of food technology, processing, safety and security;

- Water care (environmental sciences) with specific focus on water science/technology, biodiversity and conservation;

- Health Sciences relating to Nursing, Environmental Health, Dental Technology and Dental Assisting, Pharmacy, Biomedical Technology, Clinical Technology, Veterinary Technology, Radiography, Biokinetics, Somatology, Medical Orthotics and Prosthetics and Occupational Therapy Assistants.

- Postgraduate enrolments within the Management Sciences with specific focus on entrepreneurship, organizational leadership, marketing and logistics and Human Resource management as well as the MBA

Changes in TUT’s proposed institutional profile (as indicated in the IOP, 3.2, p. 21) are being indicated within the following framework:

- An overall reduction of the Total Headcount of TUT to 60 000, to be reached in 2009.

- A change in shape with regard to the mode of delivery by reducing the Distance student enrolment from 19% in 2005 to 7% in 2010 which relates to 4000 Headcount enrolment of which 3000 Headcount enrolment will be in Distance Teacher Education and 1000 in Policing, to be reached in 2010. TUT is currently conducting a feasibility study towards all Distance education programmes. The outcome of the study will effect the Enrolment Headcount projections with regard to the shape of enrolments in the different modes of delivery.

- Maintaining an 83% enrolment of African students in the Contact mode and a 50 % ratio between Male and Female enrolments.

- Increasing Enrolments to 40% within the SET major fields of study with a 35% in Business and Commerce and a 25% enrolment towards the Humanities

- Increasing post graduate enrolments to 8% on contact mode

A summary of the current enrolment (2005) and progressive movement towards 2010 is indicated in Table one. The percentages for 2006 have been already implemented through a Student enrolment Model and strategies towards the proposed growth have been developed.

C.    PROPOSED HUMAN RESOURCE PROFILE AND SALARY EXPENDITURE

It is proposed to reduce the Ratio for FTE Instructional/research professional and FTE student enrolment from 1:38 in 2004 to 1:31 in 2010, and not 1:25 as indicated in the IOP. The total of % of personnel salary expenditure per total distributable income will be reduced from 71% (2005) to 65% (2010).

The proposed staff profile is indicated in Tables 16 and 17.  It is proposed that the permanent staff profile be reduced and stabilized at 2600 with 1326 as total Professional staff and 1274 as Non Professional staff in 2010.  This is also enforced by implementation of the approved structure by reducing the Executive management Professionals to 39 (includes level 5 positions).

The reason for increasing Support Professionals relates to the new Educational intervention (Academic Development Support Strategy).  Technical and Crafts/Trades staff component will be kept at 1% of the total staff profile.  Non-professional staff (permanent) to be decreased to 962 to reflect the situation before the merger (strategies to be developed), although it will still reflect 37% of the total staff complement.

It is also proposed to decrease the total FTE staff complement by reducing the temporary staff complement with a factor of 0,35 as indicated in Table 17.  The major reduction will be focused on the Non-Professional staff category.  This benchmark was determined through an analysis of the years 2000 – 2004 averages.

The implementation of Scenario B will be earmarked by the following:

- Implementing the new approved organizational structure. (Levels 1 – 6)

- Increasing income through improvement of Teaching output and Research output.

- Reducing the Salary Budget (Staff Costs) to 65% in 2010 through a short term and long term strategy.

The merger guidelines do provide National Benchmarks.  TUT has indicated in the IOP a desire to reach the stated national benchmarks.  Due to financial constraints, TUT adjusted targets to reflect a more realistic and achievable situation,  as indicated in the following Table.  These new targets form part of the Turn-around Strategy, which proposes a financial viability.

Benchmarks and Projected Expenditure

| EXPENDITURE CATEGORY | 2006 (ALLOCATED) | 2010 (PROJECTED) | MERGER GUIDELINES |
| --- | --- | --- | --- |
| PERSONNELL (includes Employment Benefits) | 70,38% | 65% | 55 – 62,5% |
| Goods & Services (Includes Operational, Corporate & Strategic) | 25,3% | 29% | 35,5 – 29% |
| Finance Cost (Includes Interest & Loan redemption) | 2,9% | 2% | 2 – 3% |
| Capital Expenditure | 0,69% | 3% | 6,5 – 4,5% |
| Rationalization Cost | 1,38% | 0% | 0% |
| Surplus | 1% | 1% | 1% |
| TOTAL | 100% | 100% | 100% |

Therefore, the following benchmarks have been adjusted within TUT’s Strategic Planning Framework for 2006-2010. The National benchmarks are indicated in brackets.

- Undergraduate Success rate of 70% (75%), which is currently at 66%

- Graduation rate of 20% – (22,5%), which is currently at 15%

- Staff student ratio (FTE) of 1:30 (1:25), which is currently at 1:36 in 2005

- SET  FTE enrolment of 40% (40%), which is currently at 33,9%

- Research output of 0,18 weighted units per FTE academic staff member (0,5)

- Academic Staff Qualifications to be improved towards

-	Masters 40%        (40%), currently at 32,2%

-	Doctorates 15%    (20%), currently at 9%

- 40% Black representation in Research/Instruction  (40%), which is currently at 34%

- 50% Representation of female in Research/Instruction (50%), which is currently at 40%.

The Framework of the Turn-Around strategy is based on the implementation of Scenario B where the consolidation of Faculties, Departments & Academic programmes, will eliminate all duplication.  The implementation of the new organizational structure will result in a long term saving of R20,9 million.  The following will also be addressed as part of the Turn-Around strategy:

- The student FTE ratio to Headcount enrolment will be increased from 69% in 2004 to 75% in

2010.

- Enrolment growth is proposed in a ratio of  - SET /  B&C  /  HUM (40:35:25) and Post graduate enrolment (contact)  to 8%

- Improvement of graduation & success rates to 20% and 70%.

- Consolidation of Support Services will lead to a streamlined cost effective support structure, and reduced Non-professional administrative staff.

- Consolidation of Class Fees and the consolidation of income resources together with a decrease of expenditure will result in a higher surplus which can then be applied to appropriate areas.

This will be substantiated by the following planning and management interventions.

HR PLANNING AND MANAGEMENT

The following short term and long term strategies relating to HR planning and management will reduce the salary budget to 65% in 2010.

SHORT TERM STRATEGY:

- Cutback of 2% in total distributable budget (R22 million) in the following categories:

-	Retention Staff will not be extended from 2005

-	Support temporary staff appointed in 2005

    - Support temporary staff appointed in 2004

    - Support temporary staff appointed in 2003

    - Academic temporary staff

This results in a reduction of 4 million in Academic salary expenditure and a reduction of 18 million in Support staff salary expenditure.

LONG TERM STRATEGY:

The Long-term strategy relating to the HR Planning and management is based on the restructuring and re-organization of TUT towards the stated Scenario B.

The consolidation of Faculties/departments/support will be informed by a needs analysis of staff and staff requirements per faculty and per support directorate.

- It is proposed that the Academic : Administrative Staff ratio be reduced from 1:2,2 to 1:1,7.  This is achievable through redeployment, transfers and the rationalization of temporary and part time staff complement in the mentioned categories.

- To reach a 1:30 staff: student FTE ratio the reduction of FTE enrolled students in distance programmes is proposed with a realistic increase in the Research/Instructional category

      - This is based on a reduction of student enrolment

Head count to 60 000 and an FTE of 44 500.

FINANCIAL & QUALITY PLANNING

SHORT TERM STRATEGY:

The following short term strategy, relating to Financial & Quality Planning will be achieved through a change in shape of enrolment to TUT Strategic Benchmarks and an increase in FTE credited students.

- Student enrolment will be managed through a stricter application of the Exclusion Policy

- TUT will embark on Academic development interventions to increase the through put rate.

- Intensive activities to increase R&I outputs will be embarked upon.

- Selection criteria for First time entering students will be reviewed

- Alignment of the class fee structures will be done

LONG TERM STRATEGY:

The long term strategy relating to Financial & Quality planning is to have a growth to 40% in Science, Engineering & Technology programmes although it would not necessary lead to an increase in the Teaching input grant.  However, it is proposed that a

- Post-graduate growth to 8% and increase in graduation rate will lead to improved Research output.

- A higher % of FTE enrolled students in undergraduate programmes will be ensured through academic development interventions, and refined selection criteria

- Increase success rate to 70% will lead to an increase in the Teaching output grant.

- Simultaneous research capacity building amongst all lecturing staff will eventually promote a  0,18 weighted research output and supervision of M & D students will be improved in order to increase M & D output.

SECTION C – IMPLEMENTATION PLAN AND FINANCIAL PROJECTIONS

TRANSFORMATION OF TUT TO THE DESIRED POSITION

TUT is facing numerous challenges relating to the equalization of service levels and the standardization of facilities across all learning sites to reflect a unified institution, implementation of the preferred scenario and becoming an established University of Technology.

This section will provide additional information with regard to above stated issues as it was extensively discussed in the IOP.

### IMPLEMENTATION TOWARDS STANDARDISATION OF SERVICE LEVELS

The following summarizes the serious backlog that TUT has with regard to maintenance and upgrading of buildings and facilities, as well as equipment and infrastructure.  In most cases it was only possible to provide an estimated cost due to the fact that no final quotes or tenders have been obtained. The financial needs to address the current backlog at TUT are indicated.

1.      Backlog on maintenance and upgrading of buildings and facilities

- During May and June 2004, a company of Quantity Surveyors and Valuators, conducted a comprehensive audit and evaluation of all TUT’s buildings.  The AfriQS Report consisted of the surveying; auditing and evaluation for a renovation/maintenance plan for all buildings of TUT as well as a projected cost cash flow over a period of five years.

- To bring all the buildings of TUT to a habitable, acceptable standard will cost the institution R131 million (VAT exclusive) over a five year period, with the costs calculated at projected building costs as in June 2005.

The needs at the different teaching and learning sites are as follows:

| Teaching & Learning Sites | Information | Estimated Cost |
| --- | --- | --- |
| Ga-Rankuwa | Upgrading of residences | R18,2 million |
|  | Other buildings | R11 million |
| Soshanguve | Upgrading of residences | R27,8 million |
|  | Other buildings | R19,3 million |
| Pretoria and Satellites at Polokwane, Witbank and Nelspruit | Upgrading of residences | R7,1 million |
|  | Other buildings | R48 million |
| TOTAL OF AfriQS REPORT |  | R131 million |

Note:  An allocation of R 36 million has been granted for the upgrading of Residences in Ga-Rankuwa and Soshanguve

(13 February 2006) by the Minister of Education.

- The total renovation cost of buildings within the “urgent” category (to be completed in year 1 to 2) amounts to R75 million, of which a total of R53 million is earmarked for residences, as it is identified as a high priority.

- The majority of improvements on the Pretoria and Satellite campuses have a lower priority due to the fact that the deferred maintenance is minimal as compared to the northern campuses, according to the AfriQS Report.

- Serious concerns with regard to Occupational Health and Safety specifications of laboratories have also been reported.  This includes the following to meet the minimum requirements of the Act:

- Additional safety doors in all laboratories on all campuses,

- Inadequate air-conditioning in laboratories,

- Upgrading of electrical wiring and cable networks

An additional estimated amount of R15 million is needed to address this serious backlog on all six teaching and learning sites.

- The total of these backlogs amounts to R131 million plus R15 million, i.e. R146 million.

2.     Backlog on alterations and expansions of buildings and facilities if the status quo prevails

- The Faculty of Education has a backlog on expansion and alterations to Engineering Technology Education laboratories on the Soshanguve and Pretoria campuses at an estimated cost of R4,8 million.

- The Faculty of Arts has identified backlogs on buildings and facilities for different departments at a total estimated cost of R10 million.

- The Faculty of Health Sciences has a backlog on lecture hall and ablution facilities at the Soshanguve Campus (Department of Environmental Health) at an estimated cost of R0,25 million.

- The Faculty of Natural Sciences has a serious backlog with regard to the upgrading and expansion of laboratories to accommodate students at the Pretoria Campus and at both the Ga-Rankuwa and Soshanguve Campuses.  An estimated additional amount of at least R12 million is needed to address the backlogs.

- The Faculty of Engineering, currently operating on five of the six teaching and learning sites, has a serious backlog on alterations and expansion of the different engineering laboratories across the different disciplines.  This is of key importance in order to maintain the accreditation status at ECSA.  The estimated cost amounts to R28 million.

- There is a backlog for the upgrading of the Contact Centre at an estimated cost of R0,5 million.

- The refurbishment of the Metro Skinner building, including facilities for the Institute for Economic Research on Innovation, at an estimated amount of R3,5 million.

3.          Backlog on equipment and infrastructure upgrading

- It is estimated that an annual additional amount of R43 million for a period of 4 to 5 years will be needed to address the backlog on equipment and infrastructure.  This amount is made up from –

- R15 million annually for the ICT (Information and Communication Technology) and ITP (Integrated Technology Plan) environment;

- R4 million annually for computer replacement in the academic environment, due to ageing;

- R20 million annually for the replacement and upgrading of science- and technology-related equipment in laboratories;

- R4 million annually for multimedia equipment upgrading in all lecture facilities on the six teaching and learning sites.

- There is also a serious backlog with regard to security access and surveillance system equipment, in particular at the Ga-Rankuwa and Soshanguve campuses, as well as in the residences linked to these campuses.

4.	Financial summary on backlogs relating to the current campus topography

| ITEM |  | ESTIMATED COST |
| --- | --- | --- |
| 1 | Backlog on maintenance and upgrading of buildings and facilities | R146 million |
| 2 | Backlog on alterations and expansions of buildings and facilities | R59 million |
| 3 | Backlog on equipment and infrastructure upgrading at R43 million per annum for 2006 - 2009 | R215 million |
| 4 | TOTAL | R420 million |

5.    Financial projections

The projected financial impact is presented in Schedule 1, section E.  This will have to be calculated into the financial projections as portrayed in Section D once clarification is obtained on the financial position of:

- Grants from the Department of Education

- Loan agreements

- Spending program

### B.	IMPLEMENTATION OF SCENARIO B – SHORT TERM (3 – 5 YEARS)

With affirmation of the newly constituted faculties, it is realistic to indicate that movement and relocation of the Faculties will take place within a period of 3 to 5 years, with relocation and enrolment of first years according to the new Faculty topography, to commence during January 2007. Logistical and space planning are imperatives so that it will support the topography. Space allocation has to be properly investigated and planned in order to enhance the relocation of Faculties. A financial forecasting of proposed relocations will have to be conducted during 2006. This will be substantiated by a structured implementation and monitoring plan. This plan will be developed to ensure that the relocation is cost effective and add value. It is proposed that a director for Merger implementation facilitate the restructuring process. A possible financial implication of R1 million is foreseen to conduct the cost analysis. 	Preliminary calculations indicated that the proposed relocations of the Faculties will amount to approximately R450,1 million. This will be confirmed by the cost analysis and financial forecasting process.

An Implementation plan is in the process of development (see planning framework for 2006) which will state inter alia the process of relocation; phases of movement of Staff and student / equipment; preparation and allocation/restructuring of venues such as residences/ lecture halls / office space; testing and upgrading of ICT infrastructure applicable to the faculty environment; ITS preparation for the new Academic Qualification Structure linked to the new academic entities / budgeting / payroll.

1.	Financial needs to fund the changes in the topography

This section refers to the costs related to the relocation of faculties and support services in line with the proposals in paragraph 5.2 and 5.5 of scenario B of the IOP.

A simulation model was developed to exchange space between target campuses based on data contained in the TUT space program.

- Basic assumptions

A comprehensive list of assumptions and principles applied is contained in a working document of which the most important are:

- All affected entities should be in a similar position after the IOP implementation.

- All faculties and academic departments will be consolidated on a specific target campus and no fragmentation or duplication will be allowed for.

- It is further assumed that in any department, laboratory formal tuition can be interchanged randomly during any 8-hour period of any day from Monday to Friday.

- Open plan architecture will be considered as the feasible alternative to limit the space that will be required for offices.

- Buffer space need to be created for all relocations, meaning that the space for a faculty or directorate first need to be cleared of the existing inhabitants before refurbishment can start.

- Preliminary cost estimates

The costing was done by applying a rate of R5 000 per m2 to refurbish all vacated space.  The cost for new/reconstructed space was calculated by deducting required space from vacated space per campus and applying a rate of R10 000 per m2.  The effective amount for direct materials and equipment halves when VAT, professional fees, sundries and non-assignable space have been factored in.

The cost estimates from the space relocation model reflects the following preliminary fund requirements:

|  | R’mil |
| --- | --- |
| Faculties: |  |
| Refurbishments | 197,7 |
| Reconstruction | 229,5 |
| TOTAL | 427,2 |
| Support Services: |  |
| Refurbishments | 12,0 |
| Reconstruction | 10,9 |
| TOTAL | 22,9 |
| GRAND TOTAL | 450,1 |

This excludes the following phases:

- Matching of different space categories through detail planning for each faculty.

- Moving of laboratory equipment and the cost involve.

- This exercise will reveal if new lecture halls should be constructed at a particular target campus, or if smaller lecture halls can be converted into other space.

- Sport Business Plan to ensure equity.

- Library and Electronic Resource Centres (ERC) Space.

- Academic programmes will be phased in over three-five years to accommodate the pipe line students.

- Requirements for new residences to limit the transport costs between residences.

- Landscaping and parking needs.

- Sufficient and reliable backup power systems to support the Business Continuity Plan.

Other aspects that might affect the IOP implementation have not yet been fully discounted in the cost, e.g.:

- Relocation allowances to staff and the anticipated higher staff turnover

- Travel reimbursements for shuttle staff during the three year phase-in period to service pipe line students still located on the mother learning sites

- Bussing of students between residences and target campuses

- Cross-subsidies relating to differential residence fees for migrant students.

- Financial projections

The financial projections are presented in Schedule 2, Section E. This does not provide for any financial contributions from external sources.

The impact of these financial charges has not been accommodated in the financial statements of the previous sections.

SECTION D: FINANCIAL PROJECTIONS

The financial projections are based on the various elements and strategies contained in the IOP and are divided into three categories:

- Projected Financial Statements based on the current status and a move towards ideal benchmarks.

- Financial needs to address the current backlogs at the TUT to ensure equal standards at a proper level.  (See Section C)

- Financial needs to fund the changes in the topography to implement the IOP (See Section C).

- PROJECTED FINANCIAL STATEMENTS FOR THE PERIOD 31 DECEMBER 2006 – 2010

The IOP information, the current budget (2006), together with various statistical data, was used to build the Resource Allocation Model (RAM) based on the following principles:

- It uses the new funding framework from the Department of Education as point of departure.

- It is an income-driven model, i.e. all allocations to expenditure categories needs to be funded by the different income streams in principle.

- It incorporates the different benchmarks and performance indicators from government, as well as those agreed upon in the strategic plan of TUT.

- The different parameters included in the model are used as variables so that when they are adjusted the model is automatically updated, showing clearly the impact of the adjustments made on the income generation and resource allocation to different sections of the TUT.

The RAM allocations between income and expenditure categories according to various benchmarks are indicated in the table below:

| RAM% INCOME DISTRIBUTION | EARMARKED | DISTRIBUTABLE |
| --- | --- | --- |
| GOVERNMENT SUBSIDY | % | % |
| Teaching Input | 0.40% | 99.60% |
| Teaching Output Grant | 0.00% | 100.00% |
| Teaching Output Development | 100.00% | 0.00% |
| Research Output Grant | 90.00% | 10.00% |
| Research Output Development | 100.00% | 0.00% |
| Institutional Factors | 0.00% | 100.00% |
| Long term Liabilities | 0.00% | 100.00% |
| Adhoc Grant | 0.00% | 100.00% |
| TUITION FEES |  |  |
| Class Fee | 1.00% | 99.00% |
| Subject Levies | 100.00% | 0.00% |
| Other fees income | 0.00% | 100.00% |
| Other designated fees income | 100.00% | 0.00% |
| Bad debts recovered | 0.00% | 100.00% |
| NON SUBSIDIZED PROGRAMMES | 92.50% | 7.50% |
| RESIDENCES | 100.00% | 0.00% |
| FOUNDATION DONATIONS | 100.00% | 0.00% |
| RESEARCH CONTRACTS | 100.00% | 0.00% |
| INVESTMENT INCOME | 21.79% | 78.21% |
| SALE OF GOODS AND SERVICES | 33.22% | 66.78% |

The projected income for 2007 – 2010 was based on the following assumptions:

Government subsidy		:	5% based on Government’s MTEF framework

Class fees and residences	:	7% based on TUT’s estimated annual increase

Other income streams	:	4% based on the CPIX

- RESOURCE ALLOCATION AND PROJECTED EXPENDITURE

| RAM EXPENDITURE ALLOCATIONS | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- |
| PERSONNEL (Include provision for employee benefits) | 70,38% | 70,38% | 68,59% | 66,79% | 65% |
| GOODS & SERVICES (Include operational, corporate and strategic projects expenditure) | 25,03% | 25,03% | 26,35% | 27,68% | 29% |
| FINANCE COST (Include Interest & Loan Redemption) | 2,90% | 2,90% | 2,60% | 2,30% | 2% |
| CAPITAL EXPENDITURE (Link to depreciation) | 0,69% | 0,69% | 1,46% | 2,23% | 3% |
| SURPLUS | 1% | 1% | 1% | 1% | 1% |
| TOTAL | 100% | 100% | 100% | 100% | 100% |

The Resource Allocation Model determines the operational budgets which, in turn, result in the Financial Statements, as indicated

The following income statement, balance sheet and cash flow statement highlights TUT’s estimated income less expenditure without taking into account any borrowings that TUT may need in the future for any upgrading of buildings or relocations costs.  It also provides for rationalization cost of 1:38% in 2007.

- Schedule 3	:	Balance Sheet

- Schedule 4	:	Income Statement

- Schedule 5	:	Cash Flow Statement

SECTION E

- This section indicates statistical data and financial projections.  The Consolidated PQM, Enrolment planning (2006 – 2010), staff profile to support the proposed enrolment statements and PQM is indicated.

- Schedules 1 – 5 are included.

- The planning framework 2006 is tabled.

| TABLE 1: CONSOLIDATED APPROVED PQM (PROGRAMME QUALIFICATION MIX) FOR TUT (CONTACT) 2004 - 2006 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CESM | MAJOR FIELDS OF STUDY | NOTES | CERTIFICATES: NS + HS | NATIONAL DIPLOMAS | B TECH DEGREE | POST DIP/ GRAD CERT + DIP | NATIONAL HIGHER DIPLOMA | HONOURS DEGREE | M TECH DEGREE | DOTORAL DEGREE + L TECH |
| 1 | AGRICULTURE AND RENEWABLE NATURAL RESOURCES |  |  |  |  |  |  |  |  |  |
| 1a | Agricultural Economics |  |  |  |  |  |  |  |  |  |
| 1b | Agriculture | 1, 2 |  | X | X |  | X |  | X | X |
| 1c | Fisheries |  |  |  |  |  |  |  |  |  |
| 1d | Forestry |  |  |  |  |  |  |  |  |  |
| 1e | All other Agriculture and Renewable Natural Resources |  |  | X | X |  |  |  | X | X |
| 2 | ARCHITECTURE AND ENVIRONMENTAL DESIGN |  |  |  |  |  |  |  |  |  |
| 2a | Architecture and Building Science |  |  | X | X |  |  |  | X |  |
| 2b | Quantity Surveying |  |  |  | X |  |  |  |  |  |
| 2c | Building Management |  |  | X | X |  |  |  | X | W |
| 2d | Town and Regional Planning |  |  |  |  |  |  |  |  |  |
| 2e | All other Architecture and Environmental Design |  |  |  |  |  |  |  |  |  |
| 3 | ARTS, VISUAL AND PERFORMING |  |  |  |  |  |  |  |  |  |
| 3a | Music |  | X | X | X |  |  |  | X | X |
| 3b | Drama |  | X | X | X |  |  |  | X | X |
| 3c | Fine Arts |  | X | X | X |  |  |  | X | X |
| 3d | All other Arts, Visual and Performing |  | X | X | X |  |  |  | X | X |
| 4 | BUSINESS, COMMERCE AND MANAGEMENT SCIENCES |  |  |  |  |  |  |  |  |  |
| 4a | Accounting |  | X | X | X |  |  |  | X | X |
| 4b | Banking and Finance |  |  |  |  |  |  |  |  |  |
| 4c | Business Data Systems and Business Quantitative Methods |  |  |  |  |  |  |  |  |  |
| 4d | All other Business, Commerce and Management Sciences | 3 | X | X | X |  |  |  | X | X |
| 5 | COMMUNICATION |  |  |  |  |  |  |  |  |  |
| 5a | Journalism and Media Studies |  |  | X | X |  |  |  | X | X |
| 5b | All other Communication |  | X | X | X |  |  |  | X | X |
| 6 | COMPUTER SCIENCE AND DATA PROCESSING | 4 |  |  |  |  |  |  |  |  |
| 6a | All computer Science and Data Processing |  | X | X | X |  |  |  | X | W |
| 7 | EDUCATION |  |  |  |  |  |  |  |  |  |
| 7a | Primary |  |  |  |  |  |  |  |  |  |
| 7b | Secondary |  |  | X | X |  |  |  | X | X |
| 7c | Special |  |  |  |  |  |  |  |  |  |
| 7d | All other Education | 5 | X | X | X | X | X | X | X | X |
| 8 | ENGINEERING AND ENGINEERING TECHNOLOGY |  |  |  |  |  |  |  |  |  |
| 8a | Chemical Engineering |  |  | X | X |  |  |  | X | X |
| 8b | Civil Engineering |  |  | X | X |  |  |  | X | X |
| 8c | Electrical Engineering |  |  | X | X |  |  |  | X | X |
| 8e | Mechanical Engineering |  |  | X | X |  |  |  | X | X |
| 8h | All other Engineering and Engineering Technology |  |  | X | X |  |  |  | X | X |
| 9 | HEALTH CARE AND HEALTH SCIENCES |  |  |  |  |  |  |  |  |  |
| 9a | Medicine / surgery |  |  |  |  |  |  |  |  |  |
| 9b | Dentistry |  |  |  |  |  |  |  |  |  |
| 9c | Nursing |  |  | X | X |  |  |  | X | X |
| 9d | All Clinical Health Sciences |  | X | X | X |  | X |  | X | X |
| 9e | Pharmacy |  |  |  | X |  |  |  | X | X |
| 9f | Veterinary Science |  |  | X | X |  |  |  | X | X |
| 9g | Rehabilitation and Therapy |  | X | X | X |  |  |  | X | X |
| 9h | Hospital and Health Care Administration |  |  |  |  |  |  |  |  |  |
| 9i | All other Health Care and Health Sciences |  | X | X | X |  |  |  | X | X |
| 10 | HOME ECONOMICS |  |  |  |  |  |  |  |  |  |
| 10a | All Home Economics | 6, 7 |  | X | X |  | X |  | X | X |
| 11 | INDUSTRIAL ARTS, TRADES AND TECHNOLOGY |  |  |  |  |  |  |  |  |  |
| 11a | All Industrial Arts, Trades and Technology |  |  |  | X |  |  |  | X | W |
| 12 | LANGUAGES, LINGUISTICS AND LITERATURE |  |  |  |  |  |  |  |  |  |
| 12a | Linguistics |  |  |  |  |  |  |  |  |  |
| 12b | Literary Studies |  |  |  |  |  |  |  |  |  |
| 12c | Afrikaans / Nederlands |  |  |  |  |  |  |  |  |  |
| 12d | English |  |  |  |  |  |  |  |  |  |
| 12e | African Languages |  |  |  |  |  |  |  |  |  |
| 12f | Modern European Languages |  |  |  |  |  |  |  |  |  |
| 12g | All other Languages, Linguistics and Literature | 8, 9 |  | X | X |  |  |  | X | X |
| 13 | LAW |  |  |  |  |  |  |  |  |  |
| 13a | All Law |  | X | X |  |  | X |  |  |  |
| 14 | LIBRARIES AND MUSEUMS |  |  |  |  |  |  |  |  |  |
| 14a | All Libraries and Museums |  |  |  |  |  |  |  |  |  |
| 15 | LIFE AND PHYSICAL SCIENCES |  |  |  |  |  |  |  |  |  |
| 15a | Life Sciences | 10 |  | X | X |  |  |  | X | X |
| 15b | Physical Sciences |  | X | X | X |  |  |  | X | X |
| 15c | All other Life and Physical Sciences |  | X | X | X |  |  |  | X | X |
| 16 | MATHEMATICAL SCIENCES |  |  |  |  |  |  |  |  |  |
| 16a | All Mathematical Sciences | 11, 12, 13 |  |  | W |  |  |  | X | X |
| 17 | MILITARY SCIENCES |  |  |  |  |  |  |  |  |  |
| 17a | All Military Sciences |  |  |  |  |  |  |  |  |  |
| 18 | PHILOSOPHY, RELIGION AND THEOLOGY |  |  |  |  |  |  |  |  |  |
| 18a | Philosophy |  |  |  |  |  |  |  |  |  |
| 18b | Science of religion |  |  |  |  |  |  |  |  |  |
| 18c | All other Philosophy, Religion and Theology |  |  |  |  |  |  |  |  |  |
| 19 | PHYSICAL EDUCATION, HEALTH EDUCATION, LEISURE |  |  |  |  |  |  |  |  |  |
| 19a | All Physical Education, Health Education and Leisure | 14 | X | X | X |  |  |  | W | W |
| 20 | PSYCHOLOGY |  |  |  |  |  |  |  |  |  |
| 20a | All Psychology |  |  |  |  |  |  |  |  |  |
| 21 | PUBLIC ADMINISTRATION AND SOCIAL SERVICES |  |  |  |  |  |  |  |  |  |
| 21a | Public Administration | 15 | X | X | X |  |  |  | X | X |
| 21b | Social Work |  |  |  |  |  |  |  |  |  |
| 21c | All other Public Administration and Social Services | 16 | X | X | X |  | X |  | X | X |
| 22 | SOCIAL SCIENCES AND SOCIAL STUDIES |  |  |  |  |  |  |  |  |  |
| 22a | Economics |  | X | X | X |  |  |  |  |  |
| 22b | All other Social Sciences and Social Studies | 17 | X | X | X |  |  |  | X | X |
|  | The highlighted areas in green indicate the variation from the previous PQM documents as approved by the DoE on 26/11/2004 (See Notes) |  |  |  |  |  |  |  |  |  |
| X | The institution has previously been active: (a) All previously approved programmes as well as (b) the new programmes which were specified are approved for 2003 - 2006 |  |  |  |  |  |  |  |  |  |
| W | The previously approved programmes specified HAVE BEEN with drawn for 2003 – 2006 |  |  |  |  |  |  |  |  |  |

| TABLE 2: CONSOLIDATED APPROVED PQM (PROGRAMME QUALIFICATION MIX) FOR TUT (DISTANCE) 2004 – 2006 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CESM | MAJOR FIELDS OF STUDY | NOTES | CERTIFICATES: NS + HS | NATIONAL DIPLOMAS | B TECH DEGREE | POST DIP / GRAD CERT + DIP | NATIONAL HIGHER DIPLOMA | HONOURS DEGREE | M TECH DEGREE | DOTORAL DEGREE + L TECH |
| 1 | AGRICULTURE AND RENEWABLE NATURAL RESOURCES |  |  |  |  |  |  |  |  |  |
| 1a | Agricultural Economics |  |  |  |  |  |  |  |  |  |
| 1b | Agriculture |  |  |  |  |  |  |  |  |  |
| 1c | Fisheries |  |  |  |  |  |  |  |  |  |
| 1d | Forestry |  |  |  |  |  |  |  |  |  |
| 1e | All other Agriculture and Renewable Natural Resources |  |  |  |  |  |  |  |  |  |
| 2 | ARCHITECTURE AND ENVIRONMENTAL DESIGN |  |  |  |  |  |  |  |  |  |
| 2a | Architecture and Building Science |  |  |  |  |  |  |  |  |  |
| 2b | Quantity Surveying |  |  |  |  |  |  |  |  |  |
| 2c | Building Management |  |  |  |  |  |  |  |  |  |
| 2d | Town and Regional Planning |  |  |  |  |  |  |  |  |  |
| 2e | All other Architecture and Environmental Design |  |  |  |  |  |  |  |  |  |
| 3 | ARTS, VISUAL AND PERFORMING |  |  |  |  |  |  |  |  |  |
| 3a | Music |  |  |  |  |  |  |  |  |  |
| 3b | Drama |  |  |  |  |  |  |  |  |  |
| 3c | Fine Arts |  |  |  |  |  |  |  |  |  |
| 3d | All other Arts, Visual and Performing |  |  |  |  |  |  |  |  |  |
| 4 | BUSINESS, COMMERCE AND MANAGEMENT SCIENCES |  |  |  |  |  |  |  |  |  |
| 4a | Accounting |  |  | X | X |  |  |  |  |  |
| 4b | Banking and Finance |  |  |  |  |  |  |  |  |  |
| 4c | Business Data Systems and Business Quantitative Methods |  |  |  |  |  |  |  |  |  |
| 4d | All other Business, Commerce and Management Sciences |  |  | X | X |  |  |  |  |  |
| 5 | COMMUNICATION |  |  |  |  |  |  |  |  |  |
| 5a | Journalism and Media Studies |  | X | X | X |  |  |  |  |  |
| 5b | All other Communication |  |  |  |  |  |  |  |  |  |
| 6 | COMPUTER SCIENCE AND DATA PROCESSING |  |  |  |  |  |  |  |  |  |
| 6a | All computer Science and Data Processing |  |  |  |  |  |  |  |  |  |
| 7 | EDUCATION |  |  |  |  |  |  |  |  |  |
| 7a | Primary |  |  |  |  |  |  |  |  |  |
| 7b | Secondary |  |  |  | X |  |  |  |  |  |
| 7c | Special |  |  |  |  |  |  |  |  |  |
| 7d | All other Education | 5 | X |  | X | X |  | X | X |  |
| 8 | ENGINEERING AND ENGINEERING TECHNOLOGY |  |  |  |  |  |  |  |  |  |
| 8a | Chemical Engineering |  |  |  |  |  |  |  |  |  |
| 8b | Civil Engineering |  |  |  |  |  |  |  |  |  |
| 8c | Electrical Engineering |  |  |  |  |  |  |  |  |  |
| 8e | Mechanical Engineering |  |  |  |  |  |  |  |  |  |
| 8h | All other Engineering and Engineering Technology |  |  |  |  |  |  |  |  |  |
| 9 | HEALTH CARE AND HEALTH SCIENCES |  |  |  |  |  |  |  |  |  |
| 9a | Medicine / surgery |  |  |  |  |  |  |  |  |  |
| 9b | Dentistry |  |  |  |  |  |  |  |  |  |
| 9c | Nursing |  |  |  |  |  |  |  |  |  |
| 9d | All Clinical Health Sciences |  |  |  |  |  |  |  |  |  |
| 9e | Pharmacy |  |  |  |  |  |  |  |  |  |
| 9f | Veterinary Science |  |  |  |  |  |  |  |  |  |
| 9g | Rehabilitation and Therapy |  |  |  |  |  |  |  |  |  |
| 9h | Hospital and Health Care Administration |  |  |  |  |  |  |  |  |  |
| 9i | All other Health Care and Health Sciences |  |  |  |  |  |  |  |  |  |
| 10 | HOME ECONOMICS |  |  |  |  |  |  |  |  |  |
| 10a | All Home Economics |  |  |  |  |  |  |  |  |  |
| 11 | INDUSTRIAL ARTS, TRADES AND TECHNOLOGY |  |  |  |  |  |  |  |  |  |
| 11a | All Industrial Arts, Trades and Technology |  |  |  |  |  |  |  |  |  |
| 12 | LANGUAGES, LINGUISTICS AND LITERATURE |  |  |  |  |  |  |  |  |  |
| 12a | Linguistics |  |  |  |  |  |  |  |  |  |
| 12b | Literary Studies |  |  |  |  |  |  |  |  |  |
| 12c | Afrikaans / Nederlands |  |  |  |  |  |  |  |  |  |
| 12d | English |  |  |  |  |  |  |  |  |  |
| 12e | African Languages |  |  |  |  |  |  |  |  |  |
| 12f | Modern European Languages |  |  |  |  |  |  |  |  |  |
| 12g | All other Languages, Linguistics and Literature |  |  |  |  |  |  |  |  |  |
| 13 | LAW |  |  |  |  |  |  |  |  |  |
| 13a | All Law |  |  | X |  |  |  |  |  |  |
| 14 | LIBRARIES AND MUSEUMS |  |  |  |  |  |  |  |  |  |
| 14a | All Libraries and Museums |  |  |  |  |  |  |  |  |  |
| 15 | LIFE AND PHYSICAL SCIENCES |  |  |  |  |  |  |  |  |  |
| 15a | Life Sciences |  |  |  |  |  |  |  |  |  |
| 15b | Physical Sciences |  |  |  |  |  |  |  |  |  |
| 15c | All other Life and Physical Sciences |  |  |  |  |  |  |  |  |  |
| 16 | MATHEMATICAL SCIENCES |  |  |  |  |  |  |  |  |  |
| 16a | All Mathematical Sciences |  |  |  |  |  |  |  |  |  |
| 17 | MILITARY SCIENCES |  |  |  |  |  |  |  |  |  |
| 17a | All Military Sciences |  |  |  |  |  |  |  |  |  |
| 18 | PHILOSOPHY, RELIGION AND THEOLOGY |  |  |  |  |  |  |  |  |  |
| 18a | Philosophy |  |  |  |  |  |  |  |  |  |
| 18b | Science of religion |  |  |  |  |  |  |  |  |  |
| 18c | All other Philosophy, Religion and Theology |  |  |  |  |  |  |  |  |  |
| 19 | PHYSICAL EDUCATION, HEALTH EDUCATION, LEISURE |  |  |  |  |  |  |  |  |  |
| 19a | All Physical Education, Health Education and Leisure |  |  |  |  |  |  |  |  |  |
| 20 | PSYCHOLOGY |  |  |  |  |  |  |  |  |  |
| 20a | All Psychology |  |  |  |  |  |  |  |  |  |
| 21 | PUBLIC ADMINISTRATION AND SOCIAL SERVICES |  |  |  |  |  |  |  |  |  |
| 21a | Public Administration |  |  | X | X |  |  |  |  |  |
| 21b | Social Work |  |  |  |  |  |  |  |  |  |
| 21c | All other Public Administration and Social Services |  |  |  | X |  |  |  |  |  |
| 22 | SOCIAL SCIENCES AND SOCIAL STUDIES |  |  |  |  |  |  |  |  |  |
| 22a | Economics |  |  |  |  |  |  |  |  |  |
| 22b | All other Social Sciences and Social Studies |  |  |  |  |  |  |  |  |  |
| X | The institution has previously been active: (a) All previously approved programmes as well as (b) the new programmes which are specified are approved for 2003 – 2006 |  |  |  |  |  |  |  |  |  |
|  | The highlighted areas in green indicate the variation from the previous PQM documents as approved by the DoE on 26/11/2004 (See Notes) |  |  |  |  |  |  |  |  |  |

NOTES TO CONSOLIDATED APPROVED PQM (PROGRAMME QUALIFICATION MIX) FOR TUT (CONTACT)

CESM 01

- Two programmes namely National Higher Diploma: Pig Production Management and National Higher Diploma: Poultry Production Management is not listed on the PQM Document although it was previously approved. No students currently registered on NHDip Poultry Production Management for 2004.  Registered students for 2004 on the programme NHDip Pig Production Management. These programmes are phasing out. IT should be placed on the PQM for audit purposes until there are no more active students in these programmes.

- D Tech Agriculture – Withdrawn by the Department of Education BUT reinstated during June 2003, together with D.Tech: Game Range Management, D.Tech: Horticulture, D.Tech: Nature Conservation

CESM 04

- The MBA is listed to CESM 04 / 4d. Full accreditation received by CHE in September 2004. Approved Doctoral programmes are: DTech: Business Administration, DTech: Contact Center Management, DTech: Environmental Management

CESM 06

- All doctoral programmes in this CESM have been with drawn and the appeal for re-instatement was not successful. Therefore following  programmes are not approved: DTech: Knowledge Management; DTech: Information Technology; DTech: Business Information Systems;  D. Tech: Computer Systems; DTech Professional Practice in IT, DTech: Information Networks.

CESM 07

- New teacher education qualifications. All are approved on letter faxed on 26/03/2004 from the Department of Education. This includes ACE (undergraduate certificate) NPDE (Nat. Professional diploma), B.Ed(GET) and (FET), B.Ed (HONS), PGCE, M. Ed, D. Ed, M.Ed Educational Technology.

CESM 10

- National Diploma: Fashion and National Diploma: Fashion and Design Technology – Previous Technikon North-West (TNW) PQM Document did not indicate approval for offering. Appeal was successful and the programme is approved.

- NHD: Food and Nutrition not indicated on PQM of Pretoria Technikon.  However, the programme is phasing out. It should be placed on the PQM for audit purposes until there are no more active student in the programme.

CESM 11

DTech: Somatology is with drawn

CESM 12

- MTech: Language Practice was approved in March 2004

- DTech: Language Practice was not withdrawn by the Department of Education on the PQM Document of 26/11/2002.

CESM 15

- D Tech degrees - Withdrawn by the Department of Education on the PQM Document of 26/112002. Appeal was successful for offering. Only DTech: Biotechnology reinstated in June 2003.

CESM 16

- B Tech Mathematical Technology – Previous Technikon Pretoria PQM Document did indicate approval.  However, decision reversed on letter faxed on 26/03/2004 from the Department of Education and therefore not approved - PQM 2004 from DoE does indicate approval.  Review of decision will be made with submission of the Institutional Operating Plan for 2005 – 2007.

- M Tech Mathematical Technology – Approval never withdrawn by the Department of Education on the PQM Document of 26/112002.

- D Tech Mathematical Technology – Approval never withdrawn by the Department of Education on the PQM Document of 26/112002.

CESM 19

- MTech and DTech: Sport and Exercise Technology not approved (14/05/2004).  Doctoral programmes with drawn. Appeal for re-instatement not

approved

CESM 21

- B Tech: Public Management is not approved in the Technikon Northern Gauteng (TNG) PQM; however students are registered for 2004.

- NH Dip: Parks and Recreation Management.  Previously approved for Technikon Pretoria.  Registered students for 2004 on the programme. It should be placed on the PQM for audit purposes until there are no more active student in the programmes as it is phasing out.

CESM 22

- MTech: Tourism and Hospitality Management approved, although cell is indicated as inactive (reference: 14/5/10/5/12/2).

DTech: Tourism and Hospitality Management appeal not approved (14/05/2004)

DTech: Adventure Tourism Management approval never with drawn. Programme accredited by the CHE in October 2000.

DTech: Fire Technology not approved

| TABLE 3: PROPOSED PQM (PROGRAMME QUALIFICATION MIX) FOR TUT (CONTACT) 2007 - 2010 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| This table stipulates the approved programmes of TUT, as stipulated in the Consolidated PQM of the three merged institutions. It also indicates approved programmes as received from the DoE during the submission cycle of 2004, 2005 |  |  |  |  |  |  |  |  |  |  |
| CESM | MAJOR FIELDS OF STUDY | NOTES | UNDER GRADUATE CERTIFICATES | UNDER GRADUATE DIPLOMAS | GENERAL 1ST BACHELORS DEGREE | PROF 1ST BACHELORS DEGREE | POST GRAD & POSTDIP DIPLOMA | HONOURS DEGREE | MASTERS DEGREES AND DIPLOMAS | DOTORAL DEGREES |
| 1 | AGRICULTURE AND RENEWABLE NATURAL RESOURCES |  |  |  |  |  |  |  |  |  |
| 1a | Agricultural Economics |  |  |  |  |  |  |  |  |  |
| 1b | Agriculture | 1 |  | X | X |  | X |  | X | X |
| 1c | Fisheries |  |  |  |  |  |  |  |  |  |
| 1d | Forestry |  |  |  |  |  |  |  |  |  |
| 1e | All other Agriculture and Renewable Natural Resources |  |  | X | X |  |  |  | X | X |
| 2 | ARCHITECTURE AND ENVIRONMENTAL DESIGN |  |  |  |  |  |  |  |  |  |
| 2a | Architecture and Building Science | 2 |  | X | X |  |  |  | X |  |
| 2b | Quantity Surveying |  |  |  | X |  |  |  |  |  |
| 2c | Building Management |  |  | X | X |  |  |  | X |  |
| 2d | Town and Regional Planning |  |  |  |  |  |  |  |  |  |
| 2e | All other Architecture and Environmental Design |  |  |  |  |  |  |  |  |  |
| 3 | ARTS, VISUAL AND PERFORMING |  |  |  |  |  |  |  |  |  |
| 3a | Music |  | X | X | X |  |  |  | X | X |
| 3b | Drama |  | X | X | X |  |  |  | X | X |
| 3c | Fine Arts |  | X | X | X |  |  |  | X | X |
| 3d | All other Arts, Visual and Performing | 3 | X | X | X |  |  |  | X | X |
| 4 | BUSINESS, COMMERCE AND MAN. SCIENCES |  |  |  |  |  |  |  |  |  |
| 4a | Accounting |  | X | X | X |  |  |  | X | X |
| 4b | Banking and Finance |  |  |  |  |  |  |  |  |  |
| 4c | Business Data Systems and Business Quantitative Methods |  |  |  |  |  |  |  |  |  |
| 4d | All other Business, Commerce and Management Sciences | 4 | X | X | X |  |  |  | X | X |
| 5 | COMMUNICATION |  |  |  |  |  |  |  |  |  |
| 5a | Journalism and Media Studies |  |  | X | X |  |  |  | X | X |
| 5b | All other Communication | 5 | X | X | X |  | N |  | X | X |
| 6 | COMPUTER SCIENCE AND DATA PROCESSING |  |  |  |  |  |  |  |  |  |
| 6a | All computer Science and Data Process. | 6 | X | X | X |  |  |  | X | N |
| 7 | EDUCATION |  |  |  |  |  |  |  |  |  |
| 7a | Primary | 7 |  |  |  | N |  | N |  |  |
| 7b | Secondary |  |  |  |  | X | X |  | X | X |
| 7c | Special |  |  |  |  |  |  |  |  |  |
| 7d | All other Education | 8 | X |  |  | X | X | X | X | X |
| 8 | ENGINEERING AND ENGINEERING TECHNOLOGY |  |  |  |  |  |  |  |  |  |
| 8a | Chemical Engineering |  |  | X | X |  |  |  | X | X |
| 8b | Civil Engineering |  |  | X | X |  |  |  | X | X |
| 8c | Electrical Engineering |  |  | X | X |  |  |  | X | X |
| 8e | Mechanical Engineering |  |  | X | X |  |  |  | X | X |
| 8h | All other Engineering and Engineering Technology | 9 |  | X | X |  |  |  | X | X |
| 9 | HEALTH CARE AND HEALTH SC. |  |  |  |  |  |  |  |  |  |
| 9a | Medicine / surgery |  |  |  |  |  |  |  |  |  |
| 9b | Dentistry |  |  |  |  |  |  |  |  |  |
| 9c | Nursing |  |  | X | X |  |  |  | X | X |
| 9d | All Clinical Health Sciences |  | X | X | X |  | X |  | X | X |
| 9e | Pharmacy | 10 |  | N | X |  |  |  | X | X |
| 9f | Veterinary Science |  |  | X | X |  |  |  | X | X |
| 9g | Rehabilitation and Therapy |  | X | X | X |  |  |  | X | X |
| 9h | Hospital and Health Care Administration |  |  |  |  |  |  |  |  |  |
| 9i | All other Health Care and Health Sciences | 11 | X | X | X |  |  |  | X | X |
| 10 | HOME ECONOMICS |  |  |  |  |  |  |  |  |  |
| 10a | All Home Economics |  |  | X | X |  | X |  | X | X |
| 11 | INDUSTRIAL ARTS, TRADES AND TECHNOLOGY |  |  |  |  |  |  |  |  |  |
| 11a | All Industrial Arts, Trades and Technology |  |  |  | X |  |  |  | X |  |
| 12 | LANGUAGES, LINGUISTICS AND LITERATURE |  |  |  |  |  |  |  |  |  |
| 12a | Linguistics |  |  |  |  |  |  |  |  |  |
| 12b | Literary Studies |  |  |  |  |  |  |  |  |  |
| 12c | Afrikaans / Nederlands |  |  |  |  |  |  |  |  |  |
| 12d | English |  |  |  |  |  |  |  |  |  |
| 12e | African Languages |  |  |  |  |  |  |  |  |  |
| 12f | Modern European Languages |  |  |  |  |  |  |  |  |  |
| 12g | All other Languages, Linguistics and Literature |  |  | X | X |  |  |  | X | X |
| 13 | LAW |  |  |  |  |  |  |  |  |  |
| 13a | All Law |  | X | X |  |  | X |  |  |  |
| 14 | LIBRARIES AND MUSEUMS |  |  |  |  |  |  |  |  |  |
| 14a | All Libraries and Museums |  |  |  |  |  |  |  |  |  |
| 15 | LIFE AND PHYSICAL SCIENCES |  |  |  |  |  |  |  |  |  |
| 15a | Life Sciences |  |  | X | X |  |  |  | X | X |
| 15b | Physical Sciences |  | X | X | X |  |  |  | X | X |
| 15c | All other Life and Physical Sciences | 12 | X | X | X |  |  |  | X | X |
| 16 | MATHEMATICAL SCIENCES |  |  |  |  |  |  |  |  |  |
| 16a | All Mathematical Sciences | 13 |  |  | N |  |  |  | X | X |
| 17 | MILITARY SCIENCES |  |  |  |  |  |  |  |  |  |
| 17a | All Military Sciences |  |  |  |  |  |  |  |  |  |
| 18 | PHILOSOPHY, RELIGION AND THEOLOGY |  |  |  |  |  |  |  |  |  |
| 18a | Philosophy |  |  |  |  |  |  |  |  |  |
| 18b | Science of religion |  |  |  |  |  |  |  |  |  |
| 18c | All other Philosophy, Religion and Theo |  |  |  |  |  |  |  |  |  |
| 19 | PHYSICAL EDUCATION, HEALTH EDUCATION, LEISURE |  |  |  |  |  |  |  |  |  |
| 19a | All Physical Education, Health Education and Leisure | 14 | X | X | X |  |  |  | N |  |
| 20 | PSYCHOLOGY |  |  |  |  |  |  |  |  |  |
| 20a | All Psychology |  |  |  |  |  |  |  |  |  |
| 21 | PUBLID ACMINISTRATION AND SOCIAL SERVICES |  |  |  |  |  |  |  |  |  |
| 21a | Public Administration |  | X | X | X |  |  |  | X | X |
| 21b | Social Work |  |  |  |  |  |  |  |  |  |
| 21c | All other Public Administration and Social Services |  | X | X | X |  | X |  | X | X |
| 22 | SOCIAL SCIENCES AND SOCIAL STUDIES |  |  |  |  |  |  |  |  |  |
| 22a | Economics |  | X | X | X |  |  |  |  |  |
| 22b | All other Social Sciences and Social Studies | 15 | X | X | X |  |  |  | X | X |
| NOTES |  |  |  |  |  |  |  |  |  |  |
| X | The institution has previously been active: All previously approved programmes as well as the new programmes which are specified in the notes are approved for 2004/5 – 2006 |  |  |  |  |  |  |  |  |  |
| N | New Qualification : APPROVAL OF NEW QUALIFICATION IN NEW CELL WHERE TUT HAS NOT PREVIOULSY BEEN ACTIVE |  |  |  |  |  |  |  |  |  |

| TABLE 4: PROPOSED PQM (PROGRAMME QUALIFICATION MIX) FOR TUT (DISTANCE) 2007 - 2010 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CESM | MAJOR FIELDS OF STUDY | UNDER GRADUATE CERTIFICATES | UNDER GRADUATE DIPLOMAS | GENERAL 1ST BACHELORS DEGREE | POST DIP DIPLOMA | PROF 1ST BACHELORS DEGREE | POSTGRAD & POSTDIP DIPLOMA | HONOURS DEGREE | MASTER DEGREES & DIPLOMAS | DOTORAL DEGREES |
| 1 | AGRICULTURE AND RENEWABLE NATURAL RESOURCES |  |  |  |  |  |  |  |  |  |
| 1a | Agricultural Economics |  |  |  |  |  |  |  |  |  |
| 1b | Agriculture |  |  |  |  |  |  |  |  |  |
| 1c | Fisheries |  |  |  |  |  |  |  |  |  |
| 1d | Forestry |  |  |  |  |  |  |  |  |  |
| 1e | All other Agriculture and Renewable Natural Resources |  |  |  |  |  |  |  |  |  |
| 2 | ARCHITECTURE AND ENVIRONMENTAL DESIGN |  |  |  |  |  |  |  |  |  |
| 2a | Architecture and Building Science |  |  |  |  |  |  |  |  |  |
| 2b | Quantity Surveying |  |  |  |  |  |  |  |  |  |
| 2c | Building Management |  |  |  |  |  |  |  |  |  |
| 2d | Town and Regional Planning |  |  |  |  |  |  |  |  |  |
| 2e | All other Architecture and Environmental Design |  |  |  |  |  |  |  |  |  |
| 3 | ARTS, VISUAL AND PERFORMING |  |  |  |  |  |  |  |  |  |
| 3a | Music |  |  |  |  |  |  |  |  |  |
| 3b | Drama |  |  |  |  |  |  |  |  |  |
| 3c | Fine Arts |  |  |  |  |  |  |  |  |  |
| 3d | All other Arts, Visual and Performing |  |  |  |  |  |  |  |  |  |
| 4 | BUSINESS, COMMERCE AND MANAGEMENT SCIENCES |  |  |  |  |  |  |  |  |  |
| 4a | Accounting |  | X | X |  |  |  |  |  |  |
| 4b | Banking and Finance |  |  |  |  |  |  |  |  |  |
| 4c | Business Data Systems and Business Quantitative methods |  |  |  |  |  |  |  |  |  |
| 4d | All other Business, Commerce and Management Sciences |  | X | X |  |  |  |  |  |  |
| 5 | COMMUNICATION |  |  |  |  |  |  |  |  |  |
| 5a | Journalism and Media Studies | X | X | X |  |  |  |  |  |  |
| 5b | All other Communication |  |  |  |  |  |  |  |  |  |
| 6 | COMPUTER SCIENCE AND DATA PROCESSING |  |  |  |  |  |  |  |  |  |
| 6a | All computer Science and Data Processing |  |  |  |  |  |  |  |  |  |
| 7 | EDUCATION |  |  |  |  |  |  |  |  |  |
| 7a | Primary |  |  |  |  |  |  |  |  |  |
| 7b | Secondary |  |  |  |  |  |  |  |  |  |
| 7c | Special |  |  |  |  |  |  |  |  |  |
| 7d | All other Education | X |  |  |  |  | X | X |  |  |
| 8 | ENGINEERING AND ENGINEERING TECHNOLOGY |  |  |  |  |  |  |  |  |  |
| 8a | Chemical Engineering |  |  |  |  |  |  |  |  |  |
| 8b | Civil Engineering |  |  |  |  |  |  |  |  |  |
| 8c | Electrical Engineering |  |  |  |  |  |  |  |  |  |
| 8e | Mechanical Engineering |  |  |  |  |  |  |  |  |  |
| 8h | All other Engineering and Engineering Technology |  |  |  |  |  |  |  |  |  |
| 9 | HEALTH CARE AND HEALTH SCIENCES |  |  |  |  |  |  |  |  |  |
| 9a | Medicine / surgery |  |  |  |  |  |  |  |  |  |
| 9b | Dentistry |  |  |  |  |  |  |  |  |  |
| 9c | Nursing |  |  |  |  |  |  |  |  |  |
| 9d | All Clinical Health Sciences |  |  |  |  |  |  |  |  |  |
| 9e | Pharmacy |  |  |  |  |  |  |  |  |  |
| 9f | Veterinary Science |  |  |  |  |  |  |  |  |  |
| 9g | Rehabilitation and Therapy |  |  |  |  |  |  |  |  |  |
| 9h | Hospital and Health Care Administration |  |  |  |  |  |  |  |  |  |
| 9i | All other Health Care and Health Sciences |  |  |  |  |  |  |  |  |  |
| 10 | HOME ECONOMICS |  |  |  |  |  |  |  |  |  |
| 10a | All Home Economics |  |  |  |  |  |  |  |  |  |
| 11 | INDUSTRIAL ARTS, TRADES AND TECHNOLOGY |  |  |  |  |  |  |  |  |  |
| 11a | All Industrial Arts, Trades and Technology |  |  |  |  |  |  |  |  |  |
| 12 | LANGUAGES, LINGUISTICS AND LITERATURE |  |  |  |  |  |  |  |  |  |
| 12a | Linguistics |  |  |  |  |  |  |  |  |  |
| 12b | Literary Studies |  |  |  |  |  |  |  |  |  |
| 12c | Afrikaans / Nederlands |  |  |  |  |  |  |  |  |  |
| 12d | English |  |  |  |  |  |  |  |  |  |
| 12e | African Languages |  |  |  |  |  |  |  |  |  |
| 12f | Modern European Languages |  |  |  |  |  |  |  |  |  |
| 12g | All other Languages, Linguistics and Literature |  |  |  |  |  |  |  |  |  |
| 13 | LAW |  |  |  |  |  |  |  |  |  |
| 13a | All Law |  | X |  |  |  |  |  |  |  |
| 14 | LIBRARIES AND MUSEUMS |  |  |  |  |  |  |  |  |  |
| 14a | All Libraries and Museums |  |  |  |  |  |  |  |  |  |
| 15 | LIFE AND PHYSICAL SCIENCES |  |  |  |  |  |  |  |  |  |
| 15a | Life Sciences |  |  |  |  |  |  |  |  |  |
| 15b | Physical Sciences |  |  |  |  |  |  |  |  |  |
| 15c | All other Life and Physical Sciences |  |  |  |  |  |  |  |  |  |
| 16 | MATHEMATICAL SCIENCES |  |  |  |  |  |  |  |  |  |
| 16a | All Mathematical Sciences |  |  |  |  |  |  |  |  |  |
| 17 | MILITARY SCIENCES |  |  |  |  |  |  |  |  |  |
| 17a | All Military Sciences |  |  |  |  |  |  |  |  |  |
| 18 | PHILOSOPHY, RELIGION AND THEOLOGY |  |  |  |  |  |  |  |  |  |
| 18a | Philosophy |  |  |  |  |  |  |  |  |  |
| 18b | Science of religion |  |  |  |  |  |  |  |  |  |
| 18c | All other Philosophy, Religion and Theology |  |  |  |  |  |  |  |  |  |
| 19 | PHYSICAL EDUCATION, HEALTH EDUCATION , LEISURE |  |  |  |  |  |  |  |  |  |
| 19a | All Physical Education, Health Education and Leisure |  |  |  |  |  |  |  |  |  |
| 20 | PSYCHOLOGY |  |  |  |  |  |  |  |  |  |
| 20a | All Psychology |  |  |  |  |  |  |  |  |  |
| 21 | PUBLIC ADMINISTRATION AND SOCIAL SERVICES |  |  |  |  |  |  |  |  |  |
| 21a | Public Administration |  | X | X |  |  |  |  |  |  |
| 21b | Social Work |  |  |  |  |  |  |  |  |  |
| 21c | All other Public Administration and Social Services |  |  | X |  |  |  |  |  |  |
| 22 | SOCIAL SCIENCES AND SOCIAL STUDIES |  |  |  |  |  |  |  |  |  |
| 22a | Economics |  |  |  |  |  |  |  |  |  |
| 22b | All other Social Sciences and Social Studies |  |  |  |  |  |  |  |  |  |
| X | All previously approved programmes as well as the new programmes which are specified are approved for 2005 - 2007 |  |  |  |  |  |  |  |  |  |

# NOTES TO PROPOSED PQM for 2006 - 2010

PART ONE

This section proposes New Qualifications in approved OR new cells.  A (N) is used to indicate new qualification in new cells.  The status of the programmes is indicated as follows:

- New programmes that were approved during June and March 2004 and 2005 submission cycles.

- Programmes that were approved by DoE but were not accredited by the CHE.  These programmes will be resubmitted to the HEQC with updated information as requested.

- Programmes that were NOT approved by the DoE.  These programmes will be resubmitted for approval.

- Possible new programmes.  The proposal of these programmes is based on a Labor market needs analysis.  These programmes will be submitted to Senate after the development of a Business Plan.  It is also proposed that the curriculation of these programmes will be in accordance to the long awaited HEQF and will be curriculated according to the informed credits.   This process will start when the HEQF is approved.

CESM 01

1:	The following programmes will be curriculated according to the rationale of the HEQF.  A Business Plan will be developed for Turf Grass

Management (Active on National diploma level) and Amenity Horticulture. The following programmes will be submitted to

Senate and DoE: M Tech:  Landscape Technology, B Tech: Game Capture, B Tech: Environmental Education

CESM 02

2:	        B Tech:  Architecture (Prof).  Approved by DoE, March 2005; submitted to CHE for accreditation.

# CESM 03

3:	B Tech:  Multimedia.  Approved by DoE, June 2004.  Conditional accredited.

# CESM 04

4:	B Tech:  Economic Management Analysis and B Tech:  Accounting will be submitted to DoE during 2006.

N Dip:  Events Management will be submitted to DoE during 2006.

NH Cert:  Financial Information Systems, NHC:  Accounting – Revised programmes.

Casino Management as well as Airline and Airport Management is programmes that will be curriculated according to the new HEQF. Business Plans still to be developed.

## CESM 05

5:		N Dip:  Broadcasting.  Will be submitted to DoE during 2006.

Post-graduate Diploma:  Inter Active Marketing Communication - Not approved but will be resubmitted for approval.

### CESM 06

6:	Resubmission to DoE for approval of offering:  D Tech:  Computer science and Data Processing - New programme in new cell (N)

#### CESM 07

7:	B Ed:  GET – Foundation Phase, B Ed (Hons):  GET-Intermediate, Senior Phase.  New programmes in new second order CESM category.  Business Plans will be developed and application to DoE will be submitted during 2006.

8:	M Ed:  Educational Technology.  Approved by DoE, June 2004, submitted to CHE.

#### CESM  08

9:	N Dip.  Engineering (Mechatronics) – approved by DoE, May 2004.

N Dip:  Engineering (Manufacturing) will be submitted to DoE for approval.

N Dip:  Industrial Design.  Business Plan to be developed and submitted to Senate.  Application will be submitted to DoE during 2006.

##### CESM 09

10:	N Dip:  Pharmaceutical Sciences to be submitted to DoE during 2006 for approval.  This is a new qualification in a new cell (N).

11:	National Certificate: Nutrition;  N Dip: Tissue Engineering to be submitted to DoE for approval.

###### CESM 15

12:	B Tech:  Ceramics Technology and B Tech:  Explosive Technology will be submitted to DoE for approval.  These programmes have a proven track record within the National Diplomas.

N Dip:  Physics/Industrial Physics as well as N Dip:  Industrial Chemistry will be submitted to the DoE for approval, as new programmes in approved cells.  Business Plans will be developed.

###### CESM 16

13:	The B Tech:  Mathematical Technology has been withdrawn.  Resubmission for the programme will be done during 2006 as approval has been obtained for the M Tech and D Tech.

#### CESM 19

14:	M Tech:  Sport and Exercise Technology, was not approved by DoE during March 2004.  The Programme will be resubmitted to DoE for approval.

M Tech:  Sport and Recreation Management was approved by DoE during June 2004, but NOT accredited by CHE.  Resubmission will be done to CHE to provide clarity on requested issues.

CESM 21        ND:  Local Government Management was approved by Senate and has to be submitted to the DoE

#### CESM 22

15:	The D Tech:  Tourism and Hospitality Management was withdrawn by the DoE.  Resubmission for approval to DoE will be done during 2006.

The following Master degree programmes will be developed with the approval of the HEQF:  Joint African Masters Programme in Comparative Local Development, Masters Programme in Economics of Innovation.

PART TWO - PROGRAMMES TO BE PHASED OUT

### CESM 01

NHD:  Pig Production Management; NHD:  Poultry Production Management

### CESM 04

N Dip:  Management of training.

### CESM 07

B Tech:  Educational Management (contact and distance); M Tech:  Educational Management (contact and distance); D Tech:  Educational Management

CESM 09

M Tech:  Nursing (Structured)

### CESM  10

N Dip:  Food and Nutrition; M Tech:  Food Services Management; D Tech:  Food Services Management

### CESM 21

NHD:  Parks and Recreation Management

STUDENT ENROLMENT TABELLE

HEADCOUNT ENROLMENTS

TABLE 5:   TOTAL HEADCOUNT ENROLMENTS

| HEADCOUNTS | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentages |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | % 2004 | % 2010 |
| Contact | 36353 | 41652 | 44598 | 48328 | 50933 | 51042 | 51073 | 52051 | 53450 | 54850 | 56250 | 79.75% | 93.75% |
| Distance | 10429 | 10030 | 8586 | 11624 | 12931 | 11140 | 9427 | 7949 | 6550 | 5150 | 3750 | 20.25% | 6.25% |
| TotaL Headcount Enrolment | 46782 | 51682 | 53184 | 59952 | 63864 | 62182 | 60500 | 60000 | 60000 | 60000 | 60000 | 100.00% | 100.00% |

TABLE 6:  TOTAL HEADCOUNT ENROLMENTS PER MAJOR FIELD OF STUDY

| MAJOR FIELD OF STUDY | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2004% | 2010% |
| Science, Engineering, Technology | 13895 | 16143 | 17207 | 19045 | 17855 | 18541 | 19200 | 20228 | 21449 | 22707 | 24000 | 27.96% | 43.75% |
| Business / Management | 13934 | 14796 | 16533 | 17387 | 24089 | 23282 | 22442 | 22005 | 21712 | 21377 | 21000 | 37.72% | 35.30% |
| Education | 10536 | 9757 | 7951 | 10622 | 11465 | 9862 | 8393 | 7196 | 6134 | 5135 | 4200 | 17.95% | 9.64% |
| Other Humanities | 8417 | 10986 | 11493 | 12898 | 10455 | 10498 | 10465 | 10571 | 10705 | 10781 | 10800 | 16.37% | 11.31% |
| Total Enrolment | 46782 | 51682 | 53184 | 59952 | 63864 | 62182 | 60500 | 60000 | 60000 | 60000 | 60000 | 100.00% | 100.00% |

TABLE 7:  CONTACT HEADCOUNT ENROLMENTS PER MAJOR FIELD OF STUDY

| MAJOR FIELD OF STUDY | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2004% | 2010% |
| Science, Engineering, Technology | 13881 | 16131 | 17198 | 19040 | 17855 | 18541 | 19200 | 20228 | 21449 | 22707 | 24000 | 35.06% | 42.67% |
| Business / Management | 13930 | 14782 | 16497 | 17367 | 23882 | 23115 | 22310 | 21902 | 21634 | 21321 | 20963 | 46.89% | 37.27% |
| Education | 842 | 1188 | 1077 | 1951 | 1453 | 1486 | 1516 | 1575 | 1649 | 1723 | 1800 | 2.85% | 3.20% |
| Other Humanities | 7700 | 9551 | 9826 | 9970 | 7743 | 7901 | 8048 | 8346 | 8718 | 9099 | 9487 | 15.20% | 16.87% |
| Total Enrolment | 36353 | 41652 | 44598 | 48328 | 50933 | 51042 | 51073 | 52051 | 53450 | 54850 | 56250 | 100.00% | 100.00% |

TABLE 8:  DISTANCE HEADCOUNT ENROLMENTS PER MAJOR FIELD OF STUDY

| MAJOR FIELD OF STUDY | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentages |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | % 2004 | % 2010 |
| Science, Engineering, Technology | 14 | 12 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00% | 0.00% |
| Business / Management | 4 | 14 | 36 | 20 | 207 | 167 | 132 | 103 | 79 | 57 | 38 | 1.60% | 1.00% |
| Education | 9694 | 8569 | 6874 | 8671 | 10012 | 8376 | 6877 | 5621 | 4485 | 3411 | 2400 | 77.43% | 64.00% |
| Other Humanities | 717 | 1435 | 1667 | 2928 | 2712 | 2597 | 2418 | 2225 | 1986 | 1682 | 1313 | 20.97% | 35.00% |
| Total Enrolment | 10429 | 10030 | 8586 | 11624 | 12931 | 11140 | 9427 | 7949 | 6550 | 5150 | 3750 | 100.00% | 100.00% |

TABLE 9:  TOTAL HEADCOUNT ENROLMENTS PER QUALIFICATION TYPE

| QUALIFICATION TYPE | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2004% | 2010% |
| Undergraduate Diplomas | 16902 | 17435 | 17837 | 18085 | 46498 | 46077 | 45612 | 46010 | 46786 | 47561 | 48336 | 72.81% | 80.56% |
| Undergraduate Degrees | 28767 | 32412 | 33034 | 38693 | 13797 | 12588 | 11424 | 10513 | 9697 | 8880 | 8064 | 21.60% | 13.44% |
| Total Undergraduate | 45669 | 49847 | 50871 | 56778 | 60295 | 58664 | 57036 | 56523 | 56482 | 56441 | 56400 | 94.41% | 94.00% |
| Postgraduate to Masters Level | 308 | 286 | 159 | 161 | 124 | 142 | 159 | 178 | 199 | 219 | 240 | 0.19% | 0.40% |
| Masters | 521 | 988 | 1415 | 2248 | 2779 | 2690 | 2602 | 2565 | 2550 | 2535 | 2520 | 4.35% | 4.20% |
| Doctors | 45 | 69 | 74 | 83 | 101 | 123 | 144 | 167 | 192 | 216 | 240 | 0.16% | 0.40% |
| Total Postgraduate | 874 | 1343 | 1648 | 2492 | 3004 | 2956 | 2906 | 2911 | 2941 | 2970 | 3000 | 4.70% | 5.00% |
| Occasional Students | 239 | 492 | 665 | 682 | 565 | 562 | 558 | 565 | 577 | 588 | 600 | 0.88% | 1.00% |
| Total Enrolment | 46782 | 51682 | 53184 | 59952 | 63864 | 62182 | 60500 | 60000 | 60000 | 60000 | 60000 | 100.00% | 100.00% |

Note – B. Ed (Hons) has been incorrectly classified as an Undergraduate Qualification on the ITS System and therefore reflects in this table as part of the undergraduate enrolments

TABLE 10:  CONTACT HEADCOUNT ENROLMENTS PER QUALIFICATION TYPE

| QUALIFICATION TYPE | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentages |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | % 2004 | % 2010 |
| Undergraduate Diplomas | 16252 | 16220 | 17836 | 18085 | 42833 | 42746 | 42594 | 43227 | 44203 | 45169 | 46125 | 84.10% | 82.00% |
| Undergraduate Degrees | 19474 | 24232 | 25150 | 28475 | 6181 | 6154 | 6118 | 6194 | 6319 | 6442 | 6562 | 12.14% | 11.67% |
| Total Undergraduate | 35726 | 40452 | 42986 | 46560 | 49014 | 48901 | 48712 | 49422 | 50522 | 51611 | 52687 | 96.23% | 93.67% |
| Postgraduate to Masters Level | 49 | 33 | 50 | 32 | 66 | 91 | 117 | 145 | 175 | 207 | 240 | 0.13% | 0.43% |
| Masters | 408 | 747 | 936 | 1076 | 1212 | 1393 | 1573 | 1785 | 2020 | 2265 | 2520 | 2.38% | 4.48% |
| Doctors | 45 | 69 | 74 | 83 | 101 | 121 | 140 | 162 | 187 | 213 | 240 | 0.20% | 0.43% |
| Total Postgraduate | 502 | 849 | 1060 | 1191 | 1379 | 1605 | 1830 | 2092 | 2382 | 2685 | 2999 | 2.71% | 5.33% |
| Occasional Students | 125 | 351 | 552 | 577 | 540 | 536 | 531 | 536 | 545 | 554 | 563 | 1.06% | 1.00% |
| Total Enrolment | 36353 | 41652 | 44598 | 48328 | 50933 | 51042 | 51073 | 52051 | 53450 | 54850 | 56250 | 100.00% | 100.00% |

TABLE 11:  DISTANCE HEADCOUNT ENROLMENTS PER QUALIFICATION TYPE

| QUALIFICATION TYPE | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentages |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | % 2004 | % 2010 |
| Undergraduate Diplomas | 650 | 1215 | 1 | 0 | 3665 | 3727 | 3635 | 3472 | 3195 | 2775 | 2213 | 28.34% | 59.000% |
| Undergraduate Degrees | 9293 | 8180 | 7884 | 10218 | 7616 | 4760 | 3458 | 2525 | 1721 | 1004 | 375 | 58.90% | 10.000% |
| B Ed (Hons) |  |  |  |  |  | 1450 | 1500 | 1406 | 1312 | 1218 | 1125 |  | 30.000% |
| Total Undergraduate | 9943 | 9395 | 7885 | 10218 | 11281 | 9937 | 8593 | 7403 | 6228 | 4997 | 3713 | 87.24% | 99.000% |
| Postgraduate to Masters Level | 259 | 253 | 109 | 129 | 58 | 42 | 28 | 18 | 10 | 4 | 0 | 0.45% | 0.000% |
| Masters | 113 | 241 | 479 | 1172 | 1567 | 1125 | 762 | 482 | 265 | 104 | 0 | 12.12% | 0.000% |
| Doctors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00% | 0.000% |
| Total Postgraduate | 372 | 494 | 588 | 1301 | 1625 | 1167 | 790 | 499 | 274 | 108 | 0 | 12.57% | 0.000% |
| Occasional Students | 114 | 141 | 113 | 105 | 25 | 37 | 44 | 47 | 48 | 45 | 38 | 0.19% | 1.000% |
| Total Enrolment | 10429 | 10030 | 8586 | 11624 | 12931 | 11140 | 9427 | 7949 | 6550 | 5150 | 3750 | 100.00% | 100.000% |

* Note – B. Ed (Hons) has been incorrectly classified as an Undergraduate Qualification on the ITS System.

FTE ENROLMENTS

TABLE 12:  TOTAL FTE ENROLMENTS

| FTE ENROLMENTS | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  |  | Percentages |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 |  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | % 2004 | % 2010 |
| Contact FTE | 28513 | 32935 | 34838 | 36441 | 38417 |  | 41101 | 40658 | 40985 | 41649 | 42312 | 42975 | 86.66% | 95.50% |
| Distance FTE | 5476 | 5070 | 4466 | 6351 | 5915 |  | 5535 | 4717 | 4015 | 3351 | 2688 | 2025 | 13.34% | 4.50% |
| Total FTE Enrolment | 33989 | 38005 | 39304 | 42792 | 44332 |  | 46637 | 45375 | 45000 | 45000 | 45000 | 45000 | 100.00% | 100.00% |

| MAJOR FIELD OF STUDY | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2004% | 2010% |
| Science, Engineering, Technology | 10692 | 13067 | 13398 | 13941 | 15036 | 16348 | 16422 | 16799 | 17311 | 17823 | 18335 | 33.92% | 40.75% |
| Business / Management | 8293 | 8835 | 9566 | 10159 | 10809 | 12245 | 12765 | 13504 | 14348 | 15192 | 16036 | 24.38% | 35.64% |
| Education | 5421 | 4691 | 4171 | 5831 | 5172 | 4995 | 4427 | 3960 | 3530 | 3101 | 2671 | 11.67% | 5.94% |
| Other Humanities | 9583 | 11843 | 12169 | 12861 | 13316 | 13048 | 11760 | 10736 | 9810 | 8883 | 7956 | 30.04% | 17.68% |
| Total Enrolment | 33989 | 38437 | 39304 | 42792 | 44332 | 46637 | 45375 | 45000 | 45000 | 45000 | 45000 | 100.00% | 100.00% |

TABLE 13:  TOTALE FTE ENROLMENTS BY MAJOR FIELD OF STUDY

TABLE 14:  CONTACT STUDENTS:  FTE ENROLMENTS BY MAJOR FIELD OF STUDY

| MAJOR FIELD OF STUDY | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2004% | 2010% |
| Science, Engineering, Technology | 10666 | 13044 | 13381 | 13918 | 14897 | 16204 | 16293 | 16690 | 17231 | 17780 | 18337 | 38.78% | 42.67% |
| Business / Management | 8237 | 8751 | 9511 | 10076 | 10688 | 12082 | 12592 | 13339 | 14211 | 15103 | 16017 | 27.82% | 37.27% |
| Education | 539 | 664 | 605 | 1019 | 901 | 1023 | 1070 | 1137 | 1214 | 1294 | 1375 | 2.35% | 3.20% |
| Other Humanities | 9071 | 10909 | 11341 | 11427 | 11931 | 11792 | 10703 | 9819 | 8993 | 8135 | 7246 | 31.06% | 16.86% |
| Total Enrolment | 28513 | 33368 | 34838 | 36441 | 38417 | 41101 | 40658 | 40985 | 41649 | 42312 | 42975 | 100.00% | 100.00% |

TABLE 15:  DISTANCE STUDENTS ONLY:  FTE ENROLMENTS BY MAJOR FIELD OF STUDY

| MAJOR FIELD OF STUDY | Actuals Enrolments |  |  |  |  | Projected Enrolments |  |  |  |  |  | Percentage |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2004% | 2010% |
| Science, Engineering, Technology | 26 | 23 | 17 | 22 | 139 | 108 | 74 | 47 | 26 | 11 | 0 | 2.35% | 0.00% |
| Business / Management | 56 | 85 | 55 | 83 | 120 | 103 | 80 | 61 | 45 | 32 | 20 | 2.03% | 1.00% |
| Education | 4882 | 4027 | 3567 | 4812 | 4270 | 3921 | 3276 | 2734 | 2236 | 1757 | 1296 | 72.20% | 64.00% |
| Other Humanities | 512 | 934 | 828 | 1434 | 1385 | 1403 | 1287 | 1173 | 1044 | 889 | 709 | 23.42% | 35.00% |
| Total | 5476 | 5070 | 4466 | 6351 | 5915 | 5535 | 4717 | 4015 | 3351 | 2688 | 2025 | 100.00% | 100.00% |

STAFF PROFILE

TABLE 16:   HEADCOUNT TOTALS PERMANENT STAFF BY CATEGORY

| STAFF CATEGORY | Actuals |  |  |  |  | Projected |  |  |  |  |  | Percentages |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | % 2004 | % 2010 |
| Instruction/Research Professionals | 816 | 798 | 853 | 884 | 895 | 881 | 906 | 941 | 975 | 1010 | 1079 | 32.74% | 41.50% |
| Executive/Management Professionals | 58 | 66 | 72 | 75 | 75 | 80 | 72 | 66 | 59 | 52 | 39 | 2.74% | 1.50% |
| Support Professionals | 168 | 182 | 198 | 225 | 212 | 159 | 166 | 174 | 183 | 191 | 208 | 7.75% | 8.00% |
| Total Professional Staff | 1042 | 1046 | 1123 | 1184 | 1182 | 1120 | 1144 | 1181 | 1217 | 1253 | 1326 | 43.23% | 51.00% |
| Technical Staff | 25 | 30 | 31 | 39 | 37 | 15 | 17 | 19 | 20 | 22 | 26 | 1.35% | 1.00% |
| Non-Professional administrative Staff | 836 | 866 | 916 | 954 | 999 | 1034 | 1013 | 1003 | 992 | 982 | 962 | 36.54% | 37.00% |
| Crafts/Trades Staff | 52 | 52 | 49 | 47 | 50 | 29 | 28 | 28 | 27 | 27 | 26 | 1.83% | 1.00% |
| Service Staff | 620 | 550 | 536 | 493 | 466 | 430 | 398 | 370 | 343 | 315 | 260 | 17.04% | 10.00% |
| Total non-Professional Staff | 1533 | 1498 | 1532 | 1533 | 1552 | 1508 | 1456 | 1419 | 1383 | 1347 | 1274 | 56.77% | 49.00% |
| Total Permanent Staff | 2575 | 2544 | 2655 | 2717 | 2734 | 2628 | 2600 | 2600 | 2600 | 2600 | 2600 | 100.00% | 100.00% |
| Ratio: Non-Professional Staff: Proff | 1: 0.68 | 1: 0.70 | 1: 0.73 | 1: 0.77 | 1: 0.76 | 1: 0.74 | 1: 0.79 | 1: 0.83 | 1: 0.88 | 1: 0.93 | 1: 1.04 |  |  |

*Notes: Stabilize Staff Headcount at 2600

*Notes: Increase Instruction/Research Professionals by 184 to 1079 to attain a 1:31 FTE Instructional/Research: Total FTE Students

TABLE 17:  TOTAL  FTE STAFF BY CATEGORY

| STAFF CATEGORY | Actuals |  |  |  |  | Projected |  |  |  |  |  | Percentages |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | % 2004 | % 2010 |
| Instruction/Research Professionals | 915 | 954 | 1064 | 1141 | 1258 | 1304 | 1335 | 1361 | 1381 | 1358 | 1470 | 32.16% | 42.00% |
| Executive/Management Professionals | 56 | 62 | 69 | 70 | 73 | 80 | 71 | 63 | 55 | 46 | 35 | 1.86% | 1.00% |
| Support Professionals | 160 | 207 | 219 | 244 | 306 | 234 | 243 | 250 | 257 | 255 | 280 | 7.82% | 8.00% |
| Total Professional Staff | 1132 | 1223 | 1352 | 1456 | 1636 | 1618 | 1649 | 1674 | 1693 | 1659 | 1785 | 41.84% | 51.00% |
| Technical Staff | 27 | 35 | 33 | 46 | 79 | 34 | 34 | 34 | 34 | 33 | 35 | 2.01% | 1.00% |
| Non-Professional administrative Staff | 1086 | 1181 | 1269 | 1443 | 1654 | 1985 | 1849 | 1719 | 1593 | 1431 | 1295 | 42.29% | 37.00% |
| Crafts/Trades Staff | 48 | 50 | 48 | 48 | 49 | 28 | 29 | 31 | 32 | 31 | 35 | 1.26% | 1.00% |
| Service Staff | 603 | 427 | 430 | 492 | 493 | 547 | 508 | 471 | 435 | 390 | 350 | 12.60% | 10.00% |
| Total non-Professional Staff | 1764 | 1694 | 1780 | 2029 | 2274 | 2594 | 2421 | 2254 | 2093 | 1885 | 1715 | 58.16% | 49.00% |
| Total Staff | 2896 | 2916 | 3132 | 3485 | 3910 | 4212 | 4070 | 3928 | 3786 | 3544 | 3500 | 100.00% | 100.00% |
| Ratio: FTE Instruction/Research Professionals : FTE Total Students | 1:`37 | 1:40 | 1:37 | 1:38 | 1:35 | 1:36 | 1:34 | 1:33 | 1:33 | 1:33 | 1:31 |  |  |
| Ratio: Total Headcount Appointed Staff: Total FTE Staff | 1.12 | 1.15 | 1.18 | 1.28 | 1.43 | 1.60 | 1.57 | 1.51 | 1.46 | 1.36 | 1.35 |  |  |

*Notes: Decreasing Temporary Staff from 0.6 FTE to 0.35 FTE

FINANCIAL PROJECTIONS – SCHEDULES 1 – 5

| # SCHEDULE 1 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CAPITAL EXPENDITURE PROGRAM TO ADDRESS THE CURRENT BACKLOGS |  |  |  |  |  |  |  |  |  |
|  | 2006 |  | 2007 |  | 2008 |  | 2009 |  | 2010 |
| 1. Expenditure Categories |  |  |  |  |  |  |  |  |  |
| - Buildings maintenance backlogs | 49,000,000 |  | 49,000,000 |  | 48,000,000 |  | 0 |  | 0 |
| - Renovations and alterations backlogs | 20,000,000 |  | 20,000,000 |  | 19,000,000 |  | 0 |  | 0 |
| - Equipment and infrastructure backlogs | 43,000,000 |  | 43,000,000 |  | 43,000,000 |  | 43,000,000 |  | 43,000,000 |
| TOTAL | 112,000,000 |  | 112,000,000 |  | 110,000,000 |  | 43,000,000 |  | 43,000,000 |
| 2. Funding Sources |  |  |  |  |  |  |  |  |  |
| - Government grants | 36,000,000 |  | 0 |  | 0 |  | 0 |  | 0 |
| - Donations | 0 |  | 0 |  | 0 |  | 0 |  | 0 |
| - Loans | 76,000,000 |  | 112,000,000 |  | 110,000,000 |  | 43,000,000 |  | 43,000,000 |
| TOTAL | 112,000,000 |  | 112,000,000 |  | 110,000,000 |  | 43,000,000 |  | 43,000,000 |
| 3. Effect on Income Statement |  |  |  |  |  |  |  |  |  |
| - Government grants | 36,000,000 |  | 0 |  | 0 |  | 0 |  | 0 |
| - Donations | 0 |  | 0 |  | 0 |  | 0 |  | 0 |
| - Loans: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |
| ▪ Interest at 9% p.a. | -6,640,652 |  | -15,966,080 |  | -24,394,460 |  | -26,190,658 |  | -27,542,184 |
| TOTAL | 29,359,348 |  | -15,966,080 |  | -24,394,460 |  | -26,190,658 |  | -27,542,184 |
| 4. Effect on Balance Sheet |  |  |  |  |  |  |  |  |  |
| - Property, plant and equipment | 112,000,000 |  | 224,000,000 |  | 334,000,000 |  | 377,000,000 |  | 420,000,000 |
| - Funds employed | -29,359,348 |  | 15,966,080 |  | 24,394,460 |  | 26,190,658 |  | 27,542,184 |
| - Long-term liabilities (interest bearing) at 31Dec | -71,087,822 |  | -170,475,847 |  | -259,571,054 |  | -276,925,987 |  | -289,095,978 |
| ▪ Opening balance at 1 Jan | -76,000,000 |  | -183,087,822 |  | -280,475,847 |  | -302,571,054 |  | -319,925,987 |
| ▪ Capital repayment | 4,912,178 |  | 12,611,975 |  | 20,904,793 |  | 25,645,067 |  | 30,830,009 |
| NETT | 11,552,830 |  | 69,490,233 |  | 98,823,406 |  | 126,264,671 |  | 158,446,206 |

| SCHEDULE 2 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CAPITAL EXPENDITURE PROGRAM TO FUND THE CHANGES IN THE TOPOGRAPHY |  |  |  |  |  |  |  |  |  |
|  | 2006 |  | 2007 |  | 2008 |  | 2009 |  | 2010 |
| 1. Expenditure Categories |  |  |  |  |  |  |  |  |  |
| - Relocation costs (IOP): |  |  |  |  |  |  |  |  |  |
| ▪ Refurbishments | 41,940,000 |  | 41,940,000 |  | 41,940,000 |  | 41,940,000 |  | 41,940,000 |
| ▪ Reconstruction | 0 |  | 120,200,000 |  | 120,200,000 |  | 0 |  | 0 |
| TOTAL | 41,940,000 |  | 162,140,000 |  | 162,140,000 |  | 41,940,000 |  | 41,940,000 |
| 2. Funding Sources |  |  |  |  |  |  |  |  |  |
| - Government grants | 0 |  | 0 |  | 0 |  | 0 |  | 0 |
| - Donations | 0 |  | 0 |  | 0 |  | 0 |  | 0 |
| - Loans | 41,940,000 |  | 162,140,000 |  | 162,140,000 |  | 41,940,000 |  | 41,940,000 |
| TOTAL | 41,940,000 |  | 162,140,000 |  | 162,140,000 |  | 41,940,000 |  | 41,940,000 |
| 3. Effect on Income Statement |  |  |  |  |  |  |  |  |  |
| - Government grants | 0 |  | 0 |  | 0 |  | 0 |  | 0 |
| - Donations | 0 |  | 0 |  | 0 |  | 0 |  | 0 |
| - Loans: |  |  |  |  |  |  |  |  |  |
| ▪ Interest at 9% p.a. | 3,664,591 |  | 17,577,612 |  | 30,483,707 |  | 31,785,702 |  | 32,611,783 |
| TOTAL | 3,664,591 |  | 17,577,612 |  | 30,483,707 |  | 31,785,702 |  | 32,611,783 |
| 4. Effect on Balance Sheet |  |  |  |  |  |  |  |  |  |
| - Property, plant and equipment | 41,940,000 |  | 204,080,000 |  | 366,220,000 |  | 408,160,000 |  | 450,100,000 |
| - Funds employed | -3,664,591 |  | -17,577,612 |  | -30,483,707 |  | -31,785,702 |  | -32,611,783 |
| - Long-term liabilities (interest bearing) at 31Dec | -39,229,253 |  | -187,924,476 |  | -324,878,742 |  | -336,559,665 |  | -342,691,331 |
| ▪ Opening balance at 1 Jan | -41,940,000 |  | -201,369,253 |  | -350,064,476 |  | -366,818,742 |  | -378,499,665 |
| ▪ Capital repayment | 2,710,747 |  | 13,444,777 |  | 25,185,734 |  | 30,259,077 |  | 35,808,334 |
| NETT | -953,844 |  | -1,422,088 |  | 10,857,551 |  | 39,814,633 |  | 74,796,886 |

| SCHEDULE 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BALANCE SHEET AT 31 DECEMBER 2005 - 2010 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2nd REVISED BUDGET 2005 |  |  | YEAR TO DATE 2005 |  |  |  | BUDGET 2006 |  |  | FORECAST 2007 |  |  | FORECAST 2008 |  |  | FORECAST 2009 |  |  | FORECAST 2010 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R'000 |  |  | R'000 |  |  |  | R'000 |  |  | R'000 |  |  | R'000 |  |  | R'000 |  |  | R'000 |  |  |  |  |  |  |  |  |  |  |  |
| ASSETS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROPERTY, PLANT & EQUIPMENT |  | 793,535 |  |  | 701,902 |  |  |  | 694,242 |  |  | 686,010 |  |  | 667,728 |  |  | 638,420 |  |  | 597,009 |  |  |  |  |  |  |  |  |  |  |  |
| INVESTMENTS |  | 110,231 |  |  | 110,231 |  |  |  | 197,453 |  |  | 197,453 |  |  | 197,453 |  |  | 197,453 |  |  | 197,453 |  |  |  |  |  |  |  |  |  |  |  |
| Fixed Deposits & Funds On Call |  | 0 |  |  | 34,728 |  |  |  | 87,222 |  |  | 87,222 |  |  | 87,222 |  |  | 87,222 |  |  | 87,222 |  |  |  |  |  |  |  |  |  |  |  |
| Listed Co.: Sanlam Ltd |  | 1,557 |  |  | 1,637 |  |  |  | 1,557 |  |  | 1,557 |  |  | 1,557 |  |  | 1,557 |  |  | 1,557 |  |  |  |  |  |  |  |  |  |  |  |
| Old Mutual PLC |  | 895 |  |  | 1,123 |  |  |  | 895 |  |  | 895 |  |  | 895 |  |  | 895 |  |  | 895 |  |  |  |  |  |  |  |  |  |  |  |
| Investment Policies |  | 76,965 |  |  | 52,143 |  |  |  | 76,965 |  |  | 76,965 |  |  | 76,965 |  |  | 76,965 |  |  | 76,965 |  |  |  |  |  |  |  |  |  |  |  |
| Retention Money |  | 570 |  |  | 122 |  |  |  | 570 |  |  | 570 |  |  | 570 |  |  | 570 |  |  | 570 |  |  |  |  |  |  |  |  |  |  |  |
| Foundation Investments |  | 865 |  |  | 796 |  |  |  | 865 |  |  | 865 |  |  | 865 |  |  | 865 |  |  | 865 |  |  |  |  |  |  |  |  |  |  |  |
| Guaranteed securities fund |  | 4,000 |  |  | 4,000 |  |  |  | 4,000 |  |  | 4,000 |  |  | 4,000 |  |  | 4,000 |  |  | 4,000 |  |  |  |  |  |  |  |  |  |  |  |
| Redemption fund investment |  | 25,379 |  |  | 15,682 |  |  |  | 25,379 |  |  | 25,379 |  |  | 25,379 |  |  | 25,379 |  |  | 25,379 |  |  |  |  |  |  |  |  |  |  |  |
| LOANS |  | 285 |  |  | 285 |  |  |  | 285 |  |  | 285 |  |  | 288 |  |  | 291 |  |  | 294 |  |  |  |  |  |  |  |  |  |  |  |
| CURRENT ASSETS |  | 104,813 |  |  | 127,799 |  |  |  | 103,745 |  |  | 104,653 |  |  | 164,057 |  |  | 235,836 |  |  | 318,098 |  |  |  |  |  |  |  |  |  |  |  |
| Inventory |  | 7,052 |  |  | 7,076 |  |  |  | 7,501 |  |  | 7,951 |  |  | 8,428 |  |  | 8,933 |  |  | 9,469 |  |  |  |  |  |  |  |  |  |  |  |
| Trade and Other Receivables |  | 96,968 |  |  | 119,931 |  |  |  | 95,453 |  |  | 95,910 |  |  | 100,332 |  |  | 105,585 |  |  | 111,213 |  |  |  |  |  |  |  |  |  |  |  |
| Deposits and Cash |  | 792 |  |  | 792 |  |  |  | 792 |  |  | 792 |  |  | 55,297 |  |  | 121,317 |  |  | 197,415 |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL ASSETS |  | 1,008,863 |  |  | 940,217 |  |  |  | 995,725 |  |  | 988,400 |  |  | 1,029,525 |  |  | 1,071,999 |  |  | 1,112,853 |  |  |  |  |  |  |  |  |  |  |  |

| EQUITY AND LIABILITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FUNDS EMPLOYED |  | 328,241 |  |  | 258,594 |  |  |  | 356,941 |  |  | 368,872 |  |  | 381,394 |  |  | 394,536 |  |  | 408,340 |  |  |  |  |  |  |  |  |  |  |  |
| Accumulated funds |  | -68,924 |  |  | -139,351 |  |  |  | -41,004 |  |  | -29,073 |  |  | -16,551 |  |  | -3,409 |  |  | 10,395 |  |  |  |  |  |  |  |  |  |  |  |
| Specifically Funded -restricted |  | 25,482 |  |  | 25,482 |  |  |  | 25,482 |  |  | 25,482 |  |  | 25,482 |  |  | 25,482 |  |  | 25,482 |  |  |  |  |  |  |  |  |  |  |  |
| Property, plant and equipment funds |  | 375,028 |  |  | 375,808 |  |  |  | 375,808 |  |  | 375,808 |  |  | 375,808 |  |  | 375,808 |  |  | 375,808 |  |  |  |  |  |  |  |  |  |  |  |
| Utilised Funds |  | 383,039 |  |  | 322,061 |  |  |  | 322,061 |  |  | 322,061 |  |  | 322,061 |  |  | 322,061 |  |  | 322,061 |  |  |  |  |  |  |  |  |  |  |  |
| Unutilised Funds |  | -60,978 |  |  | 780 |  |  |  | 780 |  |  | 780 |  |  | 780 |  |  | 780 |  |  | 780 |  |  |  |  |  |  |  |  |  |  |  |
| Unutilised Funds - Restricted |  | 24,788 |  |  | 24,788 |  |  |  | 24,788 |  |  | 24,788 |  |  | 24,788 |  |  | 24,788 |  |  | 24,788 |  |  |  |  |  |  |  |  |  |  |  |
| Debt Redemption Funds |  | 28,179 |  |  | 28,179 |  |  |  | 28,179 |  |  | 28,179 |  |  | 28,179 |  |  | 28,179 |  |  | 28,179 |  |  |  |  |  |  |  |  |  |  |  |
| Residences Fund Restricted |  | -3,345 |  |  | -3,345 |  |  |  | -3,345 |  |  | -3,345 |  |  | -3,345 |  |  | -3,345 |  |  | -3,345 |  |  |  |  |  |  |  |  |  |  |  |
| LONG TERM LIABILITIES - INTEREST BEARING |  | 192,985 |  |  | 214,858 |  |  |  | 236,384 |  |  | 262,264 |  |  | 289,946 |  |  | 315,099 |  |  | 337,598 |  |  |  |  |  |  |  |  |  |  |  |
| LONG TERM LIABILITIES - NON INTEREST BEARING |  | 333,615 |  |  | 313,576 |  |  |  | 313,576 |  |  | 313,576 |  |  | 313,576 |  |  | 313,576 |  |  | 313,576 |  |  |  |  |  |  |  |  |  |  |  |
| CURRENT LIABILITIES |  | 154,022 |  |  | 153,189 |  |  |  | 88,824 |  |  | 43,688 |  |  | 44,609 |  |  | 48,788 |  |  | 53,340 |  |  |  |  |  |  |  |  |  |  |  |
| Trade and Other Payables |  | 57,645 |  |  | 94,253 |  |  |  | 43,488 |  |  | 41,259 |  |  | 44,609 |  |  | 48,788 |  |  | 53,340 |  |  |  |  |  |  |  |  |  |  |  |
| Overdrafts |  | 96,378 |  |  | 58,936 |  |  |  | 45,336 |  |  | 2,429 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| Short Term Portion of Long Term Loans |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL EQUITY AND LIABILITIES |  | 1,008,863 |  |  | 940,217 |  |  |  | 995,725 |  |  | 988,400 |  |  | 1,029,525 |  |  | 1,071,999 |  |  | 1,112,853 |  |  |  |  |  |  |  |  |  |  |  |
| RATIOS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Equity : Funds Employed / Total Assets |  | 32.5% |  |  | 27.5% |  |  |  | 35.8% |  |  | 37.3% |  |  | 37.0% |  |  | 36.8% |  |  | 36.7% |  |  |  |  |  |  |  |  |  |  |  |
| Funding : Debt (interest-bearing)/ Funds Employed |  | 58.8% |  |  | 83.1% |  |  |  | 66.2% |  |  | 71.1% |  |  | 76.0% |  |  | 79.9% |  |  | 82.7% |  |  |  |  |  |  |  |  |  |  |  |
| Solvency :Total Assets/Total Liabilities |  | 2.907 |  |  | 2.555 |  |  |  | 3.062 |  |  | 3.231 |  |  | 3.077 |  |  | 2.946 |  |  | 2.847 |  |  |  |  |  |  |  |  |  |  |  |
| Liquidity : Current Assets/Current liabilities |  | 0.681 |  |  | 0.834 |  |  |  | 1.168 |  |  | 2.395 |  |  | 3.678 |  |  | 4.834 |  |  | 5.964 |  |  |  |  |  |  |  |  |  |  |  |
| Financing : Interest Cost / Interest Bearing Liabilities |  | 15.8% |  |  | 9.5% |  |  |  | 13.7% |  |  | 13.2% |  |  | 11.2% |  |  | 9.6% |  |  | 8.2% |  |  |  |  |  |  |  |  |  |  |  |
| Interest Bearing Liabilities/Total Assets |  | 19.1% |  |  | 22.9% |  |  |  | 23.7% |  |  | 26.5% |  |  | 28.2% |  |  | 29.4% |  |  | 30.3% |  |  |  |  |  |  |  |  |  |  |  |
| Non-Interest Bearing Liabilities/Total Assets (Staff obligations) |  | 33.1% |  |  | 33.4% |  |  |  | 31.5% |  |  | 31.7% |  |  | 30.5% |  |  | 29.3% |  |  | 28.2% |  |  |  |  |  |  |  |  |  |  |  |

| SCHEDULE 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CONSOLIDATED INCOME STATEMENT FOR THE PERIOD 31 DECEMBER 2005 - 2010 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 2nd REVISED BUDGET 2005 |  |  |  |  |  |  |  |  |  |  |  | YEAR TO DATE 2005 |  |  |  |  |  |  |  |  | BUDGET 2006 |  |  |  |  |  |  |  |  |  | FORECAST 2007 |  |  |  |  |  |  |  | FORECAST 2008 |  |  |  |  |  |  |  | FORECAST 2009 |  |  |  |  |  |  |  | FORECAST 2010 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  | R'000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL INCOME | Notes |  |  |  |  |  |  |  | 1,320,516 |  |  |  |  |  |  |  |  |  |  |  | 1,504,961 |  |  |  |  |  |  |  |  | 1,418,242 |  |  |  |  |  |  |  |  |  | 1,440,503 |  |  |  |  |  |  |  | 1,511,999 |  |  |  |  |  |  |  | 1,587,027 |  |  |  |  |  |  |  | 1,666,892 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECURRENT INCOME |  |  |  |  |  |  |  |  | 1,312,784 |  |  |  |  |  |  |  |  |  |  |  | 1,497,443 |  |  |  |  |  |  |  |  | 1,404,660 |  |  |  |  |  |  |  |  |  | 1,426,378 |  |  |  |  |  |  |  | 1,497,309 |  |  |  |  |  |  |  | 1,571,750 |  |  |  |  |  |  |  | 1,651,004 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Government subsidy | 1 |  |  |  |  |  |  |  | 707,445 |  |  |  |  |  |  |  |  |  |  |  | 709,418 |  |  |  |  |  |  |  |  | 807,300 |  |  |  |  |  |  |  |  |  | 794,487 |  |  |  |  |  |  |  | 833,192 |  |  |  |  |  |  |  | 873,700 |  |  |  |  |  |  |  | 917,221 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Education |  |  |  |  |  |  |  |  | 700,102 |  |  |  |  |  |  |  |  |  |  |  | 701,020 |  |  |  |  |  |  |  |  | 771,300 |  |  |  |  |  |  |  |  |  | 794,487 |  |  |  |  |  |  |  | 833,192 |  |  |  |  |  |  |  | 873,700 |  |  |  |  |  |  |  | 917,221 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Upgrading of residence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 36,000 |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Interest & Assessment Rates |  |  |  |  |  |  |  |  | 7,343 |  |  |  |  |  |  |  |  |  |  |  | 8,398 |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Own Income | 2 |  |  |  |  |  |  |  | 595,805 |  |  |  |  |  |  |  |  |  |  |  | 775,606 |  |  |  |  |  |  |  |  | 585,428 |  |  |  |  |  |  |  |  |  | 615,714 |  |  |  |  |  |  |  | 647,607 |  |  |  |  |  |  |  | 681,193 |  |  |  |  |  |  |  | 716,565 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tuition Fees |  |  |  |  |  |  |  |  | 429,962 |  |  |  |  |  |  |  |  |  |  |  | 399,856 |  |  |  |  |  |  |  |  | 417,586 |  |  |  |  |  |  |  |  |  | 438,601 |  |  |  |  |  |  |  | 460,672 |  |  |  |  |  |  |  | 483,853 |  |  |  |  |  |  |  | 508,198 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resident & Restaurant Fees |  |  |  |  |  |  |  |  | 79,000 |  |  |  |  |  |  |  |  |  |  |  | 76,573 |  |  |  |  |  |  |  |  | 85,253 |  |  |  |  |  |  |  |  |  | 91,220 |  |  |  |  |  |  |  | 97,606 |  |  |  |  |  |  |  | 104,438 |  |  |  |  |  |  |  | 111,749 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Donations, Research, Bursaries And Projects |  |  |  |  |  |  |  |  | 23,500 |  |  |  |  |  |  |  |  |  |  |  | 175,986 |  |  |  |  |  |  |  |  | 26,226 |  |  |  |  |  |  |  |  |  | 27,275 |  |  |  |  |  |  |  | 28,366 |  |  |  |  |  |  |  | 29,504 |  |  |  |  |  |  |  | 30,681 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sale Of Goods & Services |  |  |  |  |  |  |  |  | 35,917 |  |  |  |  |  |  |  |  |  |  |  | 50,473 |  |  |  |  |  |  |  |  | 36,432 |  |  |  |  |  |  |  |  |  | 37,890 |  |  |  |  |  |  |  | 39,405 |  |  |  |  |  |  |  | 40,981 |  |  |  |  |  |  |  | 42,621 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Miscellaneous |  |  |  |  |  |  |  |  | 27,426 |  |  |  |  |  |  |  |  |  |  |  | 72,718 |  |  |  |  |  |  |  |  | 19,932 |  |  |  |  |  |  |  |  |  | 20,729 |  |  |  |  |  |  |  | 21,558 |  |  |  |  |  |  |  | 22,420 |  |  |  |  |  |  |  | 23,317 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Investment Income | 3 |  |  |  |  |  |  |  | 9,534 |  |  |  |  |  |  |  |  |  |  |  | 12,419 |  |  |  |  |  |  |  |  | 11,932 |  |  |  |  |  |  |  |  |  | 16,177 |  |  |  |  |  |  |  | 16,510 |  |  |  |  |  |  |  | 16,857 |  |  |  |  |  |  |  | 17,217 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NON RECURRENT INCOME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other Designated Fees Income |  |  |  |  |  |  |  |  |  | 7,732 |  |  |  |  |  |  |  |  |  |  |  | 7,519 |  |  |  |  |  |  |  |  | 13,582 |  |  |  |  |  |  |  |  |  | 14,125 |  |  |  |  |  |  |  | 14,690 |  |  |  |  |  |  |  | 15,278 |  |  |  |  |  |  |  | 15,889 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL EXPENSES |  |  |  |  |  |  |  |  |  | 1,319,674 |  |  |  |  |  |  |  |  |  |  |  | 1,573,766 |  |  |  |  |  |  |  |  | 1,407,116 |  |  |  |  |  |  |  |  |  | 1,428,573 |  |  |  |  |  |  |  | 1,499,477 |  |  |  |  |  |  |  | 1,573,885 |  |  |  |  |  |  |  | 1,653,089 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECURRENT ITEMS |  |  |  |  |  |  |  |  |  | 1,268,757 |  |  |  |  |  |  |  |  |  |  |  | 1,550,534 |  |  |  |  |  |  |  |  | 1,303,932 |  |  |  |  |  |  |  |  |  | 1,367,427 |  |  |  |  |  |  |  | 1,440,125 |  |  |  |  |  |  |  | 1,516,474 |  |  |  |  |  |  |  | 1,597,722 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Personnel |  | 4 |  |  |  |  |  |  |  | 724,112 |  |  |  |  |  |  |  |  |  |  |  | 926,309 |  |  |  |  |  |  |  |  | 736,034 |  |  |  |  |  |  |  |  |  | 792,636 |  |  |  |  |  |  |  | 814,227 |  |  |  |  |  |  |  | 835,641 |  |  |  |  |  |  |  | 857,758 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General Operating |  | 5 |  |  |  |  |  |  |  | 383,214 |  |  |  |  |  |  |  |  |  |  |  | 472,063 |  |  |  |  |  |  |  |  | 494,254 |  |  |  |  |  |  |  |  |  | 395,926 |  |  |  |  |  |  |  | 432,721 |  |  |  |  |  |  |  | 472,267 |  |  |  |  |  |  |  | 514,755 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Short Courses |  |  |  |  |  |  |  |  |  | 33,529 |  |  |  |  |  |  |  |  |  |  |  | 50,473 |  |  |  |  |  |  |  |  | 33,700 |  |  |  |  |  |  |  |  |  | 37,890 |  |  |  |  |  |  |  | 39,405 |  |  |  |  |  |  |  | 40,981 |  |  |  |  |  |  |  | 42,621 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Residence |  |  |  |  |  |  |  |  |  | 90,911 |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 98,146 |  |  |  |  |  |  |  | 102,933 |  |  |  |  |  |  |  | 108,051 |  |  |  |  |  |  |  | 113,570 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Depreciation |  |  |  |  |  |  |  |  |  | 6,509 |  |  |  |  |  |  |  |  |  |  |  | 81,274 |  |  |  |  |  |  |  |  | 7,661 |  |  |  |  |  |  |  |  |  | 8,232 |  |  |  |  |  |  |  | 18,282 |  |  |  |  |  |  |  | 29,307 |  |  |  |  |  |  |  | 41,411 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finance Costs |  | 6 |  |  |  |  |  |  |  | 30,482 |  |  |  |  |  |  |  |  |  |  |  | 20,414 |  |  |  |  |  |  |  |  | 32,284 |  |  |  |  |  |  |  |  |  | 34,598 |  |  |  |  |  |  |  | 32,557 |  |  |  |  |  |  |  | 30,227 |  |  |  |  |  |  |  | 27,607 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SURPLUS/(DEFICIT) BEFORE NON RECURRENT ITEMS |  |  |  |  |  |  |  |  |  | 51,759 |  |  |  |  |  |  |  |  |  |  |  | -45,573 |  |  |  |  |  |  |  |  | 114,309 |  |  |  |  |  |  |  |  |  | 73,076 |  |  |  |  |  |  |  | 71,874 |  |  |  |  |  |  |  | 70,553 |  |  |  |  |  |  |  | 69,171 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NON RECURRENT AND DESIGNATED ITEMS |  |  |  |  |  |  |  |  |  | 50,917 |  |  |  |  |  |  |  |  |  |  |  | 23,232 |  |  |  |  |  |  |  |  | 103,184 |  |  |  |  |  |  |  |  |  | 61,146 |  |  |  |  |  |  |  | 59,352 |  |  |  |  |  |  |  | 57,411 |  |  |  |  |  |  |  | 55,367 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accrued Leave Pay Provision |  |  |  |  |  |  |  |  |  | 3,752 |  |  |  |  |  |  |  |  |  |  |  | 1,126 |  |  |  |  |  |  |  |  | 12,763 |  |  |  |  |  |  |  |  |  | 11,453 |  |  |  |  |  |  |  | 9,431 |  |  |  |  |  |  |  | 7,303 |  |  |  |  |  |  |  | 5,078 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Pension Deficit Funding |  |  |  |  |  |  |  |  |  | 5,065 |  |  |  |  |  |  |  |  |  |  |  | 9,354 |  |  |  |  |  |  |  |  | 8,770 |  |  |  |  |  |  |  |  |  | 8,195 |  |  |  |  |  |  |  | 7,146 |  |  |  |  |  |  |  | 6,039 |  |  |  |  |  |  |  | 4,881 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health Care Liabilities |  |  |  |  |  |  |  |  |  | 17,446 |  |  |  |  |  |  |  |  |  |  |  | 5,234 |  |  |  |  |  |  |  |  | 25,448 |  |  |  |  |  |  |  |  |  | 27,373 |  |  |  |  |  |  |  | 28,086 |  |  |  |  |  |  |  | 28,791 |  |  |  |  |  |  |  | 29,519 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other Designated Fees expenses |  |  |  |  |  |  |  |  |  | 24,654 |  |  |  |  |  |  |  |  |  |  |  | 7,519 |  |  |  |  |  |  |  |  | 20,203 |  |  |  |  |  |  |  |  |  | 14,125 |  |  |  |  |  |  |  | 14,690 |  |  |  |  |  |  |  | 15,278 |  |  |  |  |  |  |  | 15,889 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Upgrading of residence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  | 36,000 |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SURPLUS/(DEFICIT) FOR THE YEAR |  |  |  |  |  |  |  |  |  | 842 |  |  |  |  |  |  |  |  |  |  |  | -68,806 |  |  |  |  |  |  |  |  | 11,126 |  |  |  |  |  |  |  |  |  | 11,930 |  |  |  |  |  |  |  | 12,522 |  |  |  |  |  |  |  | 13,142 |  |  |  |  |  |  |  | 13,804 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RATIOS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finance Cost /Total Income |  |  |  |  |  |  |  |  |  | 2.3% |  |  |  |  |  |  |  |  |  |  |  | 1.4% |  |  |  |  |  |  |  |  | 2.3% |  |  |  |  |  |  |  |  |  | 2.4% |  |  |  |  |  |  |  | 2.2% |  |  |  |  |  |  |  | 1.9% |  |  |  |  |  |  |  | 1.7% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Surplus Before Appropriations /Total income |  |  |  |  |  |  |  |  |  | 3.9% |  |  |  |  |  |  |  |  |  |  |  | 1.5% |  |  |  |  |  |  |  |  | 7.3% |  |  |  |  |  |  |  |  |  | 4.2% |  |  |  |  |  |  |  | 3.9% |  |  |  |  |  |  |  | 3.6% |  |  |  |  |  |  |  | 3.3% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Surplus (shortage) for the year /Total Income |  |  |  |  |  |  |  |  |  | 0.1% |  |  |  |  |  |  |  |  |  |  |  | -4.6% |  |  |  |  |  |  |  |  | 0.8% |  |  |  |  |  |  |  |  |  | 0.8% |  |  |  |  |  |  |  | 0.8% |  |  |  |  |  |  |  | 0.8% |  |  |  |  |  |  |  | 0.8% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Personnel Expenses/Total Income |  |  |  |  |  |  |  |  |  | 54.8% |  |  |  |  |  |  |  |  |  |  |  | 61.6% |  |  |  |  |  |  |  |  | 51.9% |  |  |  |  |  |  |  |  |  | 55.0% |  |  |  |  |  |  |  | 53.9% |  |  |  |  |  |  |  | 52.7% |  |  |  |  |  |  |  | 51.5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Subsidy / Total Income |  |  |  |  |  |  |  |  |  | 53.6% |  |  |  |  |  |  |  |  |  |  |  | 47.1% |  |  |  |  |  |  |  |  | 56.9% |  |  |  |  |  |  |  |  |  | 55.2% |  |  |  |  |  |  |  | 55.1% |  |  |  |  |  |  |  | 55.1% |  |  |  |  |  |  |  | 55.0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Fees / Total Income |  |  |  |  |  |  |  |  |  | 38.5% |  |  |  |  |  |  |  |  |  |  |  | 31.7% |  |  |  |  |  |  |  |  | 35.5% |  |  |  |  |  |  |  |  |  | 36.8% |  |  |  |  |  |  |  | 36.9% |  |  |  |  |  |  |  | 37.1% |  |  |  |  |  |  |  | 37.2% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| SCHEDULE 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CASH FLOW STATEMENT FOR THE PERIOD ENDED 31 DECEMBER 2005 - 2010 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 2nd REVISED BUDGET 2005 |  | YEAR TO DATE 2005 |  | BUDGET 2006 |  | FORECAST 2007 |  | FORECAST 2008 |  | FORECAST 2009 |  | FORECAST 2010 |  |  |
|  |  |  | R'000 |  | R'000 |  | R'000 |  | R'000 |  | R'000 |  | R'000 |  | R'000 |  |  |
| CASH FLOW FROM OPERATING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash Receipts from Students and Government |  |  | 1,343,776 |  | 1,502,374 |  | 1,482,010 |  | 1,423,869 |  | 1,491,067 |  | 1,564,917 |  | 1,644,047 |  |  |
| Cash Paid to Suppliers and Employees |  |  | -1,296,607 |  | -1,463,673 |  | -1,333,637 |  | -1,341,401 |  | -1,401,102 |  | -1,468,544 |  | -1,540,576 |  |  |
| Cash Generated From Operations |  |  | 47,169 |  | 38,700 |  | 148,373 |  | 82,468 |  | 89,965 |  | 96,373 |  | 103,471 |  |  |
| Investment Income |  |  | 9,534 |  | 12,419 |  | 11,932 |  | 16,177 |  | 16,510 |  | 16,857 |  | 17,217 |  |  |
| Finance Charges |  |  | -35,876 |  | -20,414 |  | -34,028 |  | -34,598 |  | -32,557 |  | -30,227 |  | -27,607 |  |  |
| Net cash from operating activities |  |  | 20,827 |  | 30,705 |  | 126,277 |  | 64,047 |  | 73,918 |  | 83,003 |  | 93,081 |  |  |
| CASH FLOW FROM INVESTING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proceeds on disposal of property, plant & equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Additions to Property, plant & equipment |  |  | -61,440 |  | -42,133 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |
| Debt Redemption Investments |  |  | 0 |  | -4,127 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |
| (Increase) / decrease in long term investments |  |  | 0 |  | 0 |  | -87,222 |  | 0 |  | -3 |  | -3 |  | -3 |  |  |
| Change in non-current receivables |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |
| Cash utilised in investing activities |  |  | -61,440 |  | -46,260 |  | -87,222 |  | 0 |  | -3 |  | -3 |  | -3 |  |  |
| CASH FLOW FROM FINANCING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proceeds from interest-bearing borrowings |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |
| Long Term Loans redeemed |  |  | -7,343 |  | -20,414 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |
| Redemption of Long Term Staff Liabilities |  |  | -25,455 |  | 0 |  | -25,455 |  | -21,141 |  | -16,980 |  | -16,980 |  | -16,980 |  |  |
| Cash from financing activities |  |  | -32,798 |  | -20,414 |  | -25,455 |  | -21,141 |  | -16,980 |  | -16,980 |  | -16,980 |  |  |
| Increase/(Decrease) in Cash and Cash Equivalents |  |  | -73,412 |  | -35,970 |  | 13,600 |  | 42,906 |  | 56,935 |  | 66,020 |  | 76,098 |  |  |
| Cash and Cash Equivalents at beginning of period |  |  | -22,966 |  | -22,966 |  | -58,936 |  | -45,336 |  | -2,429 |  | 54,505 |  | 120,525 |  |  |
| Cash and Cash Equivalents at end of period |  |  | -96,378 |  | -58,936 |  | -45,336 |  | -2,429 |  | 54,505 |  | 120,525 |  | 196,623 |  |  |

PLANNING FRAMEWORK FOR 2006