08

Tshwane University of Technology

Quality Improvement Plan

Thandile Makubalo

Table of Contents

Executive Summary	3

Table of Contents	3

List of Acronyms	3

Introduction	3

Recommendation 1: University of Technology Model	3

Recommendation 2: Strengthen Employment Equity	3

Recommendation 3: Open and Inclusive Communication	3

Recommendation 4: Development of Soshanguve and Ga-Rankuwa Campuses	3

Recommendation 5: Faculty Based Campus Model	3

Recommendation 6: Equity of Academic Provisioning	3

Recommendation 7: Strategic Quality Management	3

Recommendation 8: Benchmarking, Surveys and Impact Studies	3

Recommendation 9: Academic Model	3

Recommendation 10: Management of Experiential Learning	3

Recommendation 11: Improving Teaching and Learning		3

Recommendation 12: Foundation Programmes	3

Recommendation 13: Student Access and Academic Development	3

Recommendation 14: Academic Staffing	3

Recommendation  15: Libraries Growth Plan	3

Recommendation 16: Comprehensive ICT Policy and Provisioning	3

Recommendation 17: Impact of Short Courses		3

Recommendation 18: Higher Degrees Committee	3

Recommendation 19: Community Engagement	3

Conclusion	3

Click here to enter text.	3

# Executive Summary

Click here to enter text.

# Table of Contents

Click here to enter text.

# List of Acronyms

Click here to enter text.

# Introduction

Click here to enter text.

# Recommendation 1: University of Technology Model

The HEQC recommends that Tshwane University of Technology select appropriate international universities of technology as models that would help the institution to understand what it means to be a university of technology in substance, and to develop its own indicators so that it can measure its progress towards achieving this goal. (p.xxx)

1.1. Overview

    - This recommendation was based on TUT’s old vision and mission statements.   TUT has revisited the vision and mission which was approved by Council in 2007.  Therefore certain statements are not relevant anymore. How about: This recommendation predates the revision of TUT’s vision and mission. The revised vision and mission which was approved by Council in 2007, has enabled the university to make headway in addressing some of the issues raised by the recommendation.

However, the concept of a UoT, especially the need and benefits of unpacking/analysing it for ourselves, still remains relevant. The activities proposed in the action plan will both show the progress TUT has made towards this analysis, as well as proffer a  development trajectory in terms of what still needs to be addressed. Therefore the concern raised that there was no common understanding amongst management and staff of what needs to be done for the new status to be achieved substantively still holds. It is therefore opportune that TUT’s approach to this recommendation both informed and was central in discussions during the review of TUT’s vision and mission.
How about: The unpacking of the concept of UoT entailed intense discussions/debate at both an internal (institution-wide debate on what constitutes a UoT) and external/national level in the form of TUT’s participation in the South African Technology Network (SATN) A third level, viz. international comparability will entail, as the audit report has recommended, the selection of appropriate international models against which TUT will measure its progress towards the attainment of this new identity. 

1.1.1.	Internal debate/discussions 

These took as their point of departure the concerns raised by the panel in relation to what might be useful to retain/ include in the mission which captured the essence of a UoT.

The first concern of the Panel was that community engagement did not form part of  the mission statement and as a consequence was not conceptualised, planned or budgeted for as an integral part of the institution’s core functions.  The revised mission statement establishes community engagement as one of the university’s pillars: TUT will partner with communities in sustainable development. The details of how this goal/objective … will be realised, forms part of the proposed action plan

Second, it was also unclear to the Panel how the institution conceptualises and plans to inculcate an entrepreneurial ethos. The Panel also noted during interviews with management that the notion of ‘entrepreneurship’ is interpreted in different ways at the institution.  One member of senior management understood that it had to do with the way the business of the different units was carried out;  for example, identifying outcomes, ensuring that appropriate resources are available, and putting in place indicators so that performance can be measured.  Other members indicated that the aim was to integrate entrepreneurship into the curriculum so that students are equipped to become job creators.  The Panel found this interpretation to be underdeveloped.

The panel, however, encouraged TUT to retain this element of its mission first by developing:  “a common conceptualisation of entrepreneurship in a university of technology, and secondly by considering how this understanding may be translated into the three core functions of teaching and learning, research and community engagement, and then establishing the resource implications The agreement reached was that TUT will offer learning programmes that  are responsive to the changing environment, whereby learning programmes are to be designed in the outcomes based mode and should include competencies such as entrepreneurship.

The third concern of the Panel related to lack of or an unclear  elaboration in regard to  statements such as international standards and relevance to the needs and aspirations of South Africa’s people in documentation as well as during interviews with management and staff. Clarity on these concepts, according to the report,  would have enabled  the panel to assess their usefulness.  It is therefore evident that a coherent strategy should be developed. However, the mission statement of TUT addresses this through the inclusion of elements of their essence in a statement relating to the  contribution TUT will make to the socio-economic development of South Africa.  This will be aligned to the identification of new programmes and enrolment targets according to priority areas. What remains to be done is to cultivate a shared understanding of this concept across TUT to enable all to work towards the achievement of this objective, as well as a clearly defined strategy to guide implementation thereof.

1.1.2.	External/National debate 

•The thrust of the debate was to get South African UoTs to arrive at a consensus as to what constitutes a UoT. This consensus should precede the international comparability exercise. To this end, a typology committee, under the auspices of SATN, has launched a process whereby characteristics, attributes, criteria and performance indicators are formulated and documented. SATN provides a forum to discuss higher education issues in the universities of technology, including co- operative education, teaching, research training; technological innovation and technology transfer, advocate the needs, interests and purposes of technological higher education and their communities to government, industry and other groups. The focal areas of the SATN are the responsibility of its standing committees. SATN has made visible progress towards a consensus on the common characteristic features of a South African UoTs.
  
1.1.3.	The international comparability exercise 

How about: Benchmarking has always been seen as a critical ingredient in quality improvement initiatives. Benchmarking goes beyond quality management. As it becomes embedded in the organisation’s day to day activities, it ensures for the organization a way of staying competitive and of moving towards excellence. It is with this in mind that the Panel encouraged TUT to use the experience of international universities of technology to help formulate for itself what it means to be a university of technology in substance and to develop appropriate terms of comparison and indicators, particularly in relation to performance in the core functions, that would allow the institution to chart its progress towards the attainment of this goal. 

SATN’s consolidation of its position on a local model of a UoT sets the stage for differentiation. Drawing and building on this local model, and using it as basis for international comparison, respective UoTs can further enhance both this understanding and identified characteristics by benchmarking with selected international UoT in line with certain distinguishing features of its mission and specific context. The groundwork for this has been prepared through the approval of best practices benchmarking plans on both the national and international level in the 2008-2012 strategic plan. The action plan will refer to plans relating to the role –out of the benchmarking exercise, which in certain instances might lead to collaboration agreements.

The action plan table below summarises both actions already operational to give a sense of what has been accomplished since and prior to the audit, as well as those the university still needs to embark on as part of its efforts to address the recommendation. It further allocates responsibility to specific structures/individuals and gives an idea of the timeframes for achieving the set goals. The table also identifies targets against which TUT will measure its progress in relation to the identified goals, and lastly, to ensure accountability, the table identifies the person, structure which is ultimately accountable for the achievement of results.

1.2   Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2. Draft PI for measuring performance | Dir. SMS Typology team | 2008 |  | PI linked to the characteristics of a UoT | VC as board member of SATN |
|  | 3. Research and Benchmark TUT against international UoT’s | Dir. SMS | 2009 & 2010 | R50 000 | Benchmarking and PI | VC |
| Incorporation of community engagement into the TUT mission | The revises strategic plan establishes CE as a pillar… |  | achieved |  |  |  |
| Strategy for Partnerships with communities |  |  |  |  |  |  |
| Retaining entrepreneurial ethos | The revises strategic plan reflects this concept |  | Achieved |  |  |  |
| Unpacking meaning of entrepreneurial ethos and arriving at a shared definition |  |  |  |  |  |  |
| Cultivation of a shared understanding of “international standards” and relevance to the needs and aspirations of South Africa’s people and strategy |  |  |  |  |  |  |
| Unpacking and defining UoT to arrive at a shared understanding of what the new identity entails |  |  |  |  |  |  |
| communicating understanding to TUT community to enable all to contribute towards its achievement |  |  |  |  |  |  |
| Best practices Benchmarking with appropriate international UoTs |  |  |  |  |  |  |

1.3.  Sustainability and Transfer of Learning

  - /

# Recommendation 2: Strengthen Employment Equity

The HEQC recommends that Tshwane University of Technology strengthen its plans to attain its employment equity targets at all levels within the institution and ensure that these plans have clear time frames and allocation of responsibilities.

2.1. Overview

    - Employment equity is a concept that addresses the area of redress within the sphere of employment pertaining to ensuring substantive equality of opportunity and benefits for all, with special reference to race, gender and disability. One of the government’s strategies for transformation was the passing of the Employment Equity, Act No 55 of 1998. The objective of the act is to promote the constitutional right of equality, eliminate unfair discrimination in employment, and to achieve a diverse workforce which reflects the demographic profile of the country. To this end, the Act requires every designated employer to implement affirmative action measures through conducting an analysis of employment equity policies, practices, and procedures in order to identify barriers to development and advancement. Each designated employer is further required to prepare an employment equity plan and report regularly to the Department of Labour.  At TUT, we consciously apply equity guidelines in various HR functions. Our overall HR plan puts an emphasis on attraction of talent, development of staff and where desirable, retention of staff.  In terms of employment equity issues, the intention is to link the three HR functions, viz.  Employment Equity, Human Resource Development and Recruitment and Selection to ensure a co-ordination of these related processes.

Senior management is committed to ensuring that TUT achieves its broader transformational goals.  Hence, the establishment of employment equity, as part of TUT’S broader transformation agenda.  To this end, the university has established an interim Employment Equity and Training Committee (EETC) as the structure which will drive implementation plans in faculties, and directorates. The establishment of the EETC is also mandated by the Employment Equity Act (EEA). The code of Good Practice in addition, requires the EETC, to be representative of and, reflect the interest of employees from both designated and non-designated groups, and from across all occupational categories and levels of the workforce. The EETC will have several subcommittees in the form of faculty/directory sub-committees, whose composition will also reflects the occupational categories and levels of staff in the respective environments, and which will drive EE planning at departmental level.  The planning at faculties/dept etc level should highlight the following among others:

	The staff profile of the faculty/directorate/department’s should be outlined to provide a basis for understanding each department’s (organization profile in respect of  diversity, and its contribution to the realization of TUT overall equity goals;
	Realistic targets should be set for new or vacant posts;
	Remedial steps for staff development and progression should be in place; and
	Each environment should articulate barriers to and challenges for meeting EE Targets as well as action that will be taken to remedy the situation etc. 
	EE plan should be reviewed annually and progress report submitted to EE Office for consolidation into TUT EE report.
The EETC has an oversight function in the development process, and also acts as a think tank, to arrive at the best solution for the organisation. Because the committee is made up of a diverse group, representing many different viewpoints, it is very creative and is able to provide perspectives from a wide range of employees. 

It is gratifying to report, that TUT has made great strides in developing documents that will guide this process.  Planning documents developed to date include the following:

	Employment Equity: Planning and Implementation Process
	Employment Equity and Management of Diversity: Planning Monitoring and Implementation Guidelines
	Institutional Employment Equity Targets 2009 -2013
The documents listed above will provide the context for as well as inform the development of the Institutional Employment Equity Strategy. 

The setting of targets, a key component of this process, however, depends on the availability of accurate MIS data, which will enable the EE Office to draw data for analysis, planning and setting of realistic EE targets.  With the near finalisation of the match and place exercise, it will not be long before we can, realistically move towards the implementation of the above, a process which will be phased in over the  short, medium and long term, and will  also be linked to the overall strategic goals and objectives of the institution. The EE Plan is envisaged to run from 2009 to 2013.

As can be observed equity planning is a legislative requirement. However, there is a need to go beyond the call of duty/compliance to facilitate the achievement of employment equity targets at TUT which forms part of TUT’s transformation agenda.  To do this the need for a proactive approach   to employment equity as we move into the realm of positive justice/positive discrimination is crucial. The following areas will be targeted for achieving our goal for positive justice.

	Recruitment 
	Succession Planning
	Retention and Reward
	Professional development/ Developing (people) professionally (contractual)

The following action plan outlines the actions which TUT will take to strengthen its employment equity. The plan will be guided by a TUT Employment Equity Strategy whose development will in turn be guided and informed by the already existing planning documents.

2.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Assuring successful implementation of EE be addressed as follows: - Communication, awareness campaigns and training opportunities | - All employees should be made aware and be informed of the content and application of the Act, be sensitized in terms of EE issues, encourage participation in process of developing EE Plan | D/ V: Institutional Planning and Operations EE Directorate/ Deans/HOD’s etc | March 2009 to June 2009 | Human Resource & Training Budget | Stakeholders participation in the process of EE Plan development | EE Directorate/ Deans/HOD’s etc |
|  | - Finalisation of the composition of Employment Equity and Training Committee (EETC) - (current Committee is interim) |  |  |  |  |  |
|  |  | Ex Dir HR/ EE Dir Deans/ HOD’s etc | June 2009 | ITS & MIS | EETC established & faculty sub-committees Match & Place exercise finalised | EE Directorate/ Deans/HOD’s etc |
| Support Employment Equity Agenda: through | - Co-ordination of TUT Employment Equity status | Ex Director: HR EE Director | June 2009 to Sept 2010 | ITS and MIS support project budget | HR data integrity established | D/C: IPO Executive Director: HR Deans/Dir |
| - Recruitment and Selection | Institution’s endeavour to reflect staff profiles in terms of demographic realities. |  | March | MIS HR policies | Targets achieved | D/C: IPO |
|  | EE Strategy to be apply according to set targets | Ex Director: HR EE Director | 2009 to December 2013 |  | according to EE Plan | Executive Director: HR |
| - Human Resource Development & Training | - Provide learning opportunities A comprehensive training & development programme, which includes a personal development & career development plan will provide link between EEA & SDA | Ex Director: HR EE Director |  | HR data integrity established MIS |  | D/C: IPO Executive Director: HR |
|  | Main strategy: align all training & development interventions with NSD strategy, EE strategy and institutional culture change, the performance appraisal system as developmental tool etc. | Deans & Dir/HOD’s |  | HRIS |  | D/C: IPO Executive |
|  | Use AA measures which include number targets as part of strategies to address the stated targets. | Ex Director: HR EE Director Deans & Dir/HOD’s |  |  |  | Director: HR |
|  |  |  |  | Availability of realistic |  | D/C: IPO Executive |
|  |  | Ex Director: HR EE Director Deans & Dir/HOD’s |  |  |  | Director: HR |
| Interventions |  |  | June to Sept 2009 |  | 5% progress towards Employment Equity target achievement |  |
| - Development of realistic affirmative action targets |  |  | June to Sept 2009 |  | Intervention strategies approved and implemented |  |
|  |  |  | January 2009 |  | AA measures implemented & monitored |  |
|  |  |  | to Dec 2009 |  |  |  |
| - Strengthening EE Plan through, implementation & monitoring | - EE outcomes incorporated into managers performance contracts | Ex Director: HR EE Director | Sept 2009 Dec 2010 | Appropriate budget allocation | On going interaction | DV: IPO Executive Dir: HR |
| - Polices, practices Analysis of HR and the working environment culture | - Revisit of HR Policies, e.g. Study Benefits - Alignment for implementation of HR Plan | Ex Director: HR EE Director | Sept 2009 Dec 2009 | Budget for external Audit of HR Policies | Identification of possible barriers that may affect implementation of EE Plan | Executive Director: HR EE Director External Auditors |

2.3.  Sustainability and Transfer of Learning

  - There is a need for an institution-wide understanding of employment equity and diversity issues. Employment equity is a concept
that addresses the area of redress, within the sphere of employment pertaining to ensuring substantive equality of opportunities
and benefits for all; with special emphasis on race, gender and disability. Whereas, management of the diversity should be based
on an organisational culture and climate that truly values and incorporates diversity issues as part of its ethos. A need to develop an understanding and internalise the values that operate within TUT by all stakeholders.  The development of human resource systems which will sustain the learning and the overall change is crucial, the systems can include ongoing training and development, new rewards strategies, new performance criteria, address successful recruitment and retention initiatives as they relate to redress.

It is also recommended that TUT continually reassess the changing environment. It must also move from compliance perspective towards
an understanding of how to utilise difference to build organizational capacity. This transformation will require sensitive and thorough management of the process of change, the most difficult of all, the building of the new values, the inculcation of the value of quality,
equity, productivity, democracy, accountability and an institutional culture that is affirming of the diversity of its human resources.

# Recommendation 3: Open and Inclusive Communication

The HEQC recommends that Tshwane University of Technology develop and implement a strategy to ensure that there is open and inclusive communication across the institution and with all stakeholders.

31. Overview

    - Corporate Affairs

Interpretation and analysis of the recommendation
The HEQC noted challenges relating to the change management effort of populating  new institutional structures through the match and place exercise, and suggested constructive communication with the Unions in order to create a bridging space during the transitional period, and ensure that all stakeholders (including non unionised staff) receive targeted communication that enables them to understand the strategic direction of the University.
Currency of recommendation or aspects of recommendation 
Further to the visit by the HEQC, Management and Unions engaged in a consultative forum through which they jointly agreed on the match and place process, set for completion by September 2008.  Consistent with the match and place was a common communication leaflet sent out to all University stakeholders.  This harnessed an understating of the strategic direction of the University and fostered openness and inclusivity.
In addition, the University established a Consultative Forum, through which Unions can forward/channel their concerns to management.  This Forum meets on a monthly basis and has harnessed relations ... with organised labour.  An additional strategy for facilitating and enhancing communicationhas been  a new practice through which the Director of Corporate Affairs and Marketing is granted observer??? status at all Executive Management Committee meetings.  After each meeting, decisions taken are communicated through the daily electronic newsletter (e-tutor), the student publication (Heita), and the two radio stations (TUT FM and TUT Top stereo).   The Directorate of Corporate Affairs & Marketing has also advised Council to consider line function communication, a key performance area  for all supervisory and management positions at TUT. Please elaborate on this and give us an idea of what you hope to achieve by doing thisResult of this 
Measure Current Levels of performance 
In spite of all these measures, communication ... not attained the desired ...Corporate Affairs and Marketing has not conducted audience research to authoritatively measure the level of line function communication, and departmental meetings, but can unobtrusively/decisively/decidedly state that enquiries and comments by staff indicate a level of not knowing  decisions taken by the University, and the strategic intent of TUT.
An analysis of the problem 
Corporate Affairs and Marketing is of the belief that has noted that whereas all attempts are made to ensure that staff and students are kept abreast of institutional developments through our electronic news bulleting and online staff forums, the level of reading such information is low, as monitored through the number of hits per news item.   Conversely, note has been made of the fact that news on match and place, as well as new appointments, are widely read and there is immense interest on the change effort at TUT.  This has been observed through the number of hits on stories related to these matters.  Equally, it is evident that line function communication is not functioning as anticipated, and those meetings, and memoranda are not used for such. 
Finance 
Corporate Relations to develop strategy.

3.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Corp Affairs Open an Inclusive Communication to all stakeholders | Review TUT website Electronic notice boards Review e-tutor Review Heita Develop management communication teaser Develop a briefing package for Council Develop an online newsletter for alumni Strengthen relations with TUT radio stations |  | 2008- | Increased Funding, and personnel | Knowledge and understanding of TUT developments, strategic direction, events, and policies | Directorate of Corporate Affairs and Marketing |
| Open an Inclusive Communication to all stakeholders | Develop line function communication guide |  | 2008- | Institutional wide commitment and co-operation by all supervisors and managers | Dissemination of information at departmental level (meetings, seminar, and circulation of notices) | All TUT supervisors and managers |
| Open an Inclusive Communication to all stakeholders | Capacitate communication with Unions Capacitate communication with student representative councils |  | 2008- | information sharing sessions | Understanding and appreciation of institutional strategic direction | Human resources and Student Affairs divisions |
| Finance Inclusive communication | Training of budget managers (workshops) | Director Expenditure | Annual/Ongoing? | None | Number of staff trained | Training of budget managers (workshops) |
|  | Informing students (notices, publications, SMS's) | Director: Revenue | Continuous | None | Number of articles | CFO |

3.3.  Sustainability and Transfer of Learning

  - Corporate Affairs 
Intervention and sustainability measures entail :

Develop an employee communication guide to assist supervisors and managers in departmental/directorate based communicative efforts.

Develop a continuous line communication  briefing package.

Targeted focus groups communication should be consistent.

Face to face interaction with decision makers must be continuous. 

Unit/Departmental/Directorate meetings with Executives must be a regular practice. 
 
Provide computer literacy training ??? to ensure access to information.

Recommendation 4: Development of Soshanguve and Ga-Rankuwa Campuses

The HEQC recommends that Tshwane University of Technology engages the local and provincial authorities in relation to the development of the Soshanguve and Ga-Rankuwa campuses in order to ensure that the relocation of faculties is done in the context of a social compact which supports the institution’s efforts to attract staff, students and suitable industrial partners.

4.1. Overview

    - Business Development
Interpretation and analysis of the recommendation 
The recommendation stems from the proposed single Faculty location model which intends to provide equivalence of provision to all campuses as well as equivalence of experience to students. However, due to the relative campus conditions at Soshanguve and Ga-Rankuwa, it was noted that it may be imperative for the university to partner with other parties in order to achieve the necessary development of these campuses. This engagement, particularly with provincial and municipal governments, and local communities, is seen as key in assisting the university establish itself in the community and in enabling socio-economic development of the surrounding areas. 
Aspects of recommendation
The recommendation covers the specific aspect of engaging local and provincial authorities in campus development. This is to lead to the creation of a ‘social compact’ providing the background for the faculty relocation. Both these actions are, in turn, to contribute to the university’s efforts to attract staff, students and partners. Note that the initial action supported by this recommendation can be seen as a specific action contributing to Recommendation 3, in enabling the university’s interaction with the community.
Rationale for our approach (improvement actions) to addressing the recommendation
The university intends managing the development of these campuses in the context of engaging with, and providing facilities for, staff, students and the community, partnered with the need to drive third-stream income from such developments. The development of the campuses is thus approached to simultaneously address all aspects of the recommendation.
The university has started investigating possible developments to the Ga-Rankuwa campus, with appropriate facilities for both the university and the wider community. It is noted that these actions are long-term initiatives, which by their very nature, cannot be completed in the short-term. Initial action has already been taken in the short-term, however, to identify specific initiatives to upgrade the campuses. 
The university acknowledges that partnerships with external bodies to effect the appropriate upgrades are necessary. Hence, the developments will be spearheaded through public-private partnerships. This will enable the development of facilities with a community-driven component while maintaining the commercial possibilities of such facilities. The transformation of this campus will be initiated by a feasibility study for which external grant funding will be sought.
The evidence/performance indicators: 
Quantitative performance indicators	Qualitative performance indicators:
Funding raised for projects from external sources	Feedback from community on proposed developments
Funding raised for projects from external sources 	Feedback from students and staff on proposals
Funding provided by the university	Relationships formed with external organisations, public or private
Number of facilities (including sporting facilities) provided	
Number of student-beds provided in residences	
Number of consultations with community	
Number of consultations with local and provincial government	
Number of public-private partnerships initiated	

Advancement Office
In the quest to provide a unified service for the whole institution which is the result of the merger of the three institutions, management has developed a model that seeks to realise the equalisation of services at different learning sites of TUT. 
It is clear that in developing this model serious thought was given to the resource disparities that continue to beleaguer the sites located in under-resourced communities such as the township environments. Given these challenges, it is comprehensible that the addressing the challenges prevalent in Soshanguve and Ga-Rankuwa are beyond the capacities of the University. This makes it important for TUT to develop a comprehensive approach to  ... which will include working with different stakeholders in these communities, including local government, local economic development agencies, spatial development agencies and suitable industrial partners.
The Advancement Office, as a role-player in community engagement, partnership formations, fundraising and development facilitation needs to cooperate with other university environments to work with various forums that have an interest in the development of these townships. This integrated development approach will work alongside the implementation of the single Faculty location model. It should also be mentioned that higher education can be an important driver of socio-economic development as examples have shown elsewhere. Therefore, there is need for a proper connection between the University and these immediate communities.

4.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Bus Development Engagement with local and provincial authorities | Incorporated into feasibility study | To be performed by external service provider/ outsourced | June 2009 | Please provide an estimate |  | PPTT (Chair: Mr Bleming Nekati) |
| Development of Ga-Rankuwa campus | Investe of gap between existing facilities and required facilities | PPTT | Completed Would help if you could provide date |  | Requirements and opportunities for new campus identified | PPTT (Chair: Mr Bleming Nekati) |
|  | Develop initial plans | PPTT | Completed Would help if you could provide date |  | Models and plans of proposed developments | PPTT (Chair: Mr Bleming Nekati) |
|  | source appropriate funding for feasibility study (internally and externally) | BDU | September / October 2008 | R200,000 | Successful proposal/s | Director: Mr Bleming Nekati |
|  | Feasibility study completed/Finalise???feasibility study | BDU | December 2008 |  | Submission of feasibility study document | Director: Mr Bleming Nekati |
|  | Feasibility study recommendations to be adopted, including incorporation of outcomes from consultation with community and local/provincial authorities | PPTT | Early 2009 |  | Adjusted plans approved by appropriate university committees | PPTT (Chair: Mr Bleming Nekati) |
|  | Seek additional funding and partnerships to cover development costs | PPTT | 2009 |  | Partnerships established and proposals successful | PPTT (Chair: Mr Bleming Nekati) |
|  | Work tendered through appropriate channels, contractors appointed, and work to begin | Operations Division | 2009 | Funding will be sought externally to cover some of the costs | Contractor appointed through university tender process | Executive Director: Operations |
|  | Development completed and faculty transition completed | Operations Division | Long-term |  |  | Executive Director: Operations |
|  | evaluation of campus in addressing needs of staff, students and community, including performance of commercial entities | DQP and BDU | Long-term/ Ongoing |  | Appropriate Quantitative and Qualitative performance indicators as above | Director: DQP Director: BDU |
| Development of Soshanguve campus | Existing plans as per ‘Soshanguve – The Living Lab’ proposal to be reviewed, particularly concerning the campus development aspects | PPTT | Medium-term |  |  | PPTT (Chair: Mr Bleming Nekati) |
|  | Adjusted/amended plans approved |  |  |  |  |  |
|  | Appropriate partnerships Establish and funding sought/seek | Executive Dean: ICT |  |  |  |  |
| Adv Office Relocation of Faculties within the context of a social compact | Lobby local government, industries, community organisations and NGOs in the areas Mobilise required resources from industry and funding agencies to support development efforts in the areas. | RIP AO/ BD TLT | 5 yrs | -Research funding -Funding of development processes -Funding for programmes and projects -Personnel with knowledge of development project | Number of development research projects Number of projects funded Provision of Project staff | RIP AO/BD AO/BD/SARO/Faculties |

4.3.  Sustainability and Transfer of Learning

  - Advancement Office
It would be important for the Campuses and the designated environments within the University to have representations and develop working relationships with NGO’s community based organizations, local economic development agencies and local government of the area through designated individuals who will provide a platform for engagement and ongoing communication so that they can assist environment such as AO and BD on the work that needs to be done

# Recommendation 5: Faculty Based Campus Model

The HEQC recommends that Tshwane University of Technology give due consideration to the impact that the additional costs of the Faculty based campus model will have on the access to higher education of financially disadvantaged students.

5.1. Overview

    - Following the merger of TUT, TNG and TNW, The Executive Management Committee and the Council of Tshwane University of University have decided that the most appropriate model for a future TUT would be a one Faculty, one Campus model. Single faculty location model 
Following the merger of TUT, TNG and TNW, The Executive Management Committee and the Council of Tshwane University of University emphasised transformation as one of the most important goal of the new institution and decided that the most appropriate model to implement this transformation in a future TUT would be a one Faculty, one Campus model.  
Implications were as follows:  Faculty of ICT to be on Soshanguve, eMhalaleni and Polokwane Campuses; Faculty of Engineering and the Built Environment to be on the Pretoria and eMahlaleni Campus, Faculty of Humanities to be on the Soshanguve, Polokwane and Nelspruit Campuses, Faculty of the Arts on the Pretoria (Arcadia) Campus; Faculty of Sciences on the Pretoria (Arcadia) Campus; Faculty of Management Sciences on the Pretoria, Nelspruit and Polokwane Campus and the Faculty of Economics and Finance to be on the Ga-Rankuwa and Nelspruit Campuses.
Principles: 
This decision was based on a number of principles: 
o	Optimal utilisation of Facilities: 
All Faculties have unique requirements. By locating  Faculties  on certain campuses, those requirements could be focused on one campus.
o	Optimal utilisation of Staff
After the merger is was noticed that some Faculties have a presence on al Campuses. This provided significant challenges because programmes were offered in different ways, smaller number of students has been serviced on the various campuses and no optimisation of resources could take place.
o	Focus
By having all staff and students ... concentrated on campuses much better collaboration and progress could be made on Faculty Priorities, staff training and building a unified culture.
o	Financial
The decision was ultimately also an economic decision, which would lead to optimal utilisation of facilities, human resources, equipment and the avoidance of duplication as far as possible.
Challenges: 
This process did put new demands and challenges on Faculties.  Much uncertainty  followed and the following challenges had to be taken care of: 
o	Management of Change:
Faculties had to spend huge amounts of time communicating to staff and students the new vision, overcome resistance to change, unify the staff from the former Campuses to all follow the same vision. A process to ensure that students pride themselves in their new environments had to be launched. 
o	Equalising of Facilities:
Some campuses did not have the same level of facilities and the equalisation of campuses received considerable attention. Close to R150 million have been spent on Ga-Rankuwa and Soshanguve campuses to upgrade residences, security, offices, laboratories and lecturing Faculties.  
o	Review recruitment areas of Faculties:
Some Faculties like the Faculty of ICT reviewed  the move to Soshanguve and had to adjusted to the new environment and have decided to recruit future students from Gauteng up to Limpopo and over to Rustenburg.  
o	Transformation
The communication and change awareness  programmes will address transformation from the old individualist cultures to a new collective culture.
All of these are actions taken by the university to create a stable management structure and a sustainable academic environment for the delivery of quality tuition across all faculties and campuses.
HEQC Concerns
The HEQC audit report documented the following concerns:
o	“During a range of interviews with academics and students the Panel heard concerns about issues of access. 
o	The move to a Faculty based model may compromise poor and rural students’ ability to access higher education; for example, potential students would no longer be able to enrol for their preferred course at the nearest campus to their home but might have to travel from Nelspruit to Witbank. 
o	This places another cost burden on already poor students. 
o	It also has implications for the institution in terms of its future student profile with respect to South Africa’s demographic profile. 
o	The Panel therefore urges the institution to give attention to this issue and to develop mechanisms to ensure that access is not compromised.” 
 The HEQC Report comments as follows in its concluding remarks: 
“The institution knows that its main challenges have to do with developing a new identity for the merged institution, resourcing all its campuses equitably, improving the quality of teaching and learning, and ensuring its financial sustainability. The institution has identified the processes and structures to help it to respond to these challenges; one of them is the Faculty based campus model.” The challenge is for TUT to … for the success of the SFLM, and the Improvement plan will address itself to this through 

For the purpose of the quality improvement plan the following aspects were identified: 
a.	Quality of Facilities across merging campuses should be the same
o	Part a: All lecturing facilities and laboratories and offices should be of the same standard across all campuses
o	Part b: All network access should be of the same standard
o	Part c: All air-conditioning, communications and standby-power should be the same across all campuses
b.	 Access for students should not be negatively impacted due to the merger
o	Part a: Clear communication during recruitment on where different Faculties are and implications if you want to enroll
o	Part b:  Faculties to devise strategies on how they will become world-class entities on their campuses
o	Part c: Accommodation should be available on or close to all Campuses
c.	 Maintenance and landscaping across the merging campuses should be equalised
o	Part a: Implement serious landscaping improvements at Ga-Rankuwa and Soshanguve Campuses
o	Part b: Urgent improvement of Ga-Rankuwa and Soshanguve sport facilities to be in line with that of Pretoria

d.	Initially Funding should benefit Northern Campuses to come in line with quality of
      facilities at the Pretoria campus

o	Part a: TUT to take conscious decision to identify shortcomings on Ga-Rankuwa and Soshanguve and top-slice the budget for those campuses
e. Communication with staff and students to explain rationale and for single camps model should be structured
o	Part a: Change management awareness campaign amongst students to look after TUT assets
o	Part b: Targeted communication strategy to staff and students to explain rationale and plans
f. All identified SHE requirements should be attended to as a matter of urgency
o	Part a: Finalise Emergency Preparedness Plan
o	Part b: Attend to SHE requirements such as emergency exits, toilets and electrical installations

g. Equalise all campuses for Disability Access
o	Part a: Improve infrastructure to provide access to disabled students on all campuses
o	Part b: Improve teaching equipment to cater for disabled students in wheel chairs and with hearing and visibly impaired students

5.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| a. Quality of Facilities across merging campuses should be the same |  |  |  |  |  |  |
| Part a: All lecturing facilities and laboratories and offices should be of the same standard across all campuses | - Determine the standard and determine the gaps on each campus - Get plan approved and implement | HEDS, Academic Committee | End 2008 End 2010 | Revised IOP | All lecturing facilities and laboratories of same standard by end 2009 | TLT, RIP |
| Part b: All network access should be of the same standard | Evaluation report on the status of the network and requirements for the next five years on each campus | ICT Steering Committee, Academic Support Committee | Mid 2009 | Integrated Technology Plan | All lecturing facilities and laboratories of same standard by end 2009 | Executive Director, Operations |
| Part c: All air-conditioning, communications and standby-power should be the same across all campuses | Evaluation report on the status of the air-conditioning, communication and standby power on each campus | Directorate Operations; Academic Support Committee | Mid 2009 | Integrated Technology Plan | All lecturing facilities and laboratories of same standard by end 2009 | Executive Director, Operations |
| b. Access for students should not be negatively impacted due to the merger |  |  |  |  |  |  |
| Part a: Clear communication during recruitment on where different Faculties are and implications if you want to enrol | Communication Strategy to students and prospective students indicating programmes offered, learning sites and rationale | Corporate Affairs, Deans | End 2008 and continuously thereafter | Marketing Plan; Business Plans of Faculties | Prospective Students begin to identify learning sites as sites of specialisation | Director, Corporate Affairs |
| Part b: Faculties to devise strategies on how they will become world-class entities on their campuses | Faculty Five Year Business Plans | Deans | End 2009 | Business Plans | Market surveys | TLT |
| Part c: Residence capacity to be increased for distant campuses | - Residence capacity analysis done for ten years - Implementation of plans | Director, Residences | End 2008 End 2010 | Business Plan | Market analysis and Faculty enrolment figures | Director, Residences and Deans |
| c. Maintenance and landscaping across the merging campuses should be equalised |  |  |  |  |  |  |
| Part a: Implement serious landscaping improvements at Ga-Rankuwa and Soshanguve Campuses | Implement landscaping plan at Ga-Rankuwa and Soshanguve | Directorate: Operations; Campus Heads | End 2009 | Landscaping Plan | Implemented plan | Director Sport; Campus Head |
| Part b: Urgent improvement of Ga-Rankuwa and Soshanguve sport facilities to be in line with that of Pretoria | Compile plan for sports facilities upgrade at the Ga-Rankuwa and Soshanguve Campuses | Sports Directorate; Campus Heads | End 2009 | Sports Facilities Plan | Upgraded sports facilities | Director Sport; Campus Head |
| d. Initially Funding should benefit Northern Campuses to come in line with quality of facilities at the Pretoria campus |  |  |  |  |  |  |
| Part a: TUT to take conscious decision to identify shortcomings on Ga-Rankuwa and Soshanguve and top-slice the budget for those campuses | Identify equitable level and quality of facilities, equipment, fencing and lighting | Deans; Campus Heads/ Campus Directors | End 2009 | Budget | % improvement against plan | TLT; RIP/ Administrative Support |
| e. Communication with staff and students to explain rationale and for single camps model should be structured |  |  |  |  |  |  |
| Part a: Change management awareness campaign amongst students to look after TUT assets | Develop a strategy for a change Management Awareness Campaign amongst students | Directorate, Corporate Affairs; Campus Head/ Campus Directors. | End April 2009 | R500 000 | IChange Management Awareness Campaign strategy | Campus Head/ Campus Directors; Director, Corporate Affairs |
| Part b: Targeted communication strategy to staff and students to explain rationale and plans | Develop and and Implement Communication Strategy for staff and students | Directorate, Corporate Affairs; Campus Head/ Campus Directors; Deans | End April 2009 | Corporate Affairs and HR to draft Communication Strategy per campus | Implemented Communication Strategy | Campus Head/ Campus Directors; Director, Corporate Affairs |
| f. All identified SHE requirements should be attended to as a matter of urgency |  |  |  |  |  |  |
| Part a: Finalise Emergency Preparedness Plan | Develop and implement an Emergency Preparedness Plan for each campus | Executive Director, Operations; Campus Head/ Campus Directors | End April 2009 | Consultants to draft Emergency Preparedness Plan per campus R250 000 | Emergency Preparedness Plan per campus | Campus Head/ Campus Directors; Appointed Officers |
| Part b: Attend to SHE requirements such as emergency exits, toilets and electrical installations | Implementation of SHE report from various campuses | Academic Support Committee, Executive Director Operations; Campus Head/ Campus Directors | Mid June 2009 | R5 million for Phase 1 | % progress according to plan | Campus Head/ Campus Directors; Appointed Officers |
| g. Equalise all campuses for Disability Access |  |  |  |  |  |  |
| Part a: Improve infrastructure to provide access to disabled students on all campuses | Perform a needs assessment per campus and compile a report with recommendations | Campus Heads/ Campus Directors; Directors from Operations | End April 2009 | R300 000 consulting fees | % Recommendations accepted | Campus Heads/ Campus Directors |
| Part b: Improve teaching equipment to cater for disabled students in wheel chairs and with hearing and visibly impaired students | Needs assessment per campus and recommendations report | Campus Heads/ Campus Directors; Deans, Directors from HEDS, ICT Services. | End April 2009 | R200 000 consulting fees | % Recommendations accepted | Campus Heads/ Campus Directors |
| h. SLA’s between Faculties/Campuses and the Support Environment | Draft Service Level Agreements to be and signed between campuses and support environments such as HR, Operations, ICT Services | Campus Heads/ Campus Directors; Deans, Directors from HEDS, ICT Services, Operations, SARO | First quarter 2009 | SLAs | Signed SLAs by end April 2009 | TLT, RIP |

5.3.  Sustainability and Transfer of Learning

  - •	Faculties to include Key Performance Areas in their Business Plans to ensure that campuses become viable entities.
•	Faculties on each campus to do a thorough analysis of their recruitment areas of future students to ensure that they form seamless partnerships with the schools in their revised catchment areas
•	Faculties to review their research niche areas and adapt their research to the new environment.
•	Monitor the implementation of IOP, Business plans, policies and guidelines.
•	Policies and guidelines are put in place to facilitate and ensure justifiable distribution of resources across campuses.
•	Sustainability of programmes and learning sites are created through the throughput committee that monitors the implementation of the macro strategy to ensure the achievement of necessary success rates on all learning sites.
•	The implementation of approved structure is a long term process and will be monitored through faculty budget allocations.
•	To ensure similar student experiences on all learning sites; continuous monitoring of teaching and learning experiences of students on the various campuses will be implemented as stipulated in the relevant policy.
 /

# Recommendation 6: Equity of Academic Provisioning

The HEQC recommends that Tshwane University of Technology develop strategies that have clear time frames and allocation of responsibilities to ensure that there is an equivalent learning experience across campuses for all of its students. This includes giving attention to infrastructure, quality of staff, student and academic support.

6.1. Overview

    - 6.1.1	Synopsis  of Recommendation 6
We have summarised the preamble to recommendation six, as the recommendation itself may seem somewhat diffuse with regard to the complexity of the particular matter. How about: The recommendation covers a range of very complex issues which undermine equity of provisioning and lead to differential learning experiences for students at TUT campuses, viz the Campus Management Model, the Resource Allocation Model (RAM), and the Programme Qualification Mix (PQM) First,the campus management model: the recommendation relates to various matters pertaining to the campus management model, with specific reference to dual reporting lines The HEQC audit report refers to the differential reporting arrangements (solid and dotted lines) obtaining at the various campuses.. Of great concern the dotted line reporting to the rotating Campus Director at the Ga-Rankuwa and Soshanguve campuses, versus the solid reporting line to the Pretoria West Campus. The concern is two-fold: (a) the extremely heavy workload of rotating campus directors, who are also the Executive Deans of their respective faculties, and (b) the fact that Executive Deans are excluded from the EMC. In addition the final reporting lines at the Tshwane campuses differ from those atf the three distant campuses. The executive deans at the four Tshwane campuses report to the DVC of TLT, while campus directors of the distant campuses (eMalahleni, Nelspruit and Polokwane) report to the DVC RI&P.  
•	Managers at the distant campuses report to their line managers in Tshwane with a solid line, while there is a dotted line to the respective campus directors.   
•	Second: The RAM): TUT campuse are differentially resourced, both in terms of material and human resources, as well as in terms of infrastructure provisioning, both In terms of infrastructure, HEQC singles out the Polokwane Campus. In addition, HEQC refer specifically to the Ga-Rankuwa and Soshanguve campuses, where HEQC say there are significant infrastructure imbalances that are not addressed by the Resource Allocation Model (RAM).
•	Third The PQM):The HEQC further expressed concern about the implications of the new PQM on the two Mpumalanga campuses, in terms of their alignment with actual needs, as well as the future requirements of the Mpumalanga National Institute for Higher Education (NIHE).
6.1.2	Background
The RAM  does not ensure equitable  distribution of funds across campuses. It is a financial management tool designed to manage debits and credits. In other words, it is incorrect to assume that it could be held responsible for inequitable distribution of funds.TUT started addressing equity of resource provisioning at its learning sites, after the merger. A grant of R302 million was secured from DoE, for this purpose. TUT has already allocated the entire grant according to the priorities determined in the Capital Allocation Budget.  This figure excludes an R11million interest, which still has to be allocated. TUT has already received another R111 million, while yet another R55 million is expected from the DoE at the end of August. TUT has thus made significant progress in terms of adequate and equitable provisioning of resources. 
 As far as the management model is concerned, TUT have invested substantial time and effort in addressing management structures. In the process TUT has taken into account that the differences in the nature of operations at its campuses, resulting in a dynamic approach. Management has continually been addressing the matter, including the bespoke management model for the three distant campuses. This process had been ongoing at the time of the HEQC visits to in 2007. All structures have, however, not yet been finalized.
6.1.3	Recommendations 
•	TUT should continue to address past inequalities in terms of resource provisioning , at  all its campuses,especially at Ga-Rankuwa, Polokwane and Soshanguve campuses. 
•	TUT should investigate the current practice of rotating campus directors, administrative support and other, relevant administrative and managerial matters at the Ga-Rankuwa and Soshanguve Campuses.
•	TUT should finalise the reporting structure and total management model at its three distant campuses. This may imply a different approach with regards to the academic and support services at these three campuses.
•	TUT should carefully consider the impact of its PQM on the market needs of Mpumalanga.
•	TUT should investigate the disparities in terms of final reporting lines at the three distant campuses, versus the other campuses (reporting to DVC, TLT vs reporting to DVC, RIP) and address the matter. 
•	TUT should make a concerted effort to communicate its past, current and future activities in this regard in a regular manner to ensure all stakeholders are informed.
•	It is recommended that TUT establish a feasible, attainable and practicable time frame for the above endeavours 
•

6.2.  Improvement Action Plan

| Aspect of Recommen-dation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/ Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Investigate resources-allocation to determine efficacy of current model | - Establish need for additional model for funds distribution. - Implement new model | - FBD - TLT - Strategic Management Support | September-October 2008 | DoE grant already allocated | - DoE buy-in - Industry buy-in | - Strategic Management Support - Dr Tromp |
| Determine status of infrastructure provisioning at Ga-Rankuwa, Polokwane and Soshanguve campuses | - Decide in performance indicators/minimum standards - Determine current status - Determine immediate needs (2008) - Determine medium and long term needs, i.e. 2009-2013 | - Executive Deans/Campus Directors of Economics and Finance, Humanities and ICT - IPO | September-December 2008 | Human Resources | Support and cooperation of all stakeholders | Prof. Molefe |
| Determine status of infrastructure provisioning at other campuses | Remaining campuses (except abovementioned) | - RIP - IPO - Campus Directors | September-December 2008 | Human Resources | Support and cooperation of stakeholders | IPO |
| Distribute additional funds where needed | - Allocate R11 million interest through Capital Allocation Budget - Distribute additional funds - Monitor applications of funds | - FBD - IPO - Relevant environments | January 2009-December 2013 | Industry /DoE additional grants/interest on grant | Funds obtained and allocated | IPO |
| Obtain additional funding | - Approach DoE - Approach industry | - TLT - Advancement Office | October 2008-December 2009 | DoE/Industry | Industry buy-in | VC or Prof. Van Staden |
| Determine status and efficacy of management model at Ga-Rankuwa and Soshanguve campuses | - Determine current (actual) status - Compare with current reporting matrix - Suggest amendments | - DVC TLT - DVC IPO - Executive Deans - Line managers | October-November 2008 | Human Resources | Support and cooperation of stakeholders | Prof. Van Staden |
| Determine status and efficacy of management model of Distant Campuses | - Determine current (actual) status - Compare with current reporting matrix - Suggest amendments | - DVC TLT - DVC IPO - Executive Deans - Line managers - HODs - Section Heads | October-December 2008 | Human Resources | Support and cooperation of stakeholders | Dr Nevhutalu/Prof Van Staden |
| Determine effect of PQM on Mpumalanga campuses | - Compare final PQM with regional needs - Compare final PQM with future NIHE requirements | - VC - DVC TLT - Executive Deans - Campus directors - Academic Section Heads - NIHE | October-December 2008 | Operational cost, eg travelling, accommodation & subsistence | NIHE support | Dr Nevhutalu |
| Determine final reporting line (TLT vs RIP) | - Revisit strategic reasoning - Decide on efficacy - Determine new reporting line, if required - Implement new strategy, if required | - DVC TLT - DVC RIP | October-November 2008 |  |  | Dr Nevhutaly/Prof Van Staden |
| Devise information dissemination strategy | - Devise strategy - Implement strategy | - Corporate Affairs - Strategic Management Support | October-November 2008 |  |  | Mr Dilotsotlhe |

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |

6.3.  Sustainability and Transfer of Learning

  - /

# Recommendation 7: Strategic Quality Management

The HEQC recommends that Tshwane University of Technology conceptualise its quality management system in such a way that it moves beyond compliance and focuses on provision of good quality teaching and learning, research and community engagement. For this to be possible senior management needs to take a more active role in providing intellectual and strategic direction in terms of the formalisation, implementation and monitoring of a quality management system across all campuses which suits the profile of a university of technology.

7.1. Overview

    - The above recommendation relating to TUT’s quality management system underpins our core
business and highlights the key elements on which efforts at addressing it should focus in order
to effectively and successfully make the transition from compliance to excellence. In our
understanding, these are:
a. TUT to formalise implementation and monitoring of a quality management
system
b. senior management to take a more active role in providing intellectual and
strategic direction
c. TUT to conceptualise its quality management system in such a way that it moves
beyond compliance...”
Whilst TUT’s commitment to ongoing improvement, evidenced by a battery/ a wide range of
internal self evaluation activities contains the seeds for facilitating this transition, we believe that
our first call is of necessity to consolidate our actions vis-à-vis quality management at the level
of compliance, especially in view of our status as a newly-merged institution and in view of our
new identity as a University of Technology. This, however, we believe should occur
simultaneously with the laying of a solid foundation for actions which will move us gradually
towards excellence. Our response to this recommendation, charts the road from compliance
through continuous improvement to excellence with specific reference to the role of TUT’s
quality management system. We regard the recommendation as long-term, in as far as it is
ongoing, but should be able to report significant progress on the first two aspects within a period
of 12 months.
The problem/issue regarding the TUT quality management system indeed revolves around the
notion of formalisation of the system in relation to its development. The issue/problem is a direct
sequel of the merger process and our newly acquired status as a University of technology,
which, among other things, necessitated that, while managing the exigencies of rapid transition
and our newly acquired status, we simultaneously continue to fulfill and deliver on our academic
mandate. What this entailed is that we had to have the structures, including the policies and
procedures to enable the newly merged institution to operate “normaly”. In the case of policies,
and in many instances, the only expeditious although not most effective way to go about this
was to consolidate policies from the three constituent institutions, and benchmark these against
policies of other institutions. First, the haste with which this consolidation (at least for some
policies) was accomplished, often led to a product which sometimes undermined the goals for
which it was designed in the first place. Second, this manner of doing things, once again of
necessity, forced us to operate on a contingency basis, where we developed policies and
procedures as and when a dysfunctional situation pointed to the existence of a policy or other
gap. Further and most importantly, this approach precluded any formal development of a quality
management system which would normally begin with a decision and agreement on quality
principles, to ensure buy-in from and ownership of the process by all involved, and which would
therefore be driven by senior management. This would normally be followed by a classification
of the processes/practices for which policies, procedures, guidelines, and forms needed to be
developed, in order to ensure, as much possible, that there were no gaps. Whilst this approach
ensured/enabled almost full functionality on the part of the institution, we were not able to reach
optimal levels in terms of effectiveness and efficiency. For this reason, we believe there is an
urgent need to revisit the process, by classifying our processes, and identifying policy and other
gaps in a much more systematic and proactive manner. One of the outcomes of this exercise
would be a planned process/programme/schedule for policy development, where participation of
the relevant role-players would be ensured, timelines defined and appropriate responsibilities.
As indicated above, the process of formalisation starts with and is driven by senior
management, whose main function is to provide both strategic and intellectual direction. One of
the key milestones in the development of a quality management system is the formulation of a
quality policy, which defines the quality management systems objectives based on an analysis
of the organisational strategy, and which commits management to resourcing, and actively
promoting, and supporting it.
The transition from compliance to excellence: Whilst we appreciate the need to ensure
compliance, and of addressing this aspect of the recommendation, we wish to reiterate that we
regard compliance as neither a goal nor a shaper of our ultimate destiny. We subscribe to the
notion of continuous improvement, the gradual/incremental steps of which will bring us closer to
our goal of excellence, which can be described as a state of having exceeded both internal and
external customer requirements in terms of the quality of our products and services. Our efforts
at will therefore be buttressed by systematic best practices benchmarking activities, first
internally, as we believe that inside TUT lies, often unknown, a vast treasure house of
knowledge, know-how and best practice, which if tapped, could yield huge gains in
effectiveness, efficiency and overall organisational competence. To this end, the DQP aims to
formally establish communities of practice (CoP) within the directorate, something which has
already started to occur naturally because of the close working relationships between members
of staff, and to encourage this for the entire institution. The establishment of CoPs (and active
nurturing of these, where they already exist) will be underpinned by robust knowledge
management strategies to ensure that knowledge and outstanding practices are shared and
transferred, and finally, effectively used to enhance organisational competence. Alongside these
internal benchmarking efforts external benchmarking, locally, nationally and internationally will
be conducted for all the processes and practices which have been identified by the audit and by
internal self assessment exercises as needing improvement. This is precisely where the
process classification activity pays dividends: By knowing what our processes are, we are able
to identify and select those in need of attention for purposes of benchmarking or targeted
improvements. Best practices benchmarking goes and should go beyond just comparing notes
to forming collaborative agreements where institutions can be of mutual benefit to each other in
many other ways post the benchmarking exercise. The mechanisms for achieving this have
already been put in place as TUT’s 2009-2013 strategic plan makes provision for benchmarking
at both national and international level.
Finally, to maintain a robust and effective quality management system requires close monitoring
to ensure even implementation across the institution. At best our efforts in this regard have been
sporadic, and could be said to be operating by default rather than by design, as when …
indicates that there has been an infringement of rules relating to one … or the other. However,
as we move from a focus on the merger to focus on our core business, we hope to rectify the
situation to a point where we could regard ourselves as fully compliant, whilst at the same we
take tentative and gradual steps towards in the long journey towards excellence, for which
proposed improvements will have laid a solid foundation. Some groundwork has been covered
in this regard. The training and capacity building workshops on the QMS with a sample of
academic and support departments, selected from both urban and distant campuses is
designed to facilitate understanding of the QMS so as to ensure even and effective
implementation across the institution. It is only in the context of a full understanding and
appreciation of the role of a quality management system on the part of all role-players that we
can sensibly talk about monitoring.
7.2 Improvement Action Plan
The period since the conduct of the institutional self evaluation exercise has seen a gradual
normalisation of institutional activities post-merger. The match and place exercise has
progressed significantly, which has had the effect of reducing uncertainties regarding
appointments. This in turn has gone a long way toward focusing staff energies on our core
business rather than on the merger, a regrettable and unavoidable situation which detracted
much from our focus. To this end, the Directorate of Quality Promotion has focused on
consolidating its plans and activities relating to the institutional Quality Management system,
which gained momentum during the time of the self-evaluation exercise. For DQP the first step
has been to take stock of policies, procedures guidelines and forms in all environments and to
capture these electronically for easy access by all users. This project started in 2007 and forms
the basis of an Institutional electronic Quality Management system (e-QMS) on which faculties,
and departments can model their own. At the writing of this report…/ Preparations are currently
under way to pilot the project by conducting capacity building workshops on the e-QMS with a
sample of academic and support departments, selected from both urban and distant campuses.
Through this project, we intend to facilitate understanding of the role of the QMS, and thus
cascade it to departmental level.
The following table identifies and describes actions which will be taken to address the
recommendation. The actions build on actions already operational as referred to in the
overview. The table also points to the structure responsible for carrying out the actions, the
time-line, resources needed, performance indicators and person/structure accountable.

7.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| senior management to take a more active role in providing intellectual and strategic direction (medium term) | Agree on Quality management principles and fundamentals Formulate a quality policy and objectives Drive and support process identification/classification exercise Jointly participate in devising quality assurance mechanisms for EMC (LbE/MaB) | Management and staff Management and DQP EMC & DQP EMC & DQP | October – November 2008 October – November 2008 January – March 2009 | Time Time All (Snr. Management & Staff) | Quality Management principles Quality Policy and Objectives Process classification framework for TUT | EMC/VC EMC/VC EMC Members |
| formalisation, implementation and monitoring of a quality management system (Short term) TUT to conceptualise its quality management system in such a way that it moves beyond compliance (long term) | Conduct a process identification/classification exercise Complete the process definition exercise, Complete process interface exercise Develop list of supporting documents Compile quality manual Conduct training for users Oversee implement, monitor and evaluate implementation of QMS Review QMS on a regular basis and capture changes Plan for the development of policies etc to close gaps Incorporate into existing (e)QMS Update electronic QMS Review existing self evaluation instruments to ensure efficacy (list them?) Establish best practices benchmarking as institutional tool for moving from compliance to excellence Develop Benchmarking framework Identify processes and practices for improvement Identify benchmarking partners Establish benchmarking team Undertake benchmarking activities Plan for collaboration | Management and staff Management and staff Management and staff Management and staff DQP DQP DQP DQP DQP DQP DQP DQP SMS and DQP SMS and DQP All All All All All | January – March 2009 January – March 2009 March - April 2009 March - April 2009 April - June 2009 Oct 2008 – Dec 2009 Ongoing On-going June 2009 June 2009 On-going June 2009 Dec 2009 Jun 2009 Jun 2009 Jun 2009 Jun 2009 Dec 2009 Mar 2010 | Time & Human resources Time & Human resources Time & Human resources Time & Human resources Time & Human resources Time & Human resources Time & Human resources Time & Human Resources Time & Human Resources Time & Human Resources Time & Human Resources Time & Human Resources Time & Human Resources Time & Human Resources Time & Human Resources Time & Human Resources Time & Human Resources Time & Human Resources Time & Human Resources | Process classification framework for TUT TUT Processes defined & flow-charts Process interface List of supporting documents Documented quality manual Training schedule & Attendance lists Improved QMS Progress reports Action plans & Revised policies Improved e-QMS Improved e-QMS Progress reports & revised instruments Benchmarking document / protocol Benchmarking framework Flow charts List of Partners Benchmarking teams Progress reports Action plans | EMC members EMC members EMC members EMC members DVC: IPO DVC: IPO DVC: IPO DVC: IPO DVC: IPO DVC: IPO DVC: IPO DVC: IPO DVC: IPO DVC: IPO EMC members EMC members EMC members EMC members EMC members |

7.3.  Sustainability and Transfer of Learning

  - The directorate of Quality Promotion believes that a sound education training and development programme should underpin any quality improvement initiative. First, the purpose is to empower staff to effect the changes brought about by the improvements, and to make sure that everyone is suitably trained to do their job. This is the only way to we can sustain the quality improvement gains which have accrued as a result of the implementation of the QMS. To this end the DQP will train its staff (other than the ones directly involved) on the use of the e-QMS, so as to enable them to answer queries and to support institution-wide capacity building initiatives on the QMS. A second function which education training and development performs is that of ensuring that the institutional intellectual capacity remains within the institution, in the event of any of the staff members resigning. When members of staff in a unit are able to function in an understudy capacity for each other, continuity is ensured. To this end, the DQP, through the education and development of its staff, will ensure that no member of staff is irreplaceable. ... entire institution. n

# Recommendation 8: Benchmarking, Surveys and Impact Studies

The HEQC recommends that Tshwane University of Technology give attention to the development of appropriate institutional systems for benchmarking, student and employer surveys, and impact studies which will include implementation plans with time frames and the allocation of responsibilities.

8.1. Overview

    - TUT is committed to the continuous monitoring, evaluation and improvement of its core business of teaching and learning, research and community engagement. 
TUT will develop an institutional and systematic approach to institutional surveys, benchmarking and impact studies. This will enable the institution to monitor and evaluate performance and implement proactive continuous quality improvement. 
The DQP has embarked on a process of reviewing and refining already existing instruments, designing and developing new ones as well as revamping its approach to stakeholder surveys. The refinement of survey protocols and instruments began with university ethics committee to validate the credibility of the instruments as well as to protect the respondents from potential negative repercussions.   
The following surveys will assist in identifying critical areas in need of improvement and contribute towards continuous improvement: student satisfaction survey, programme satisfaction survey, subject experience survey, graduate destination survey and employer satisfaction survey. 
Impact studies are important instruments for measuring and evaluating the effects of institutional initiatives to enhance the quality of its core functions.  As a point of departure, DQP will engage in conceptualisation of impact studies in TUT. Impact Studies will be undertaken on an ongoing and systematic basis. This aspect of the recommendation is considered to be of high priority and will be addressed in the medium term.

The conceptualization and practicality of benchmarking are important aspects to consider since benchmarking strategies are used to improve administrative processes as well as instructional models at universities. Such strategies include examining processes and models at other institutions and adapting own techniques and approaches accordingly. Thus, benchmarking is an ongoing, systematic process of measuring and comparing the work processes of one organization to those of another, by bringing an external focus to internal activities, functions and operations. The ultimate goal of benchmarking is to provide an external standard for measuring the quality and cost of internal activities and to help identify opportunities for improvement (Alstete, 1997). Benchmarking attempts to answer the questions: 

•	How well are we doing compared to others?
•	How good do we want to be?
•	Who is doing it the best?
•	How do they do it?
•	How can we adapt what they do to our institution?
•	How can we be better than the best? (Kempner, 1993).
Actions already operational within the institution in terms of benchmarking include annual analysis in the areas of student success rates, student enrolment trends, Institutional trends and indicator analysis, student and staff HEMIS report analysis and Employment Equity reports . However, at TUT, there are no existing policies in terms of benchmarking practices, hence a starting point in terms of recommendation 8.1 would be to develop a position paper and then to develop institutional policies and procedures in terms of benchmarking practices. 

Section 8.2 below indicates a detailed implementation plan on how aspects of this recommendation will be addressed.  g

8.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Benchmarking | Develop a position paper on institutional benchmarking practices Develop institutional benchmarking policy and procedure Implementation | Strategic Management and Support | Sep 2008 – Feb 2009 Feb – June 2009 Ongoing | None None None | Position paper Institutional benchmarking policy | DVC: Institutional Planning and Operations |
| Surveys | Develop a systematic approach and framework for stakeholder surveys in TUT Develop Survey Protocol and Questionnaires Purchase appropriate data analysis software Administer surveys : Student Satisfaction survey Programme Satisfaction survey Subject Experience Graduate Destination Survey Employer Satisfaction Reporting on surveys findings | DQP DQP DQP DQP DQP DQP DQP DQP | Sep – Nov 08 July – Nov 08 Aug – Nov 08 Biennial Biannual Ad Hoc Annual Annual Continuous | None None R300 000 Quality Advisors Field workers EvaSys data analysis system Quality Advisors Field workers EvaSys system Quality Advisors EvaSys system Quality Advisors Field workers Budget for (mailing questionnaires) EvaSys system Quality Advisors Research assistants EvaSys system | An institutional framework for surveys Survey Protocol and approved survey questionnaires EvaSys Data analysis software installed Student Satisfaction Survey Report Programme Satisfaction Survey Report Subject Experience Report Graduate Destination Survey Report Employer Satisfaction Report Surveys reports | DVC: Institutional Planning and Operations DVC: IPO |
| Impact studies | Conceptualisation of Impact Studies Development of appropriate strategies for impact studies Implementation Reporting Monitoring and Evaluation | DQP DQP DQP DQP DQP | Oct – Nov 2008 Oct 2008 – Feb 2009 As per project plan As per project plan As per project plan | None None Human and financial resources None None | Conceptual framework Strategy report Impact study project plan Impact study report Monitoring and Evaluation reports | DVC: Institutional Planning and Operations |

8.3.  Sustainability and Transfer of Learning

  - The Directorate of Quality Promotion (DQP) will develop an institutional framework for stakeholder surveys which will outline TUT’s approach to stakeholder surveys. The framework will outline the purpose, objectives, scope and implementation cycle of stakeholder surveys that TUT conducts. In addition, a process and procedure for conducting surveys will also be mapped so as to ensure consistency in conducting surveys. 
To ensure long term sustainability and adequate buy-in from stakeholders, DQP will strengthen and improve dissemination of survey results to relevant stakeholders. This will largely entail closing the feedback loop, on-time dissemination of results, providing feedback to the stakeholders on what and how the University will address the areas needing improvement. Stakeholder feedback is deemed necessary and important to give credibility to the entire surveys process. 
In order to provide timely feedback and address the time lag after survey administration, DQP purchased data analysis software which is designed to provide immediate feedback. It is envisaged that the results or findings from different surveys will inform institutional quality improvement initiatives at institutional planning level. 
Furthermore, a well developed impact study conceptual framework would enable for a consistent and systematic approach to impact studies in TUT. 
The position paper on benchmarking will also guide and underpin all TUT’s approaches to benchmarking activities in the University. Thus the development of benchmarking policy and procedures will further ensure consistency and a systematic approach in TUT.

# Recommendation 9: Academic Model

The HEQC recommends that Tshwane University of Technology develop and implement a comprehensive academic plan based on its new identity as a university of technology. This would also provide a framework for making decisions about the rationalisation of its existing programme and qualifications mix.

9.1. Overview

    - The vision, mission, goals and objectives of the university were reviewed to be aligned with a university of technology concept.    This was informed through an Institutional debate which strengthened the deliberations on national level.  The TUT goals and objectives gave direction to faculties and the higher education development and support unit to develop business plans for the next five years.
The challenge for TUT, as an university of technology, is to be a leader in and through technology by practising and transferring technology within its activities of teaching, learning, research, innovation and community engagement. 
UoTs are characterised by the following:
 
•	Relevance of technology focused programmes; 
•	Service to industry and the community; 
•	Responsiveness to, and fulfillment of the needs of industry, community and society; 
•	Appointment of experts acknowledged by industry  (not necessarily by academics); 
•	Strong attention to niche areas; 
•	Emphasis on scholarship, innovation and Research and Innovation (R & I)  to develop new technologies; processes and products
•	Transfer of technology; 
•	Preparation of a new generation of knowledge workers. (E.g. work ethics, ability to work in multi¬cultural teams, students-for-life, etc.) 
•	Application of know-how, knowledge and skills towards improved products, processes and technologies.
 
TUT is participating at a national level in the development of performance indicators for Universities of Technology (UoT’s) through membership of the South African Technology Network (SATN) Typology Committee.  This will inform the format and contents of TUT’s academic plan. 
TUT see the Academic Plan as the framework that will guide all Academic activities for the next five years.  This framework is prioritized from the Strategic Goals and Objectives, supported by TUT’s Strategies for Teaching and Learning (T & L), R & I and Community Engagement (CE).

The purpose of the Academic Plan is also to inform all Support services that need to align the services to the core business of the institution.  This will ensure that academic quality is improved.

Process
Following the workshop on 13 August 2008 by the Directorate Quality Promotion a task team was established to draft an improvement plan for recommendation 9. (Members of the task team: V Agyei, A Erasmus, D Human, T Maja, P Nkhoma, I Stevens, S Swanepoel,  H van der Merwe, E van Staden). The task team met on 25 August to draft an improvement plan. The plan was circulated for comments and finalised.
The process which informed the development of various levels of plans was approved in January 2008.
This assisted the institution to understand the rationale, process and alignment of the plans to the Strategic Plan of TUT.  It is the responsibility of the Planning Unit of TUT (Strategic Management Support Directorate - SMS) to facilitate all planning processes in the institution.
Therefore, the AQIT, is thus seen as an ad hoc group that deliberated the conceptualisation of the Academic Plan as now portrayed in 9.2.

 Rationale for our approach to address the recommendation
A holistic approach to teaching, learning and technology was used to determine the action plans necessary to formulate a comprehensive academic plan.  The formulation of a comprehensive academic plan will be based on the action plans as indicated in this recommendation in order not only to prepare the quality improvement plan  but to ensure that TUT reach its goals and objectives. 
The context of this quality improvement plan, which stipulates the framework for the Academic Plan is informed by various building blocks.  The context of the proposed framework for such an Academic Plan (see 9.2) was based on various drivers that were already developed and approved.
The main drivers for the Academic Plan are the Teaching, Learning and Technology Strategy, Research and Innovation Strategy as well as the Community Engagement Strategy.
The implementation plans for these strategies were drafted to guide Faculties business plans.
The Programme Qualification Mix (PQM) and Student Enrolment Plan (SEP) of TUT are informed by approved ministerial statements and targets.  The institutional context is informed by the relocation plan for programmes. This emanated to infrastructure and efficiency funding proposals that will support specific needs, relating to new, upgrading of extensions of buildings as well as teaching and research equipment.
The Student Enrolment Plan informed the Academic Staff profile, of each department through which a Human Resource Plan is made possible.  Another building block for the Human Resources (HR) plan is Employment Equity (EE) targets and promotion / career path possibilities.
The PQM for the next five years will be influenced by the new Gazetted Higher Education Qualification Framework (HEQF).  TUT has laid a foundation through which a programme viability exercise, Labour market analysis and a curriculum design process will inform the development of the new PQM.
The UoT concept where ‘Technology’ is seen as the qualifier, will further be portrayed in the Academic Plan through the Integrated Technology Plan and Information and Communication Technology (ICT) in support of the Teaching, Learning and Research environments.
All these building blocks have provided a foundation for the Academic Plan.

9.2.  Improvement Action Plan

| Aspect of Recommendation |  |  |  | Actions |  |  |  |  | Responsibility |  |  |  |  | Time Line |  |  |  | Resources Needed |  |  |  |  | Performance Indicators |  |  |  | Accountable Person/Structure |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Develop a comprehensive Academic Plan |  | Planning process: 1. Approval of the rationale, process and phases of planning |  |  |  | Dir. SMS |  |  |  |  | 2008 |  |  |  |  | None |  |  |  |  | Positioning paper on planning |  |  |  |  |  |  | DVC: IPO |  |  |
|  |  | Conceptualise the framework for an Academic plan: 2. Teaching , Learning & Technology - Develop a TLT Strategy - Implementation of the strategy (actions in Addendum B of TLT Strategy |  |  |  | Deans Snr. Director: HEDS |  |  |  |  | 2007 2010 |  |  |  |  | None Population of structure |  |  |  |  | Strategy approved by Senate Target dates in Addendum B met |  |  |  |  |  |  | DVC: TLT |  |  |
|  |  | 3. Conduct an Environmental Scan |  |  |  | Strategic Planner |  |  |  |  | 2007 |  |  |  |  | R10 000 |  |  |  |  | Environmental Scan approved by EMC |  |  |  |  |  |  | Director: SMS |  |  |
|  | 4. Identify Key Performance areas - Determine academic priorities linked to Performance Indicators |  |  |  | Director: SMS |  |  | 2008 |  |  |  | None R10,000 |  |  |  |  |  |  | Strategic Plan |  |  |  |  |  | Director: SMS |  |  |  |  |  |
|  | 5. Drat a Relocation Plan for Urban sites and Distant sites- Implement enrolment - Determine infrastructure needs |  |  |  | Director: Merger Office Deans, Campus Directors |  |  | 2012 In process |  |  |  | Relocation Capital Budget R302 million R1 Billion |  |  |  |  |  |  | Staff & programmes relocated |  |  |  |  |  | DVC: TLT DVC: IPO DVC: RIP |  |  |  |  |  |
|  |  | 6. Develop a Student Recruitment Strategy and Implement a Marketing Plan |  |  |  | Deans Corporate Affairs & Marketing Academic Administration |  |  |  |  | 2007 annually |  |  |  |  | Provided in budget |  |  |  |  | Ministerial approved targets met |  |  |  |  |  |  | DVC: TLT DVC: FBD |  |  |
|  | 7. Implement the approved Student Enrolment Plan |  |  |  | Deans Director: SMS |  |  | 2010 |  |  |  | None |  |  |  |  |  |  | Registration targets met |  |  |  |  |  | DVC: TLT DVC: IPO DVC:RIP |  |  |  |  |  |
|  | 8. Draft a HR Plan and Develop a Staff develop- ment strategy - Set EE Targets and implement plans - Revision of policy on academic and HEDS appointments and promotions - Develop an ideal Academic Profile and - Implement the Structure |  |  |  | Deans Dir. HRD Deans Snr. Director: HEDS Deans Snr. Director: HEDS Deans, Director: SMS Deans, Director: SMS |  |  | 2008 2008 2008 2007 anually |  |  |  | None None As per budget |  |  |  |  |  |  | Comprehensive strategy on staff development EE Targets per Faculty Policy approved Academic profile approved by Senate As per Business Plan |  |  |  |  |  | DVC: TLT DVC: IPO DVC: TLT |  |  |  |  |  |
|  |  | 9. Develop a Student Admission and Selection Plan for 2009 NSC |  |  |  | Refer to recommendation 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 10. Develop Business Plans of Faculties and Higher Education Development and Support |  |  |  | Deans Director: HEDS |  |  |  |  | 31/07/08 30/11/08 |  |  |  | per plan |  |  |  |  |  | BP finalized by 31 July 2008 |  |  |  |  |  |  | DVC: TLT |  |  |
|  | 11. Development of new PQM according to HEQF – action plan - Programme Viability - Labour market analysis - Curriculum design |  |  |  | HEQF task team Director: SMS |  |  | 2015 2008 2009 2015 |  |  |  | Structures populated See CDS plan R140 000 |  |  |  |  |  |  | PQM aligned with HEQF Financial Viability of each programme |  |  |  |  |  | DVC: TLT |  |  |  |  |  |
|  |  | 12. Develop a Co-operative Education Strategy |  |  |  | (approved 2007) Refer to recommendation 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 13. Establish Academic risk management process and procedures - Establishing risk working groups- Manage risk register |  |  |  | TLT Risk WG Chair |  |  |  |  | 2008 2008 annually |  |  |  | Training of working groups |  |  |  |  |  | Updated risk register |  |  |  |  |  |  | DVC: TLT |  |  |
|  | 14. Implement E-learning Plan |  |  |  | Director: ICT Director: TLwT Snr Director: HEDS |  |  | 2008/2009 |  |  |  | Funds secured in Nuffic eLearning Leadership project R1,1 million |  |  |  |  |  |  | eLearning plan approved |  |  |  |  |  | DVC: TLT |  |  |  |  |  |
|  | 15. Draft Integrated Technology Plan - Minimum standards in teaching venues - ICT infrastructure support - Smart classrooms - E-Assessment labs |  |  |  | Snr Director: HEDS Director: TLwT Director: ICT |  |  | Plan: Dec 2008-09-01 Roll out: 2009/10 Training: continuous |  |  |  | DOE – IOP Nuffic eLL TUT R25 million R41,5 million R21 million |  |  |  |  |  |  | Plan approved Minimum standards approved by Academic Committee Successful roll out and technologyinstalled One SMART classroom on every learning site Academic staff trained |  |  |  |  |  | DVC: TLT DVC: IPO |  |  |  |  |  |
|  |  |  | 16. Draft Teaching and Research Development grant proposals |  |  |  | Deans Snr. Director: HEDS Director: RIP |  |  |  |  |  | annually |  |  |  | DOE funding |  |  |  |  | Implementation of plan |  |  |  | DVC: TLT |  |  |  |  |
|  |  |  | 17. Develop Equipment and Capital Replacement Plan |  |  |  | Director: SMS Director: TL&T |  |  |  |  |  | 2009 |  |  |  | R102 million |  |  |  |  | Strategic Plan |  |  |  | DVC: TLT DVC:FBD DVC: IPO |  |  |  |  |
|  |  |  | 18. Improve success rate |  |  |  | Refer to recommendation 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 19. Monitoring and revision of Teaching and Learning policies |  |  |  | Refer to recommendation 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 20. Community Engagement Strategic Framework |  |  |  | Refer to recommendation 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 21. Strategy for Research & Innovation |  |  |  | Refer to recommendation 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation Process of the Academic Plan |  |  | 1. Draft of a comprehensive academic plan |  |  |  | Director: SMS Snr. Director: HEDS Deans |  |  | 2009 |  |  |  |  |  |  |  |  |  | None |  |  |  | Draft |  |  |  |  | DVC: TLT |  |
|  |  |  | 2. Submit to AC, EMC, Senate, Council for approval |  |  |  | DVC: TLT |  |  | 2009 |  |  |  |  |  |  |  |  |  | None |  |  |  | Approved Academic Plan |  |  |  |  | DVC: TLT |  |

9.3.  Sustainability and Transfer of Learning

  - Since the HEQC audit the university designed a new academic structure. The profile of academic departments and faculties as well as the support staff needed were determined according to guidelines and criteria approved at Senate and Council.
 The population of the new structure is currently in process through the match and place exercise and   vacancies are advertised and filled gradually. The match and place of teaching staff of faculties have been finalized. 
The relocation of staff and programmes started on the Urban sites in 2008 and relocation plans are updated regularly to accommodate challenges. In some faculties, a number of departments have already been relocated to plans. The Mpumalanga sites will start with relocation in 2009.
The TLT strategy and other strategies and plans referred to under this recommendation must be disseminated to the academic community and cascaded to the relevant persons. This will be done by means of including the TLT strategy and plans in the orientation programme for new academic staff and the induction programme for deans and HOD’s, and awareness workshops facilitated by Curriculum Development and Support (CDS).

# Recommendation 10: Management of Experiential Learning

The HEQC recommends that Tshwane University of Technology ensure that every student in a programme with an experiential learning component is placed appropriately, that there is a functioning system to record, monitor and assess the content and progress of the student’s learning experience in the workplace, and that the system is implemented consistently and monitored across all campuses.

10.1. Overview

    - Conceptually, the term experiential learning, referred to in the above recommendation, is described in the Tshwane University of Technology (TUT) within the context of cooperative education. The term cooperative education is used in the university as an umbrella term to describe the collaboration between the students, employers and the university.  The policy (compare Appendix A ) on cooperative education clarifies terminology on and related to cooperative education and include, experiential learning, work integrated learning (WIL), service learning and learnerships (workplace component only). 

As the university was established on 1 January 2004, from a merger between three technikons, it must be emphasized that the management of experiential learning was also implicated, since it forms part of the curriculum of most learning programmes. The former three technikons managed cooperative education/experiential learning differently  and the need to standardize became apparent as the merger was progressing. The merger and the  HEQF  resulted in a total re-conceptualisation of cooperative education and experiential learning, with the consequence of a policy and strategy  approved by senate.

Interpretation and analysis of recommendation

It is clear that the HEQC is concerned about the preparation and placement of students at the workplace. The committee  identified placements for experiential learning (EL) taking place in an inconsistent manner.  Firstly, ...  that all students should be placed and secondly that students cannot be left to find placements themselves . The university should ensure that this practice cannot continue anymore and that students should complete their qualifications. 

In addition, the committee  identified the lack of proper preparation of students for EL and the workplace. This need was not only expressed by this committee but is supported by employers to ensure that students are well prepared for EL and the workplace before entering the premises of the workplace.  This will contribute to higher success rates in EL , and consequently improve graduation rates.

The report states that a system must be in place to ensure student’s experiential learning activities and their  progress in the experiential learning component , are properly monitored, assessed and recorded at the workplace and that such a system be implemented consistently across all campuses.

Finally, clarification is needed whether cooperative education  is to be included in all programmes. Conceptually , it implies that all components of cooperative education needs to considered for such inclusion. 

Breakdown of recommendations

Following discussions from workshops, on recommendation 10, the following key areas were identified for improvement; 

1.	Every student in a programme with an experiential learning component is placed appropriately,
2.	There is a functioning system to record, monitor and assess the content and progress of the students learning experience in the workplace 
3.	The system is implemented consistently and monitored across all campuses

In addition, the following problem areas were identified: 

4.	Differences in the management of EL/ WIL  exist across departments, including placements .
5.	Quality mechanisms for evaluating and monitoring of EL/WIL  are not standardized or equally implemented across programmes at all campuses. 
6.	Work placements are not managed by the institution: Placements need to be found by the students themselves 
7.	No indication in TUT how students are prepared for EL/WIL to equip students with technical and non technical skills: Interventions to ensure preparedness for the workplace. 
8.	The process for recording, monitoring and assessing the EL/WIL component is uneven across campuses. 
9.	Students cannot complete their qualification because they could not find placement. 
10.	Clarify the extent to which cooperative education should be incorporated into the curricula – considering the resource implication!.  

NOTE: The successful implementation of this plan is dependant on the provision of adequate resources. The current subject fee allocation for EL/WIL is insufficient, and needs to be reviewed  annually.

Process

Following a workshop involving the Directorate Quality Promotion (DQP) and  Faculty Cooperative Education Coordinators on13 August 2008) a task team was established to take responsibility to plan the process and draft an improvement plan for recommendation 10. 

A draft improvement plan was tabled on 19 August 2008 by the convenor  tosub team members The inputs from the faculty coordinators were incorporated and a final report was submitted to ??? on 22 August 2008.

Rationale for our approach (improvement actions) to addressing the recommendation(s)

It is intended not only to prepare a Quality Improvement Plan (QIP) to comply to the HEQC requirements as recommended in the audit report (2007), but to implement a cooperative education strategy to ensure TUT provides excellence in career focused education through the philosophy of cooperative education.

The Directorate: Cooperative Education undertakes to ensure collaboration and partnerships with all stakeholders to ensure “cutting edge” education and training through the practice of cooperative education, which include experiential learning/work integrated learning to ensure in human resource a workforce with the necessary skills and competencies required in the world of work.  
	

The evidence/performance indicators: quantitative and qualitative data, policy, structure, appointment etc.

Compare Appendix B;

Policy and strategy on cooperative education
Action plan: Performance indicators
TUT report on cooperative education: Qualitative and quantitative data
Cooperative education structure
Business plan for cooperative education (2008-2013)
 
10.1.1	Action Plan

•	What will be done to sustain the quality improvement/intervention

The quality improvement plan was discussed for inputs from faculties at the Cooperative Education Central Committee (CECC) and a plan of action was proposed for corrective action and improvement. 

•	What will be done to ensure transfer of learning to ensure continuity

The Academic Quality Improvement Team (AQIT) was established and regular meetings were convened to monitor progress and the development of an improvement plan.

Should the AQIT be implemented as a standing Committee, it is strongly advised that faculties of Engineering and Built, as well as Sciences be co-opted, due to their major involvement in EL/WIL

The quality Improvement/action plan was listed as part of the agenda of the CECC meeting and the  HEDS EXCO meeting to record progress.

Faculty Coordinators (Cooperative Education) reported on action taken in faculties via the Faculty Cooperative Education Committee (FCEC) in faculties and CECC institutionally, for inclusion in the improvement plan.
 h

10.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Differences in the management of EL/WIL in - departments/faculties and in which includesplacements | 1.1. Appoint of Faculty Coordinators in faculties and CELs in each learning programmes. 1.2 Appoint of admin support staff in faculties 1.3 Establish Coop Ed office in faculties: students 1.4 Establish FCEC in faculties 1.5Implement Role clarification template in faculties | Appoint Coop Ed staff in faculties ( FCs & CELs) Appointment of admin assistant for faculties for Coop Ed Office for Coop Ed in faculty for FC and admin assistant Committee for Coop Ed initiated and regular meetings Implement role clarification template for each programme | 2008-2009 2009-10 2009-10 2009-10 2009-10 | Staff according to match& Place requirements Admin staff Office space and equipment None Template on role clarification | One FC / faculty CEL/programme One admin assistant per faculty Office and infrastructure for FCs and Admin Assistant FCEC Signed template by responsible role players | Deans and DVC:TLT Director DVC:TLT Deans Senior Director: HEDS Director Coop Ed FCs Director Coop Ed/ Deans/HOD/FCs Director & Faculty Coordinators, HoDs Director Coop Ed, Deans, FCs/HoD |

10.3.  Sustainability and Transfer of Learning

  - The TLT strategy and other strategies and plans referred to under this recommendation must be disseminated to the academic community and cascaded to the relevant persons. This will be done by means of including the TLT strategy and plans in the orientation programme for new academic staff and the induction programme for deans and HOD’s, and awareness workshops facilitated by Curriculum Development and Support (CDS).
The development of an academic plan constitutes both a redefinition and reaffirmation of the centrality of academic activity to the core business of the university.  This will assist the provision of support for academic activities.  The academic plan lends itself readily to supporting the link between planning and resource allocation that will be focusing both on quality management.  
The planning unit coordinates academic planning and affords the opportunity to all academics and all other closely associated with the academic enterprise to engage with planning in the immediate context of their activities and therefore in a meaningful manner.  The Academic Plan also enforces academic units to engage in academic planning through identification and articulation of the objectives of their programmes, and ongoing assessment/evaluation of whether these objectives are being met.  The academic plan has the capacity to stimulate debate on curriculum/curricular (design and development) issues and intractable issues about what a university education means and should entail.  Finally, the academic plan lays a firm foundation for the institutionalization of planning in as far as it makes planning part and parcel of our daily activities.
Prior planning facilitates or accelerates TUT’s capacity to respond to opportunities that are consistent with our stated mission.  Such effective planning also aids both institutionalization and internalization of practice, both of which contribute to sustainability.  Factors which TUT believes will facilitate sustainability are those relating to the relative advantage of improved practice, in this case of academic planning, over previous practice evidenced by the absence of an academic plan.
The development of an academic plan is an exercise in continuous/continuing learning, which requires efforts to nature and to transfer knowledge and capabilities.
TUT functions according to a planning framework designed to produce a systematic process for planning and measuring the effectiveness of University’s activities. The Five strategic goals, within nominated Key Performance Areas (KPA), are broadened within 23 institutional objectives with specific Key Performance Indicators (KPI). Five-year business plans for all academic and administrative units are developed, which are being updated annually through a review and progress reporting process and system. One-year implementation plans (year n+1) are developed by individual departments/units that indicate the institutional priority for the applicable year, linked to financial and other resources needed.
Assessment of Institutional performance is done from a qualitative perspective (by applying HEQC self-evaluation audit criteria) and quantitative perspective which is portrayed in a trends and indicators report. This is informed by the performance of individual units through a performance assessment of individual managers.
The implementation is monitored through a bi-annual reporting process. This process ensures the implementation of all planning activities and processes, organize planning activities into a logical order, and synergy between environments, monitoring tools, which will confirm implementation, and is used as a management tool for all managers.
Aligning the institution’s planning around the strategic framework is creating a planning synergy between the academic units and the support service units. This ensures that planning is a continuous process as the budget is linked to strategies and required activities.
What

# Recommendation 11: Improving Teaching and Learning

The HEQC recommends that Tshwane University of Technology make the improvement of the quality of teaching and learning an institutional priority and that strategies and resources are put in place for this purpose. In doing this, the institution might want to consider the development of appropriate mechanisms of support to professionalise teaching as a way of responding to the pedagogic challenges posed by TUT students

11.1. Overview

    - An Academic Quality Improvement Task Team sub-committee analysed Recommendation 11 and interpreted it as indicated below.  We identified the following aspects of the recommendation that required specific actions from our side:
•	TUT needs to clarify the extent to which cooperative education should be included into all career focused programmes, with specific attention paid to the resource implications of such a decision.  Recommendation 10 provides more information about the University’s response to this recommendation.
•	The University is urged to improve its bandwidth in order to ensure access to the multimode teaching and learning initiatives on all learning sites.  Action plans are put in place to address this issue.
•	The Panel requested to determine the extent to which the use of technology in teaching and learning is to be an institutional strategy and is called upon to allocate resources accordingly.  The University is committed to use technology to support both its teaching and learning activities and has responded in making resources available to ensure equal access to educational technology on all campuses.    
•	TUT agrees with the Panel and continues to develop and implement the MIS system which provides access to critical information for decision-making.
•	 In response to the Panel’s concern about the focus of the Academic Committee, TUT drew up new Terms of References for both the Academic Committee and the TLT Exco (consisting of the DVC:  TLT, Deans and Snr Director:  HEDS).  In these documents  the improvement of the quality of teaching and learning are prioritised.   The action plans below show the strategies and resources that are put in place to improve the quality of teaching and learning.  With these actions, TUT focus on mechanisms of support to professionalise teaching in response to the pedagogic challenges posed by TUT students.

11.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Cooperative education | All programmes in TUT must include a cooperative education component . | Refer to Recommendation 10. |  |  |  |  |
| Multi-mode teaching | Implementation of minimum educational technology standards across all learning sites | TLwT, IT Services and Logistics | 2010 | R 200 000 per classroom | Strategy for educational Technology: Minimum Standards Policy on procurement, maintenance & replacement of technology | Director: TLwT |
|  | Establishment of eLearning laboratories on all learning sites for all instructional modes | TLwT, IT Services and Operations | 2009 - 2010 | R 1.5 million per laboratory x 9 learning sites | Policy for eLearning Laboratory eAssessment Policy eLearning Plan | Director: TLwT |
|  | Strategy to empower staff to use and manage and integrate educational technology ...in T&Lto achieve optimal results. | TLwT | 2010 | R 1.8 million |  | Director: TLwT |
|  | Double bandwidth (Consolidate fragmented campuses, implement bandwidth management, increase current bandwidth with 30 % per year over a period of three years.) | IT Services | 2009 | R 12 million per year | Bandwidth policy | DVC: Operations |
|  | Upgrade current limited Campus Edition learning management system to an unlimited user enterprise version | TLwT, IT Services | 2008 | R 304 000 | Learning Management System (LMS) LMS Audit eLearning Plan | Director: TLwT |
|  | All issues concerning multimode education will be addressed in the elearning Plan | TLwT | 2009 | None | eLearning Plan | Director: TLwT |
|  | Nuffic eLearning Leadership Development | TLwT | 2011 | R 13 million (Funded by Nuffic, Netherlands) | Annual Nuffic eLearning Leadership Report Project plan | Director: TLwT |
| Integrated Technology plan | Develop an Integrated Information and Communication Technology plan | IT Services, TLT, SMS, Faculties, Support Services | 2009 - 2013 | See IICT plan | Integrated Information and Communication Technology plan | Director: IT Services |
| MIS | Continue development and implementation of the MIS | SDS, IT | Ongoing | See SMS business plan | SMS business plans | Director: SMS |
| Prioritising teaching and learning | Policies for teaching and learning Review the TUT policies that relate to teaching and learning (e.g. academic appointment and promotions, study guides, evaluation of lecturing staff & cooperative education) Create policy awareness among staff | Academic Committee, Admin Support Committee, HEDS, DQP, Policy owners CDS, DQP, Corporate Relations | Ongoing in 3 year cycles Throughout | Populated structures See DQP Business Plan | Revised policies Workshops, seminars, internal media articles DQP Business Plan | DVC: TLT Director: DQP |
|  | Strategic targets Set realistic targets for throughput rates. Ensure formal mechanisms and resources are in place to address throughput issues | DVC: TLT, SMS Academic Committee, Throughput Committee | Annually Ongoing | See Throughput Committee’s Business Plan | Throughput targets Throughput committee business plans and annual reports | DVC: TLT Chair: Throughput Committee |
|  | Prioritise the quality of the core function of teaching and learning Finalise the merger-related activities, including match & place and relocation. Constitute a task team to look into measures to prioritise the professionalisation of teaching and learning at TUT Develop and implement a comprehensive staff development policy and action plan Develop and implement an holistic orientation programme for - new staff, and - newly appointed HODs Introduce an award for Teaching Excellence based on pre-determined criteria Introduce teaching sabbaticals for the purpose of recurriculation, the development of OBE-based curricula, or technology-assisted teaching/learning materials Recurriculate the HDHET into a PGDHET to enable academic staff to improve their teaching qualifications through TUT | Human Resources, Merger office, Relocation committee HEDS, Faculty representatives, HR, Unions HEDS, CCPD, RIP, HR, Unions, Above-mentioned task team CDS, HR, Unions, Above-mentioned task team HEDS, Faculties, Above-mentioned task team HR, CDS, TLT, Faculties CDS, Faculty of Humanities | 2010(?) Nov 2008 Nov 2008 From 2008 annually 2009 2009 2010 | ?? None See Staff Development Action Plan As per Orientation strategy R 200 000 R 500 000 per year R 460 000 | As per activity (e.g. All staff is matched and placed, all Faculties are relocated) Detailed action plan Revised policy on staff development Revised policy on staff orientation Orientation strategy Revised policy on Teaching Excellence awards Policy on teaching sabbaticals Senior academic appointed as coordinator for the PGDHET curriculum | Director: Human Resources Director: Merger office Senior Director: HEDS Senior Director: HEDS Director: CDS Senior Director: HEDS HR Dean: Humanities |
|  | Recruitment and selection of academic staff Prioritise educational experience and qualifications alongside specialist qualifications and research achievements, when academic appointments are made. | Faculties, HR, Unions | Ongoing | None | All teaching advertisements to state that an education qualification will be an advantage. | Director: Human Resources |
| Committee structures | Clarify the terms of reference for the - Academic Committee - TLT Exco | Academic Committee TLT Exco | 2008 | None | Terms of References | DVC: TLT |
| Mechanisms of academic support | Empower academic support units to respond to the pedagogical challengers posed by TUT students | DVC: TLT, HR, Finances | 2009 | See HEDS Business Plan | HEDS Business Plans | DVC: TLT |

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |

11.3.  Sustainability and Transfer of Learning

  - 11.3.1	Sustainability and Transfer of Learning
To ensure sustainability and transfer of learning it is important that the newly-approved academic structures be populated with permanent appointments.  It is furthermore vital that the entire relocation process be finalised so that stability can be established within all learning programmes on all learning sites.  Another important factor is the upgrading of the post-graduate qualifications of all staff who were matched and placed in positions that require specific qualifications.

# Recommendation 12: Foundation Programmes

The HEQC recommends that Tshwane University of Technology discontinue the practice of admitting unsuccessful diploma applicants to short courses and instead develop and implement appropriate foundation provision to meet the needs of these students.

12.1. Overview

    - At the time of the HEQC audit in 2006 there were many short courses that were being offered at TUT for the purposes of access to main stream study but currently, almost all of those have been discontinued or converted to formally supported and approved (DoE) extended curricula. Since the inception of Foundation Provisioning at TUT in 2005, significant progress has been made in the area of Foundation Provisioning with funding of R9.8 million awarded for 2008 for the running of 19 different extended qualifications (of which 11 were formerly short courses) with a total student enrolment of   approximately 1800. It is therefore apparent that growth and quality improvements in these areas are an essential part of teaching and learning at TUT. All academic staff involved with Foundation Provisioning is in strong agreement that a strategy should be developed ensuring that full-time, highly skilled and proficient staff should be presenting the courses to students. This is however, more expensive than the current model of using part-time staff. It is also more risky financially for the institution as there are no formal written guarantees of funding from the DoE, similar to those in place for formally subsidized students. The recommendation above however, makes it imperative that TUT commits 100% to the DoE approved Foundation structures in a manner which clearly indicates the serious light in which TUT views the problems of underprepared students. The experience and success of the Foundation office in implementing and securing funding for extended curricula offerings has lowered the risks to the institution enough to make this viable and sustainable.
	Strategy towards a Centralized Foundation Unit: This model would use the allocated funding to make new appointments of a dedicated Foundation Provisions academic and administrative team which would work with the faculties and departments involved with extended curricula. The tracking studies that have been carried out to date would indicate that the performance of students who passed through the stand-alone non-credit bearing year programmes in 2005 and 2006 have generally performed better than the extended curriculum students from January 2007. A complicating factor in these results is the relatively low (approximately 50%) retention rates of students. The reasons for this are probably mainly financial and it is for this reason that a separate foundation unit is proposed to maximize the cost effectiveness and quality of presentation of the foundation provisions. The question is also as to the overall effectiveness of the foundation strategy from the DoE’s point of view to which end a report is expected by the end of 2008.  j

12.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Discontinuation of Short courses for Access Purposes | - Introduce relevant extended curricula to replace them. - Initiation of CE at TUT to manage short courses | Foundation Office Curriculum Development Offering Departments CE @TUT | In progress, completion June 2009 | DoE grant | - Approval by DoE - Resume levels (2006) of short course offering | DVC:TLT DVC: BFD |
| Development of Foundational Access options | - Investigate all qualifications with throughput problems - Review data integrity with SMS (Subject success rates) - Plan new extended curricula taking into consideration the HEQF - Introduction of alternative forms of subsidised access (Higher Certificate) | Foundation Office Academic Departments SMS CDS Faculty Advisory Committees | - June 2009 (This is probable due date for application to DoE for funding for next 3 year cycle.) | DoE grant | - Introduction of new extended curricula (unfunded) in 2009. - Support for Higher Certificate from industry - Approval of Foundations under HEQF | DVC: TLT |
| Appropriateness of Foundational options | Review of HR strategy on presentation of Foundation provisions (see proposal page 1) | Foundation Office Faculty representative HR/Manage ment | By December 2008 | DoE grant | Initiation of successful qualifications 2009. | Foundation Academic Department |

12.3.  Sustainability and Transfer of Learning

  - The recommendations made here are based on the experiences in presentation of Foundational or Access provisions made at this institution over many years and are appropriate to the current PQM. The experiences since 2004 of DoE supported Foundational offerings indicate that the funding will be increasing in the future and that the foundation team at TUT is well positioned to maintain and expand these offerings well into the future under the new HEQF structures. It must be stressed however, that this will only succeed if TUT fully commits to the processes and that all stakeholders (internal and external) are also committed. With a successful foundation provisioning model/strategy, great potential exists for addressing the the throughput and success rate challenges currently faced by the institution in a financially sustainable and academically sound manner.  The engagement with national forums on first year experience and access as well as the regular workshopping inputs of HESA registrar5s forum and action projects on implementing the new qualification system ensures regular update and review of current practices.  The Department of Education has also allocated additional funding that will be utilised for capacity building through an international benchmarking visit.  
The national report with analysis of the Foundation provisioning success rate is due towards the end of 2008 and will.

# Recommendation 13: Student Access and Academic Development

The HEQC recommends that Tshwane University of Technology reconceptualise its access and academic development programmes to ensure that students are optimally prepared and supported throughout the duration of their studies and that such programmes are implemented across all sites of delivery.

13.1. Overview

    - 13.1.1	The actions and improvements in quality towards excellence in access and academic development have been a priority of the university  In the past several practices transpired where short learning programmes were utilised for purposes of access in the form of bridging and certificate courses.  There was no alternative at the time. However two actions transpired since 2006. Firstly the University audited all access related programmes and decided to regulate short learning programme offerings very strictly and secondly the Department of Education launched the foundation provision funding mechanism.  The university responded by implementing the new Policy on short learning programmes (SLP’s) that regulates the use of SLP’s for purposes of access.  
A further major development since the audit took place was that the University took a critical strategic decision to establish a consolidated unit for Higher Education Development and Support (HEDS) in 2007, which would incorporate curriculum development and support,,the student development and support function (including counselling and academic development)  Cooperative education, and Teaching and Learning with Technology in an effort  to ensure a holistic and coordinated approach to academic development.  Further, the University scheduled the development of a new Academic Plan.  All Faculties are currently involved in the planning and implementation activities for HEQF and this cements the strong partnership between HEDS and Faculties.  
The 2007 HEQC audit found the University in a state of flux. The merger was being consolidated and a number of new structures were being established and plans developed, most of which have since been approved . , paving way for the ... of the match and place exercise. With the latter approaching completion, TUT can look forward to a time when it will be able to focus its energies on its core business. Top on the agenda is the implementation of the  new strategic approach to  access and academic development.
For the purpose of addressing this recommendation, we have delineated three related aspects, on which the improvement plans will focus These are:
•	Reconceptualise access .
•	Reconceptualise academic development programmes. 
•	Optimally prepare students  for academic success and entering the work place
•	 Support students throughout the duration of their studies.
•	Ensuring equity of provisioning vis-a-vis student support and academic development programmes across all learning sites

The action plan table which follows incorporates both actions already operational as well as those still to be implemented j

13.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Reconceptualise Access Reconceptualise academic development | Meeting/discussion Revise TUT Admissions policy, procedures and programme specific statements for alignment to the NSC, NVC and HEQF. Revise subject specific statement. Review of Policy and statements Implement new strategy Monitor and Evaluate on a continuous basis New Policy: Phasing out SLP’s for access and bridging. Full implementation of foundation provisioning as extended curricula: Interim Funding for extended curricula (2008 – 2009).Roll out of DoE’s extended programme strategy. Critical review of existing foundation programmes. Identification of additional programmes for foundation provisions. Next cycle optimal funding (2010-2012). Establish support unit for students with disability and improve access to University: review current policy on students with disabilities review admissions procedure | TLT and Registry TLT Registrar TLT TLT | - 2007 -2008 (completed) Jan2009 - March 2009 - Implementa-tion 2007 - Proposal and petition to DoE 2007 - Extensive impl 2008 - Academic cycle 2009 - 2009 Review cycle 2009 Proposal sub-mitted Sept 2009 | Human Participation of all Academic departments Deans of Faculty SDS: FP Unit + Faculties SDS: Disability Unit | Strategy and/position paper, Academic committee minutes for confirmation of plan Senate approval: TUT Policy + programme specific admission statements | DVC TLT and Registrar Deputy Registrar: Enrolment SDS: Director (Academic Committee; Senate) SDS: FP Unit Deans of Faculty HoD’s (Academic Committee; Senate) SDS Disability Unit Registrar |
| Part b: Academic Development | Consolidation of student development and support functions in new (Council approved structure): - Establishing holistic service approach with services in: - Personal counselling - Career counselling - Study counselling - Health counselling - Reading and writing skills development - Language development support - Disability support - Mentorship - Risk profiling - Potential assessment - Setting up focus area for HEDS (curriculum development; cooperative education; education technology and student development and support) in the academic line-function. - Extending Faculty Business Plans to accommodate strategically considered student development and support strategies. TUT Academic plan: Development + Implementation | TLT TLT TLT TLT | - Implement new structure October 2008. - Populate structure 2009 – 2011. - Implement all services per learning site HEDS structure implemented 2006 2009-2012 Business Plans 2009-2010 | Revised operational and staff budgets Relocation and establishment funds Consolidated funding structure - re-aligned form previous sectors | Established centres per learning site Full service portfolio per learning site Functional unit with business plans and annual reports Evidence of student success strategies in Faculty BP’s Academic plan approved by Senate and Council | Snr Dir HEDS; SDS Director DVC TLT; HEDS Snr Director; SDS Director Deans of Faculty DVC:TLT; Snr Dir HEDS; SDS Director DVC:TLT; Deans |
| Student support throughout university life | Throughput projects: Development and implementation of the Risk profiling system. Mentorship programme. Developing a Student Tracking system: - Process analysis - Negotiation and development with ITS - Piloting TUT student success programme (development of a comprehensive skills programme for all academic programmes including academic literacy; self regulated learning; emotional intelligence; health matters; information literacy and student workplace skills preparation) Subject success rate analysis Establishment of unit for Health services | TLT RIP FBD | Piloting in 2008 Piloting in 2008 2007 2008-2009 2012 Curriculum design 2008-2009 Annually Implemented 2008 | Budget based funding Budget based funding Budget based funding Budget based funding Subject success data Budget based funding | Risk profiling for 60% of academic programmes Programme per Faculty ITS system development Faculty business plans indicating strategies Throughput report/s to academic committee Annual report to Student Services Council | Snr Dir HEDS; SDS Director Snr Dir HEDS; Director SDS Manager FP Unit Director SMS Director Health and Wellness |
| Equality of service delivery across all campuses | Foundation is faculty based thus delivery will be per academic programme regardless of site. New organisational structure mandates an SDS Unit per learning site. - Match and Place exercise to place current staff. - Populating all the new positions. - Equalise infrastructure. | TLT TLT | 2009 2009-2011 | Foundation grant based funding Foundation grant based funding Relocation and capital funding | Implementation per learning site Functional service unit per site | Snr Dir HEDS; Director SDS Manager FP Unit Snr Dir HEDS; Director SDS |

13.3.  Sustainability and Transfer of Learning

  - •	The University considers the planning for quality improvement in access and academic development sustainable.  The processes, action plans and new structures are policy-based and therefore compulsory and imperative for all stakeholders.
•	The TUT Council has approved new structures that provides the organisational and resourcing platform for the action and improvement plans.
•	As indicated the majority of projects and plans are already underway and evidence of progress and success is regularly reported to the Academic Committee.
•	The institutional roll-out of Foundation programmes to increase accessibility to academic programmes across all learning sites will be secured via the Faculty based approach, i.e. as programmes will be implemented per Faculty it will be done on every site where the programme is delivered.  Current examples already exist.
•	The resourcing of new initiatives and innovations via Teaching Development funding is an effective strategy to fast track the implementation of a number of quality improvement plans in the domain of academic development.  H

# Recommendation 14: Academic Staffing

The HEQC recommends that Tshwane University of Technology ensure that the number of full-time academic staff is sufficient to create an enabling teaching and learning environment for students across all campuses.

14.1. Overview

    - 14.1.1	Whilst under normal circumstances the identified initiatives would constitute a natural starting point, the context of the merger dictates otherwise, viz. taking one step back in order to move forward. For TUT this has meant  finalisation of the Match-and-Place exercise of TUT   as well as the implementation of sustainable academic structures for the different academic departments and faculties, issues which have been priorities for the university.  Since the audit took place TUT has been in the final stages of confirming all staff in their positions to ensure equal distribution of qualified staff and to establish a stable environment at the university.   Monitoring the appointment of academic staff according to approved academic structures to ensure a  justifiable distribution of resources has been a central function of the university.  

Another area of concern raised by the audit report relates to is the uneven quality of programme managenet, a matter largely due to the interim appointment of programme of HoDs and the ongoing consolidation of departments and programmes. It is gratifying to report some progress on these matters: The appointment of Head of Departments was finalised during  the end of 2007.  It is important to provide clarification re the apoointment of HoDs. Heads of Departments do not occupy a specific post but such a person is appointed to an  academic  substantive position and then to the “office” of Head of Department with an allowance as remuneration for the task as Head of Department.  Heads of Department are appointed for a period of five years.  In the event of such a person being relieved of the responsibilities of Head of Department after the five year period or if the person would resign from this task, he or she would return to his/her substantive post.  A range of workshops and induction programs for HODs and Deans were presented during 2007 and 2008 to educate managers in aspects such as TUT’s financial planning and enrolment strategy.  The unit of CCPD is developing  a range of courses ... “License to lead”, addressing all relevant aspects to prepare managers for their task as academic leaders.

The Academic structures of the various academic departments in the faculties were approved by Senate and EMC at the end of 2007.  Academic departments may use approximately  10% of their salary budgets for the appointment of part time staff and industry experts for specialist subjects.  This will ensure that the majority of academic staff is permanent staff with a staff student ratio of 1:33.   This measures well against the national norm of 1:25 staff per student ratio.

Different technology components are implemented in TUT to improve the accessibility of all staff.  Electronic means of communication via WebCT, Email and E-learning projects enhance the accessibility of part time as well as permanent staff.  The workload norms guideline stipulates the minimum criteria for consultation times and availability of staff on the various learning sites.  
All of these are actions taken by the university to create a stable management structure  and a sustainable academic environment for the delivery of quality tuition across all faculties and campuses.

For the purpose of the quality improvement plan the following aspects were identified:
a.	Number of full-time academic staff should be sufficient to create an enabling teaching and learning environment for students across all campuses
The HEQC audit report documented the following concerns:
o	Large number of part time academic staff across campuses alarming (during 2005 60.5% of TUT academics were temporary staff members).
o	Inaccessibility of part-time staff to students.
o	The university should balance the need for permanent staff with the need to provide industry experience for students.
b.	Academic staff should Implement 
The HEQC audit report documented the following concerns:
o	Quality of programme management uneven across the campuses
	Largely due to the interim appointment of all HODs and
	Ongoing consolidation of departments and programmes.
	The above create a major academic risk for the institution in terms of:
1.	student experience,
2.	quality of graduates and 
3.	reputation.
o	TUT needs to ensure that there are substantive HODs in all areas of the institution.
	Academic leadership at HOD level should be properly prepared (through induction or training).
	HODs should be able to manage the quality of their programmes.
o	TUT has to put effective quality measures in place to ensure comparable standards and student experiences
	The quality of tuition provided across faculties and campuses should be consistent.
	A Faculty based campus model may address the above issues.

 Y

14.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Reconceptualise Access Reconceptualise academic development | Meeting/discussion Revise TUT Admissions policy, procedures and programme specific statements for alignment to the NSC, NVC and HEQF. Revise subject specific statement. Review of Policy and statements Implement new strategy Monitor and Evaluate on a continuous basis New Policy: Phasing out SLP’s for access and bridging. Full implementation of foundation provisioning as extended curricula: Interim Funding for extended curricula (2008 – 2009).Roll out of DoE’s extended programme strategy. Critical review of existing foundation programmes. Identification of additional programmes for foundation provisions. Next cycle optimal funding (2010-2012). Establish support unit for students with disability and improve access to University: review current policy on students with disabilities review admissions procedure | TLT and Registry TLT Registrar TLT TLT | - 2007 -2008 (completed) Jan2009 - March 2009 - Implementa-tion 2007 - Proposal and petition to DoE 2007 - Extensive impl 2008 - Academic cycle 2009 - 2009 Review cycle 2009 Proposal sub-mitted Sept 2009 | Human Participation of all Academic departments Deans of Faculty SDS: FP Unit + Faculties SDS: Disability Unit | Strategy and/position paper, Academic committee minutes for confirmation of plan Senate approval: TUT Policy + programme specific admission statements | DVC TLT and Registrar Deputy Registrar: Enrolment SDS: Director (Academic Committee; Senate) SDS: FP Unit Deans of Faculty HoD’s (Academic Committee; Senate) SDS Disability Unit Registrar |
| Part b: Academic Development | Consolidation of student development and support functions in new (Council approved structure): - Establishing holistic service approach with services in: - Personal counselling - Career counselling - Study counselling - Health counselling - Reading and writing skills development - Language development support - Disability support - Mentorship - Risk profiling - Potential assessment - Setting up focus area for HEDS (curriculum development; cooperative education; education technology and student development and support) in the academic line-function. - Extending Faculty Business Plans to accommodate strategically considered student development and support strategies. TUT Academic plan: Development + Implementation | TLT TLT TLT TLT | - Implement new structure October 2008. - Populate structure 2009 – 2011. - Implement all services per learning site HEDS structure implemented 2006 2009-2012 Business Plans 2009-2010 | Revised operational and staff budgets Relocation and establishment funds Consolidated funding structure - re-aligned form previous sectors | Risk profiling for 60% of academic programmes Programme per Faculty ITS system development Faculty business plans indicating strategies Throughput report/s to academic committee Annual report to Student Services Council | Snr Dir HEDS; SDS Director DVC TLT; HEDS Snr Director; SDS Director Deans of Faculty DVC:TLT; Snr Dir HEDS; SDS Director DVC:TLT; Deans |
| Student support throughout university life | Throughput projects: Development and implementation of the Risk profiling system. Mentorship programme. Developing a Student Tracking system: - Process analysis - Negotiation and development with ITS - Piloting TUT student success programme (development of a comprehensive skills programme for all academic programmes including academic literacy; self regulated learning; emotional intelligence; health matters; information literacy and student workplace skills preparation) Subject success rate analysis Establishment of unit for Health services | TLT RIP FBD | Piloting in 2008 Piloting in 2008 2007 2008-2009 2012 Curriculum design 2008-2009 Annually Implemented 2008 | Budget based funding Budget based funding Budget based funding Budget based funding Subject success data Budget based funding | Implementation per learning site Functional service unit per site | Snr Dir HEDS; SDS Director Snr Dir HEDS; Director SDS Manager FP Unit Director SMS Director Health and Wellness |
| Equality of service delivery across all campuses | Foundation is faculty based thus delivery will be per academic programme regardless of site. New organisational structure mandates an SDS Unit per learning site. - Match and Place exercise to place current staff. - Populating all the new positions. - Equalise infrastructure. | TLT TLT | 2009 2009-2011 | Foundation grant based funding Foundation grant based funding Relocation and capital funding |  | Snr Dir HEDS; Director SDS Manager FP Unit Snr Dir HEDS; Director SDS |

14.3.  Sustainability and Transfer of Learning

  - The University considers the planning for quality improvement in access and academic development sustainable.  The strategies that have already been put in place is embedded in institutional procedures and policies and the establishment of new structures to support the plans are well underway, The processes, action plans and new structures that are policy-based  were developed based on  international and national benchmarking  which indicated best practice.  The merger processes of integrating and establishing relevant structures are concluded and these units are already functional.  
A number of factors indicate sustainability:
•	The TUT Council has approved new structures that provides the organisational and resourcing platform for the action and improvement plans.
•	As indicated the majority of projects and plans are already underway and evidence of progress and success is regularly reported to the Academic Committee via annual reports, project plans and business plans.
•	The institutional roll-out of Foundation programmes to increase accessibility to academic programmes across all learning sites will be secured via the Faculty based approach, i.e. as programmes will be implemented per Faculty it will be done on every site where the programme is delivered.  Current examples already exist.
•	The resourcing of new initiatives and innovations via Teaching Development funding is an effective strategy to fast track the implementation of a number of quality improvement plans in the domain of academic development.
•	The strong partnerships between HEDS Directorates and Faculties provides a community of learning and operation for the quality improvement strategiesnh

# Recommendation  15: Libraries Growth Plan

The HEQC recommends that Tshwane University of Technology find innovative ways to develop and resource a five-year growth plan for its libraries that will ensure sustainability and equivalence of provision across campuses.

15.1. Overview

    - Context:
“It was found from the surveys that the library services do not adequately meet the needs of postgraduate students and research staff. Problems with space, access for the disabled and outdated equipment were also identified. During visits to the campuses, the Panel found that there is a lack of seating space for students to study, insufficient access to computers and insufficient copies of prescribed and recommended books. Pretoria West has good library facilities, but these are not matched by the other campuses. The Panel found that there was no equivalence of library provision across the campuses in terms of infrastructure and provision. The Panel learned that TUT has not taken steps to attend to these issues owing to a lack of financial and human resources (AP vol.1: 97). The Panel urges the institution to try to develop and implement a plan to address these concerns.”


Rationale for the proposed improvement plan:

According to Professor Ian Bunting of the DoE, the DoE does not want to impose percentages of the subsidy to be allocated to academic support departments like LIS as they believe that Councils and Vice-Chancellors will do the right thing by the libraries.  N.B. The emphasis (underlining/boldface) is Ms Agyei’s:   “When the new funding framework was introduced in 2004, it did away with the notion of cost units being generated for various institutional activities, including library provision. Institutions now receive input funding based on their student enrolments and output funding based on their graduates and research activities. These funds all go into the pot of Council-controlled funds, which are then distributed at the discretion of the Council. The previous provision for library materials is included in what is called the “teaching input grant”. This is a single, undifferentiated grant amounting to 63% of the total discretionary grant to institutions, and is intended to support the direct teaching activities as well as those such as libraries which offer the underpinning support to teaching.  

“We cannot, with the present framework, give you any breakdown of government funds generated for library materials and equipment or for library staffing. The allocation of funds to libraries is a matter for Councils, which are of course expected to fund reasonably all the activities required for the production of good quality graduates.” 

Currently, TUT does not have a structured way of funding information resources.  It ranks the lowest w.r.t. funding information resources per student head count as shown in the slide at the end of the document.  There has been gross underfunding which has resulted in the current book to student ratio of 3 whilst the minimum recommended ratio for universities is 20.  The average cost of a journal (print or electronic) is R450, while that of books is R400.  For TUT to attain a ratio of 20 books for each of the 56,000 students it plans to have by 2013 1, 120, 000 books are required, costing R448, 000, 000 if calculated at the current rates.   In order to build the collection in manageable chunks and considering the financial implications to TUT, R89, 600, 000 is required to have 224, 000 books by 2013; i.e. over the next 5 year period at least 81,000 books are required at  R32, 400, 000, implying R6, 480, 000 per year for 16, 200 books (print or electronic) only.  Journals and databases account for the rest of the requested funds.  With the funds allocated since 2004, the LIS has been maintaining journal and database subscriptions taken out by the three former technikons; i.e. there has not been any growth in the collections.  LIS also relied on open source e-resources.  In order to add new relevant current titles, subscription to subject and interdisciplinary titles would be done if at least R7, 000, 000 is allocated on an annual basis as from 2009.  Examples of a few databases with current annual subscription prices: 
Sciefinder – R700, 000; IEEE – R450, 000; Scopus – R304, 000; CABI – R352, 500. 


Therefore, the following is a request for funding information resources as from 2009:
•	1% from the Teaching input grant
•	1% from the research development grant
•	1% from the research output grant 1% from Tuition fees collected
This amounts to slightly over R13, 000, 000 in the first year; i.e. 2009.


In addition, TUT should commit to implement the following:
•	Allocations for the following year should not be less than that of the preceding year.  That would provide for inflation; fluctuation of the exchange rate; upkeep of annual subscriptions to electronic resources including databases and print journals that have to be retained.  It would also ensure growth in the collections of information resources.  Maintenance of collections would require at least 10% of the previous year’s allocation.  Provision for growth would require at least 5% of the previous year’s allocation. The LIS funding model shall be reviewed by the LIS Committees every three years.
•	 Funding of the LIS contribution to the Institutional Information Technology Plan (ITP) as revised will be required.
•	 Academic departments will be required to make inputs on annual budget requests for information resources.  This will be jointly done with faculty information librarians and librarians at Distant Campuses.  The recommended budgets will serve at the central library committee.
•	 Each manager in LIS will have to engage in active fund-raising to increase the institution’s allocation for their unit.


H

15.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Develop and Resource the Libraries; Establish forums at all campuses for all stakeholders to be involved in developing and resourcing the libraries to meet their needs and a central forum that will consolidate inputs from the campuses - Establish Campus LIS Committees - Establish Central LIS Committee - Compile terms of reference for both committees - Obtain approval of the committees by relevant structures; i.e. Academic Committee; EMC; Senate; - Heads: Campus Library/Director: LIS - Director: LIS/DVC: RIP; March 2009; - Approval of establishment of the committees by relevant structures - Existence the committees - Scheduled meetings - Participation of academic staff in library matters at strategic level; DVC’s: RIP/TLT. Inadequate seating space for students to study. Lack of access for disabled persons. Outdated equipment. Insufficient access to computers. Insufficient copies of prescribed and recommended books. Inequivalence of provision across campuses: - Pretoria West has good library facilities, but these are not matched by the other campuses - No plan to address these concerns. Five-year growth plan; - Allocation of funds from research development and outputs will be required - Funding of the LIS contribution to the Institutional Information Technology Plan (ITP) as revised will be required - Academic departments will be required to make inputs on annual budget requests for information resources. This will be jointly done with faculty information librarians and librarians at Distant Campuses. The recommended budgets will serve at the central library committee. - Improving the role of academic staff in the acquisition of information resources to support their departments through: - Recommendation of annual budget for information resources; including budget for resources provided through inter-library loans and document delivery systems. This will be done jointly with faculty information librarians. - Recommendation of addition or cancellation of journal titles or databases to support the departments. - Recommendation of book titles (including e-books) and reference works to be added to the collection of the departments. - High level participation in the library committee of the faculty or Distant Campus and the central library committee. - Active oversight of expenditure of the requested funds jointly with the LIS staff. - Each manager in LIS will have to. Sustainability. |  |  |  |  |  |  |

15.3.  Sustainability and Transfer of Learning

  - k

# Recommendation 16: Comprehensive ICT Policy and Provisioning

The HEQC recommends that Tshwane University of Technology develop an ICT policy that addresses the use of IT facilities, including adequate Internet access for students and equitable access to IT facilities for all students across campuses, and ensure that such provision is monitored and evaluated

16.1. Overview

    - Development of ICT policy to address use of IT facilities
Provide adequate internet access and IT facilities at all campuses
Monitor and evaluate facilities and internet access provided 
 
Development  ICT policy to address use of IT facilities
POLICY ON ELECTRONIC RESOURCE CENTRES & i-CENTRES
Date approved by Council: 29 November 2005
1. POLICY ON ELECTRONIC RESOURCE CENTRES & i-CENTRES
 It is the policy of the Tshwane University of Technology (TUT) to give enrolled students access to internet connected computers at a minimal yearly payable ERC / i-Centre levy. 

That a review of existing policy be  conducted in line with the current view to consolidate all laboratories /ERC’s. This would allow for better utilisaion of current infrastructure and facilities.
The following stake holders are involved 
ICT Services 				K. Bokala	
Student Services and Residences    	 Marechal Rabie and Rose Laka-Mathebula
Library Services 			V. Agyei
Academic Committee Representative
Building and Estates 			P. Engelbrecht  
 
Refer to
ERC/I-CENTRE INTEGRATION PROJECT – BUSINESS CASE
AND
COMPUTER LABORATORIES - ICT SERVICES SUPPORT GUIDELINES
 

Provide adequate internet access and IT facilities at all campuses 
The completion of the TENET (Tertiary Education Network) GEN3 project has led to the consolidation all internet links to a single point of entry.
Consolidation has led to increased bandwidth, although not adequate, being made available for equitable distribution amongst campuses.
Provision of additional bandwidth will be addressed by the South African National Research Network SANReN /SEACom project.TUT is a participant in this project, via TENET, which upon completion will provide a backbone of 10GB and increase current internet bandwidth by a factor of ten.
The provision of physical facilities needs to be addressed as part of the IOP or TUT’s long term facilities plan. Financial provision also needs to be made to equip any new venues as well to replace equipment in existing venues. 
The LAN and ERC  projects, currently in progress, will address upgrading of the current network infrastructure and facilities. Provision needs to be made for any venues that have to connect to the LAN backbone.Comment 
16.1.3 Monitor and evaluate facilities and internet access provided 
 ICT Services have begun to deploy ISA servers to monitor and manage bandwidth. The integration of ISA with Active Directory will enable ICT Services to manage usage on an individual account basis. 
Development of a usage / charge back application is also being investigated to implement the approved Internet charge back policy. 
Online surveys / utilisation reports as well as facility utilisation will be used to monitor and evaluate the services being offered.
 Monitoring and Evaluation: This, in our understanding refers to the the continuous assessment of the quality of your servive with a view to findinding out if the levels and quality of delivery is still satisfactory (evaluation) and on the basis of your findings deciding on whether to maintain the status quo or to effect further improvements H

16.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Policy to address use of IT facilities | Review ERC policy | ICT Services | 2009 | Human | Revised Policy | DVC IPO |
| Adequate internet access and IT facilities at all campuses | Link internet gateway to SANReN Provide additional LAB venues Provide IT Equipment | ICT Services Building and Estates Library service Student Services Faculties |  | Financial Human | Upgraded bandwidth | DVC IPO |
| Monitor and evaluate facilities and internet access provided | deploy ISA servers to monitor and manage bandwidth. Develop usage / charge back application Implement internet charge back policy | ICT Services Library service Student Services Faculties | 2010 /2012 | Financial??? Human | ??? | DVC IPO |

16.3.  Sustainability and Transfer of Learning

  - For additional venues provided to be sustainable the following issues would need to be addressed
•	Adequate electricity supply
•	Security for both facilities and students, especially if venues are to be opened for extended hours or even  24*7
•	Environmental issues and air-conditioning
•	Support staff to be available after hours or to implement flexible working hours 
N

# Recommendation 17: Impact of Short Courses

The HEQC recommends that Tshwane University of Technology investigate the quality of the considerable number of short courses currently being offered and their impact on the mainstream activities of departments and Faculties

- Discontinue short courses for access

- Develop and implement appropriate foundation provision

17.1. Overview

    - The HEQC recommends that Tshwane University of Technology revisits the approach to short learning programmes and eliminate all programmes that are used for purposes of bridging and access.  In addition the Committee expresses concern about the impact and quality of short learning programmes and suggests that this aspect should be monitored. Little evidence was found on actual monitoring and evaluation systems within short learning programmes.  Due to the fact that the Policy was newly implemented the HEQC also suggests that the impact and effectiveness of the policy should be evaluated.  The role of foundation provisions versus short learning programmes also require clear defining.

At the time of the audit the university was battling with a legacy of ongoing short learning programmes from the three former institutions.  There were several programmes offered that were bridging programmes by nature and which did not necessarily provide a clear route of access into mainstream programmes.  An internal audit by the Office of the DVC: TLT indicated that the involvement of academic staff in such types of courses was a matter of serious concern.  A number of serious cases of misappropriation came to light and two specific incidents were even reported in the national media. At this time the university took drastic steps and implemented the new Policy on Short Learning Programmes.  The policy had the immediate effects of differentiating between foundation provisions and short learning programmes as well as defining a specific and extensive route of approval and scrutiny for short learning programmes.  

The new approach has had immediate effect in eliminating all short courses of a bridging and access but also to establish short courses as mainly for the purpose of continuous education.  The Senate agenda now regularly reflect applications to offer short courses and these are open to extensive scrutiny. The managing unit has also been reviewed and a new business entity the CE@TUT, an independent business unit, was established.

The university has taken meaningful steps towards regulating the offering of short learning programmes.  (The offering of foundation provisions is dealt with in the context of recommendation 12). 
 K

17.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Review and implement improved practices for SLP’s | Review TUT approach to short learning programmes (SLP’s)Policy or formulation or review of existing policy and procedures approval Revised/ adjusted planning and approval template - Review of current SLP programme portfolio. - Phasing out all bridging and access programmes or restructure as foundational provisions - Review procedure for approval of new short learning programmes. - Role clarification for all stakeholders (Quality promotion; Curriculum development; Academic departments). | Senate DVC: TLT Registrar Foundation Unit Academic Committee DVC: TLT | 2007 2007 2008 2009 | Policy task team Audit team Task team of the Academic Committee Task team of the Academic Committee | Strategy or position approved Phased out programmes Revised procedure implemented Approved role descriptors | DVC:TLT DVC: TLT Faculty DVC: TLT Registrar Faculty Academic Committee + Senate |
| Continuous Quality assurance for SLP’s | Develop a model/tool for quality review and monitoring of short learning programmes - Clear planning for integrated and continuous quality assurance arrangements implemented as part of the programme planning and curriculum format to be approved by Senate: - Regular programme review system. - Implementing arrangements for SLP’s and specified pre-requisites based on academic workload norms. | DVC: TLT Academic Committee Senate DQP DVC:TLT SMS | 2009 2009 + 2008-2009 | Task team of the Academic Committee DQP review cycle plan Workload norms | Implement planning structure (template) Implement review cycle Implemented | DVC:TLT DQP DQP Faculty Exco Senate |
| Investigate impact of offering of SLP’s Implement/ Address | Success rate analysis task team of the Academic Committee to review student pass rates in specified programmes where short coursed are allowed. Establishing a business unit for the management and control of short learning programmes: Investigate options for a business unit to manage SLP’s - Establish CE at TUT - Clarify the main functions of the business unit: - Implement policy - Align SLP with institutional strategic plan and goals - Programme review - Financial control - Monitoring the impact of the SLP on the department and mainstream academic activity - Certification arrangements | DVC:TLT DVC:TLT DVC:FBD EMC EMC Certification Unit Manager : CE@TUT | 2008 - 2009 October 2008 November 2008 | Benchmarking information Updated policy Business Plan | Annual review report to academic committee Exercise complete Functional Unit Approved Business plan SLA with Faculty | EMC Chairperson: Academic Committee DVC:TLT DVC:FBD DVC:TLT DVC: FBD Manager: CE@TUT Registrar |

17.3.  Sustainability and Transfer of Learning

  - The University considers the planning for quality improvement sustainable as the new quality arrangements requires strict monitoring by Senate during the planning of short learning programmes; a regular monitoring but he new business unit (CE@TUT) and also regular review by the student success rate task team.  The establishment of an independent business unit is an approach based on extensive benchmarking of best-practice
In addition the university is set for
•	A policy review in 2009 will accommodate all lessons learnt during the first implementation phase in 2008 and this will be monitored by the Academic Committee.
•	Various very senior managers of the University  to be  directly responsible for the successful transformation of the University approach to short learning programmes with expansion of the foundation provisions strategy (refer recommendations 12 and 13)
•	Regular peer review and self-assessment will ensure relevance and viability of short learning programmes offered.
The University embarked on drastic measures to re-regulate the offering of short learning programmes and set numerous new  plans in place.  The monitoring and implementation of these are well assigned and regular quality review will now be possible. •

# Recommendation 18: Higher Degrees Committee

The HEQC recommends that Tshwane University of Technology establish a Higher Degrees Committee to lead the further development of a research culture at the institution that will embrace responsibility for postgraduate student supervision and student completion, the need for consistency in the application of research student policies and procedures, and student publication requirements.

18.1. Overview

    - Of TUT’s three constituent institutions, Technikon Pretoria was the only institution who offered post graduate qualifications in a number of programs  prior to the merger. Technikon Northwest did not offer any postgraduate qualifications while Technikon Northern Gauteng offered post graduate qualifications in one program.  Although the latter institution did have a set of rules and procedures to regulate postgraduate studies, it did not have  a comprehensive policy for post graduate studies. Technikon Pretoria did not only have a policy with relevant procedures in place but also had a number of supporting documents relating  to postgraduate studies. These included:  
Citation and Bibliographic Reference  Guide                                                                                    Guidelines for the Preparations of Dissertations and Theses                                                       Guidelines for students
Shortly after the merger the policy “Postgraduate Studies” was revised to incorporate  arrangements for the quality  assurance of  postgraduate studies . Both the  Audit Portfolio (AP) and the  Audit Report (AR) from the HEQC refer to a number of procedures and processes put in place by the institution to regulate the various aspects of postgraduate education. In most cases both the AP/AR  refers  to but also acknowledges the efforts of the institution. Responsibilities were assigned to individuals, academic departments, Faculty Boards and Senate as follows: 

TASK	RESPONSIBILITY
Selection of study field and study panel	Head of Department and specialist in the Department
Approval of Research Protocol	Faculty Research Committee and Executive Committee of the Faculty Board
Selection of External assessors	Head of the Department and supervisors
Approval of final title and external assessors	Executive Committee of the Faculty Board
Ratification of title, supervisors and external assessors	Senate
Approval of final result	Senate

The Audit Portfolio did not report separately on the three criteria relating to Research as proposed in “Criteria for Institutional Audits” due to the overlap in   matters to be assessed for each of these criteria. The report was presented in the format proposed in “A  good practice for quality management of research” prepared by the Centre for Research on Science and Technology (CREST) at the University of Stellenbosch,  for the HEQC with inputs from Directors of Research from most institutions. The format ofTUTs submission was based on the four stages of the research process (Developing and evaluating proposals, Assessing resources, Conducting and concluding research and Making research public ) resulting in fairly comprehensive report addressing all aspects of research management. The Audit Portfolio was structured  according to the format and all relevant matters were addressed.
The Audit Portfolio identified a number of shortcomings but in most cases also submitted evidence to the effect that these were being or had been attended to and were acknowledge as such by  the Audit Report from the HEQC.
The inconsistency identified by the Audit Report with regard to the approval of research protocols can be ascribed to the fact that in some faculties the proposal is not approved by the Executive Committee of the faculty after approval by the Faculty Research Committee. 
Inconsistencies with regard to a number of issues related to the approval of research proposals, appointment of supervisors, evaluation of the reports of external assessors and the final approval of the results had been identified long before the self assessment . Minutes of both the Academic Committee and Central Research and Innovation Committee indicate that the issue had been the subject of debate as far back as   2005. Guidelines to manage the process were included in the “Policy on Postgraduate Studies” published in March 2004 as well as amendments in 2005 and 2006. and Faculties were requested to  structure procedures in line with  these guidelines which address inter alia the approval of the research protocol, supervisors, external assessors, qualifications of supervisors and assessors, calculation of marks ( for M degree only ) and approval of the final result.  
There is evidence that Faculties use the guidelines. Perhaps due to the diversity between and within faculties, some degree of inconsistencies still persist.
It is however important to note that the Senate has specific procedures in place to monitor the implementation of these guidelines by faculties. The Directorate Research, Innovation and Partnerships monitor the submissions to Senate by Faculties prior to the meeting of Senate for possible inconsistencies and violation of guidelines.  These are reported to the meeting of Senate. If a specific submission can not be corrected it is been referred back to the relevant Faculty Board.
The Audit Portfolio, recognising the inconsistencies with regard to the development and ultimate approval of research proposals across faculties, argued that a central higher degree committee might contribute to combating the situation. The institution is therefore in full agreement with the findings and recommendations of the HEQC .  The process to establish a Higher Degrees Committee at the institution started in April 2008, will be concluded at the end of 2008 and implemented in 2009.
The function and responsibilities of the HDC and the FHDC are to evaluate, consider and approve all applications and to monitor matters related to postgraduate studies at TUT.  In most cases, the FHDC consider submissions from the departments and will submit their recommendation to the HDC for approval.  Senate will ratify all such approvals.  As a standing subcommittee of Senate, Senate delegates all its powers related to postgraduate studies to the HDC and the FHDC is appointed as a subcommittee of the HDC within each faculty.  Before any degrees can be awarded, the final results of a dissertation or thesis must be approved by the HDC, on recommendation of the FHDC, and ratified by the Senate.  The terms of reference of the established Higher Degree Committee clearly define the role of the different structures ( See Table ). 











Delegated decision making responsibilities of the different committees with respect to postgraduate studies.
COMMITTEE
	Provisional Study Panel	Final Project Proposal	Assessors	Final Results
Department
	Recommend		Recommend	Recommend
DRIC
	-	Recommend	-	-
FHDC
	Approve	Recommend	Recommend	Recommend
Faculty Board 	Ratify	Notice	Notice	Notice
HDC
	Notice	Approve	Approve	Approve
SENATE	-	Ratify	Ratify	Ratify

A number of other structures at the institution support and compliment the tasks of the Higher Degrees Committee. These other structures with their identified tasks are attached to the Higher Degrees Committee resulting in  framework of policies, procedures, guidelines and business processes supporting the development and sustainability of the research strategy of the institution.
Apart from the abovementioned tasks of the Higher Degrees Committee the terms of reference includes inter alia  
•	Arranging a defense of thesis meeting for Doctorate students to defend their theses in accordance with the policy.
•	Advise Faculty Boards on the development and implementation and improvement of policies related to postgraduate studies at TUT.
•	Report to the Faculty Boards on matters related to postgraduate studies.
•	Monitor and manage standards and quality of postgraduate studies in the Faculty.
•	Monitor and manage progress of postgraduate students.
•	Consideration of Ethical issues related to higher degrees.
•	Advise Faculties on strategies related to recruitment and retention of PG students.
•	Receive progress reports from supervisors and use these to monitor progress of PG students.  Appropriate action needs to be taken where required.
•	Consider appeal cases of students who may be of the opinion that they have not been given fair treatment.
•	Report to Senate on matters related to postgraduate studies.
•	Monitor and manage standards and quality of postgraduate studies.

The composition of the Higher Degrees Committee is indicative of the responsibility of the committee but also that the role of all stakeholders in the process is recognised. This include supervisors and student representatives. 
•	DVC (Research, Innovation and Partnerships) as Chairperson
•	DVC (Teaching, Learning and Technology)
•	Executive Deans or their representatives as nominated by the FHDC
•	Director RIP or his/her representative
•	Two members of Senate (not Deans), nominated by Senate

Non voting members of the HDC:
•	Registrar or his/her representative
•	The Director Quality Promotion or his/her representative
•	Representative of the Postgraduate Forum (PGF)
•	The committee has the right to co-opt additional member to assist it where needed.

	      By invitation as observers:
•	Relevant supervisors and/or Heads of Department


The quality–related arrangements for postgraduate education are divided in four broad categories and can be summarised as follows:
Policies related to admission requirements, evaluation of proposals, funding, supervision,   assessment and publication of results  
Processes related to evaluation and monitoring , funding, lodging of appeals and tracking of trends
An information system capturing relevant information and reporting
Strategies for development and support with regard to training for supervision, courses for students, services to students, access to  expertise in the  specific  field, special funding and  support to previous disadvantage  students 
The policy on Postgraduate Studies was revised and approved by Senate in September 2008.
The issues related to the first two categories ( See above ) were addressed in the revised Policy and sufficient procedures are built in to ensure the implementation of the rules and guidelines. 
A number of business processes ( approval of an annual budget for research, guidelines regarding the appropriation of funds, training courses on e.g. proposal writing, supervision, intellectual property, scientific writing, conducting research, various categories of bursaries and funding) are in place to enhance  and support the research of staff and students. The institution is a member of the “consortium” responsible for the implementation of the InfoEd Research Information Management System. The system will ultimately be implemented on a national basis and it is envisage that it will not only addresses the needs of individual institutions but of all the stakeholders up to national level.  


The following documents are relevant and form part of set of documents enhancing  and steering the research strategy at the institution.                                                                         Research and Innovation Strategy                                                                                                             Policy on Intellectual Property                                                                                                                                Policy on Contract Research                                                                                                                                Strategic Framework on Community Engagement                                                                                       Research and Innovation Capacity Development Program

The recommendation by the HEQC to establish a Higher Degrees Committee argues strongly that this committee has “to lead the further development of a research culture at the institution”.
 
The research section of the audit portfolio, but especially  the open ended questions by faculties - is however silent on what one could regard as ”prerequisites” for research ( critical mass of experienced researchers for guidance and mentorship ,  sufficient and high quality postgraduate students – particularly  full time, postdoctoral fellows, infrastructure and resources and linkages – nationally as well as internationally). The “status” of a research culture is not refer  to.  Although not all of these ”prerequisites” will be included in the terms of reference of the Higher Degrees Committee there is no doubt that the activities of the proposed committee will contribute significantly towards the establishment ( if not already present ), enhancement  of a research culture at the institution.
The ultimate question emanating forms the audit is whether  a true research culture exists at the institution. What element(s) one may asked are absent at the university to further enhance a research culture at the institution?  Are there specific factors hinder/ facilitate the development of a culture of research?
What characterize a research culture at an institution of higher education? 
         Should an institution not decide on a “set of the characteristics” in order to benchmark/monitor   
         the development of a research culture? The following three indicators should provide an institution    
        some  insight regarding the “status” of a research culture.

•	Active groups operating at the institution in various disciplines
		Recognition for groups and individuals
		Members link ideas in own and other discipline
		Mentoring and assistance in writing of papers, application for grants, etc. 
		Disseminate the results of their research
		Mentoring of novice members and students
Members of the group visit other researchers and the group is visited by other researchers 
	Where does TUT stands with regard to groups operating within the university?
The Research and Innovation Strategy depends on the development and implementation of R&I focus areas and the relevant niche areas.  In the development of R&I focus areas the following are considered as important criteria:
•	Strategically selected, approved and managed by the institution.  
•	Relevance to national and regional needs, priorities and opportunities.
•	Consolidation of R&I expertise and infrastructure.
•	Critical mass of staff and students.
•	A recruitment strategy that is directed towards building capacity in the R&I focus areas.
•	Potential to develop into a centre of excellence.
•	Potential for sustainability.
An R&I focus area, with constituent niche areas, is an area with a central focus that can involve several disciplines or aspects of one discipline.  It is designed to bring resources and people together around a central theme and a critical mass of people and provide the platform for the full spectrum of R&I activities.  The theme should be relevant to national and regional needs, priorities and opportunities.
The R&I focus area is therefore envisaged as the generating point for heightened R&I outputs and increased capacity for the involvement of staff and postgraduate students.
•	Partnerships
The understanding the importance of different formats of partnerships between higher education, government, industry and communities at regional, national and international levels  remains one of the big challenges for higher educational institutions to be recognized as innovative and entrepreneurial. Mode two of knowledge production advocates strongly  the operating in collaboration with industry and other partners. 
	Where does TUT stands with regard to partnerships?
The audit of the partnerships the institution indicated successful co-operation in a number of disciplines with national ( local, provincial and central governmental structures, industry and non-governmental organisations  ) as well as on international level ( Europe, North and South America and Asia). All these initiatives are taking place on an ad-hoc basis and not always structured resulting in the absence  of quality related arrangements. 
A document “Community Engagement – Strategic Framework” was recently approved by Senate. The document indicates the difficulty to define and accommodate the a variety of views and definitions:
•	The view that community is synonymous with the public and hence a public good. This intersects with concepts of citizenship.
•	A geographic or regional notion of community that is linked to place that is particularly prevalent. 
•	A community of interest may transcend place and bind by values, beliefs, or commonly shared identity traits. 
•	Community can also refer to the professional and industry bodies which employ university graduates.

For the purpose of the TUT Strategic Framework on Community Engagement, the following definition has been adopted:

“Communities refer to specific, collective interest groups, primarily within the regions close to ( but not restricted to ) TUT, which contribute  to the mutual search for sustainable solutions to jointly identified challenges and service needs through the utilisation of the full range of resources at their disposal”

Until fairly recently, internationally and in South Africa, views on community engagement focused on a one-way, paternalistic and altruistic implications of the term.  
There is a clear distinction between the one-way, paternalistic and altruistic implications of the term community service, and the mutually active implications of the term community engagement. Effective community engagement requires deliberate, considered and mutually determined collaborations between communities, governments, funding partners, scholars, students and administrative staff. It is also based on democratic principles of participation, consultation and accountability.   
It often involves partnerships and coalitions that help mobilize resources and influence systems, change relationships among partners, and serve as catalysts for changing policies, programs, and practices.

It is envisage that the strategic document will direct the institution in the involvement in partnerships as part of a research culture.  

•	Undergraduate education
The answer most probably is whether the institution is successful to promote and facilitate a key characteristic of a university - to link Teaching and Research.  

Evidence indicated that students may benefit from research activities provided that the linkages are well planned and be explicit. A number of processes can be implemented to enhance this linkage of which the following two are crucial:

Research based learing 
Research-led curricula 

In essence – undergraduate students should be participants in the research process. The current mainly career – focused  curricula could be restructured to enhance all the elements of true scholarship – teaching, discovery, integration and application.

  Where does TUT stands with regard to the contents of curricula? 
The current re-curriculation process allows the institution to attend to this challenge. 
,

18.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Develop policy | Revised the existing policy ( Policy on Postgraduate Studies approved by Senate in 2004 and amendments approved in 2005 and 2006 ) and incorporate resolutions by different structures related to the policy in the document | Director: Research, Innovation and Partnerships Executive Dean: Sciences | April 2008 | None | Draft document available | DVC: Research Innovation and Partnerships |
| Approval of policy | Submitted the policy for approval to the relevant structures (Academic Committee, Administrative Support Committee, Central Research and Innovation Committee and Faculty Boards. Incorporated comments, suggestions and recommendations into the document Submitted the document to the relevant DVC for submission to the EMC and to Senate | Director: Research, Innovation and Partnerships Executive Dean: Sciences Director: Research, Innovation and Partnerships Executive Dean: Sciences Director: Research, Innovation and Executive Dean: Sciences | May to June 2008 July 2008 August 2008 | None None None | Agendas and minutes of the different committees Revised document available Document submitted to the relevant DVC | DVC: Research Innovation and Partnerships |
| Implementation | Establishment of the Institutional Higher Degrees Committee Establishment of Faculty Higher Degrees Committees | DVC: Research, Innovation and Partnerships Executive Deans of Faculties | October 2008 October 2008 | None None | Agenda and minutes Agenda and minutes | DVC: Research Innovation and Partnerships |

18.3.  Sustainability and Transfer of Learning

  - According to the PQM the institution aims that seven percent of the total student number will be at postgraduate level.  Currently the percentage is three percent.  The increase of research output is included in the strategic goals and objectives for the period 2009 to 2013. Activities identified to enhance the research output include the improvement of the management of postgraduate studies, supervision capacity and increase in postgraduate enrolments and outputs. The role and responsibilities of the Higher Degrees Committee are pivotal to achieve the envisage outputs. 
A comprehensive policy (adopted by and communicated to all stakeholders) on “Postgraduate Studies” was approved recently to guide but also regulate all aspects of postgraduate studies at the institution. These revised procedures were decided upon after the shortcomings in the previous practice were identified.  
In summary – the institution decided to increase research outputs which include an increase in postgraduate students and their outputs, policies and rules are in place to regulate the processes, faculties set targets with regard to the number of postgraduate enrolments, the necessary monitoring procedures are in place  and interventions  have already be implemented. Academic staff is committed to ensure that the institution be recognised as a role player with regard to research at South African institutions of higher education.
According to the terms of reference of the Higher Degrees Committee the committee reports to Senate
The terms of reference also prescribes the format of reports to Senate.
In the light that the VC , DVC:RIP and the Executive Deans chair meetings of Senate, the Institutional Higher Degrees Committee and Faculty Higher Degrees Committees respectively  it can be argued that the sustainability and the implementation will not be in question
/

# Recommendation 19: Community Engagement

The HEQC recommends that Tshwane University of Technology engage in an institution-wide debate on who constitutes its community for purposes of engagement, develop a framework, policies and implementation plans by means of which community engagement can be quality managed and integrated into the curriculum, establish an institutional structure to direct its activities, and allocate responsibilities.

19.1. Overview

    - Prior to the merger the three erstwhile technikons were involved defferently in community engagement activities, which involvements were practiced on an ad-hoc basis. Projects ranged from small activities-driven by individuals in local communities-to fairly large projectts, which were structured, clearly defined (some linked to research projects) and funded by donor agencies, the private sector and international funders. A few of these projects are refered to in the Audit Portfolio. Unfortunately, the situation persists after the merger. 
Conceptualisation/Implementation
In light of the above CE is now an institutionally accepted as an umbrella term- a co-function to Teaching, Learning and Research- supported by the university’s mission statement as entrenched in the institution’s IOP. An instituitional CE Strategic Framework has been developed, which document is presently doing its rounds within the various bodies of the university. The document has also managed to conclusively bring an understanding on who it constitutes as its community for purposes of engagement and arived at the following definition: “Communities refer to specific, collective interest groups, primarily within the regions affiliated to TUT, which contribute to the mutual search for sustainable solutions to jointly identified challenges and service needs through the utilisation of the full range of resources at their disposal”.
 The newly formulated strategic goals and objectives in no uncertain terms not only commit the institution to community engagement but also set targests to be reached within the next five years.
•	A risk register was established and the absence of linkages was identified amongst one of the high risks of the institution. Necessary interventions have been proposed to manage and reduce the risk.
•	The Turnaround Strategy approved and implemented by the institution provided interventions.
 
•	A database of current community engagement activities is constructed.

•	A new structure has been approaved.

The rationale behind TUT’s engagement is based on the general empowerment for the betterment of its community and to respond to the National Higher Education’s Transformation Strategy.


Contextualization
a. The present organisational structure for the institutional governance of the community engagement is as follows:

                                                                       DVC: RIP

                                                          Executive Director: Partnerships
                                                                         
                                                                 HOD: Parnerships
                                                                      
                                                   Project Officer: Community Engagement (CEPO)

b. The proposed organisational structure for the institutional governance of community engagement is as follows:
                                                                                  DVC: RIP or CE

 

CE Inst Committee		            Ex Dir: Partnerships/CE/		              CE Advisory Committee
(CEIC)				           HOD: Parnerships/CEPO 			(CEAC)
(DVCs:RIP, T & LT, reps from deans/faculties,					(DVCS: RIP, T &LT reps
 Directorates: Partnerships(2)/CE,						Dir Partnerships, deans, 
R&I, AO, QM & Student Affairs).							external stakeholders).



Operationalisation
					Curricular
                                                                          				

 			         DVC: T & LT/Deans/Directorates





Academic/support staff & students				-     Cooperative Education
-	Experiential Learning
-	Discipline Based Learning
-	Service Learning
-	Research
-	Short Learning Programmes
-	Philanthropic activities.
M

19.2.  Improvement Action Plan

| Aspect of Recommendation | Actions | Responsibility | Time Line | Resources Needed | Performance Indicators | Accountable Person/Structure |
| --- | --- | --- | --- | --- | --- | --- |
| Debate on who constitutes TUT’s community; Hold Workshops and with the general staff, students to stimulate discussions on the cocept; Ex Director Partnerships, HOD: Partnerships; June to 2007- November 2008; Cost estimate: R 5000,00 for posters; Workshops reports, essays from staff & students as well as posters; DVC: Research Innovation and Partnerships. Development of a CE framework; -Develop a strategic framework based on national and international benchmarks and the incorporation of inputs of workshops and by individuals. -Submit the framework to key governance structures for ratification (DVC: T & LT, Academic Committee, Administrative Support Committee, Central Research and Innovation Committee and Faculty Boards. Incorporate committees’ comments, suggestions and recommendations into the document. -Submit document to the EMC and to Senate; Ex Director: Partnerships HOD: Partnerships & staff; February to April 2008 May to July 2008 August 2008 April 2009; None Costs: None Costs: None Costs: None; Draft strategic framework finalised Agendas and minutes of the different committees Revised document available Document submitted to the relevant DVC.; DVC: Research Innovation and Partnerships. Develop policies; - Develop of policies. -Submit the policies to key governance structures for ratification (DVC: T & LT, Academic (Academic Committee, Administrative Support Committee, Central Research and Innovation Committee and Faculty Boards. -Incorporate comments, suggestions and recommendations into the document. -Submit the document to the relevant DVC for submission to the EMC and to Senate; Director: Research, Innovation and Partnerships/ Ex Director Partnerships/hod : Partnerships/Project Officer; January to March 2009 April and May 2009 June 2009; Costs: None Costs: None Costs: None None; Draft document available Agendas and minutes of the different committees Revised document available Document submitted to the relevant DVC; DVC: Research Innovation and Partnerships. Implementation of CE framework; -Develop implementation plans which will be reflected in the Business plan. - Monitor the implementation of the Strategy and Policies.; Director: Research, Innovation and Partnerships HOD : Partnerships; July 2008; Depending on the planning of Faculties, Departments and units; Annual business plans submitted and approved; DVC: Research Innovation and Partnerships. Integrate CE into curricular; Training of academic staff for the implementation of CE into curricular; Directorate: Curriculum Development & Support; November 2009 onwards; Cost: to be culculated; Reports to the CRIC , DVCs: T&LT,RIP, EMC and Senate; DVC: T&LT. Populatate the CE institutional structure and responsibilities; -Appoint committee members for the different CE operational strutures. -Compile relevant job profiles. -Filling of the posts.; DVC: RIP, Ex Director: Partnerships HOD : Partnerships; As from February 2009 onwards; None; Job profiles submitted to and approved by the JP committee Appointments finalised; DVC: Research Innovation and Partnerships. |  |  |  |  |  |  |

19.3.  Sustainability and Transfer of Learning

  - The business processes envisaged to be part of the policies will provide guidelines to sustain the initiatives.
The submission of reports to Faculty Boards and Senate will enable managers to oversee the sustainability of initiatives.
The construction and approval of business palns for projects, including targets/outputs will be a prerequisite to monitor progress and outcomes.
Regular evaluations including assessments by stakholders will be used to determine the general project quality (whether expectations were met, if not why and if the project was beneficial to all stakeholders).

Overall remarks: 
In introduction refer to the lip service paid to the trilogy of Research, Teaching and Community Engagement, as reflected amongst othe things by the faculty reward structure and promotion policies. I would like to believe that the success of community engagement is also tied to the value attached to CE by the sector. Prof Kok, you correctly point out to the direct reference to CE in our mission. In spite of the odds against CE, we have to make it work, because it is one of the things we elected to excel in according to our mission. As in REC 19, I think it is opportune to include somewhere in the overview or even in the concluding paragraph, a section on factors which either facilitate or hinder successful implementation of a  community engagement strategy.

# Conclusion

# Click here to enter text.

Faculty Cooperative Education Coordinators: located in faculties.

Cooperative Education Lecturers ( Lecturers having the addition responsibility to do Coop Ed in a learning programme)

Deputy Vice Chancellor: Teaching , Learning and Technology

Cooperative Education

Head of Department