## Sheet1
TSHWANE UNIVERSITY OF TECHNOLOGY
CAPITAL EXPENDITURE PROGRAMME - IMPLEMENTATION OF ADOPTED INSTITUTIONAL OPERATING PLAN
IOP PROGRAMME MANAGEMENT PROGRESS REPORT RTT: 29-05-2009
| PROJECT NO | TENDER NO | PROJECT DESCRIPTION | DOE ALLOCATION | Appt. of Consultants | Project Brief | DESIGN PROCESS | Concept Design | Design Layout sign-off by TUT | Design Development | MUNICIPAL APPROVALS | PROJECT BUDGET | Pre- Tender Estimate | Total Project Costs Inc VAT, Fees | Cost Status | PROCURMENT | Tender Documentation | Tender Process | Appt. of Contractor | CONSTRUCTION | Commencement Date | Completion Date | Construction Status Report | Comments | `
Updated on Thursday, 05 November 2009.
[14 empty] | ESTIMATED | [7 empty] | PLANNED
SECTION B:TUT B&E MANAGED PROJECTS
31 | PT27 |  | Teaching and Learning with Tech Phase 1 | 5.3 | ☺☻ | Ж |  | Ж | Ж | Ж |  |  |  | 10000000 | IOP Budgets | [5 empty] | Jan 2007 | Dec 2009 | In Planning Stage, awaiting Security. | Funds Transferred, Installations in progress as per IOP Projects.
32 | PT27 |  | Teaching and Learning with Tech Phase II | 5.3 | ☺☻ | Ж |  | Ж | Ж | Ж |  |  |  | 6000000 | IOP Budgets | [5 empty] | Jan 2008 | Dec 2010 | In Planning Stage, awaiting Security. | Funds Transferred
33 | PG62 | TR51/2006 | Student Affairs Building Ga-Rankuwa | 1.4 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | ☺☻ |  | ☺☻ | 500000 | IOP Budgets |  | ☺☻ | ☺☻ | ☺☻ |  | Jan 2008 | Sept. 2009 | 100% Completed | 100% Completed.
34 | PS17 | TR25/2008 | Fencing at Soshanguve South and Ga-Rankuwa | 1.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 4500000 | IOP Budgets |  | ☺☻ | ☺☻ | ☺☻ |  | Nov 2008 | 2009-09-01 | Soshanguve South 100% Complete and Erf 9126 Zone 2 Ga-Rankuwa 100% Complete and Erf 9122 Zone 2 is 100% Complete. | 100% Completed.
35 | PS20 | TR26/2008 | Upgrading of Residences Soshanguve South | 2.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 4000000 | IOP Budgets |  | ☺☻ | ☺☻ | ☺☻ |  | Nov 2008 | Sept. 2009 | 100% Completed | 100% Completed.
36 | PT23 |  | Upgrade Residences Soshanguve North | 2.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 20000000 | IOP Budget |  | ☺☻ | ☺☻ | ☺☻ |  | Jan 2008 | May 2009 | 100% Completed | 100% Completed.
37 | PU01 |  | Upgrade Lift Kosmos guesthouse | 5.2 | ☺☻ | Ж |  | Ж | Ж | Ж | Ж |  | Ж | 600000 | IOP Budget | [5 empty] | May 2009 | Sept. 2009 | 100% Completed | 100% Complete.
38 | PU01 |  | Upgrade lift Towers Residence | 5.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 100000 | IOP Budget |  | ☺☻ | ☺☻ | ☺☻ |  | Nov 2008 | Jan 2009 | 100% Completed | 100% Completed.
39 | PP04 | TR2/2009-IOP | Premos Laboratories | 3.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 1500000 | IOP Budget |  | ☺☻ | ☺☻ | ☺☻ |  | Oct 2008 | August 2009 | 100% Completed | 100% Completed.
40 | PP04 | TR3/2009-IOP | Old Mutual Park: Relocate Procurement | 3.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 2000000 | IOP Budget |  | ☺☻ | ☺☻ | ☺☻ |  | Oct 2008 | Nov. 2009 | Demolition in progress. | Contractor appointed, Site Handed-Over -27-10-2009, Commencement date - 02-11-2009.
41 | PS17 |  | Upgrading Security | 2.3 | ☺☻ | ☺☻ |  | ☺☻ | Ж | Ж | Ж |  | Ж | 21000000 | IOP Budget | [5 empty] | April 2008 | Dec 2010 | In tender Stage | Consultant appointed, Security implementation in progress.
42 | PM53 |  | CPM Fees | 5.5 | [9 empty] | 8000000 | IOP Budget | [7 empty] | DPA Managed Projects as per Section A. | For Notification.
43 | PG31 |  | Ga-Rarankuwa allocation | 1.1 | [9 empty] | 3000000 | IOP Budget | [8 empty] | Allocation awaiting Feasibility Study Outcome (Guidance).
44 |  |  | Distance Campuses | 5.1 |  | x | [7 empty] | 3600000 | IOP Budget | [7 empty] | In planning stage, Planning meetings held on 03 and 04 September 2009 and Follow-up meetings between 29 September and 02 October 2009. | Report Compiled and presented to the RTT, awaiting response. Clarity needed whether the Funds are for Upgrading or TLT-Minimum standards.
45 |  |  | Project Buffer for ICT installations, VO's | 5.6 | [9 empty] | 4000000 | IOP Budget | [5 empty] | Jan 2008 | Dec 2010 | Ongoing - Connectivity Per Project | Proposal to allocate to ICT Department, Connectivity Project.
46 | PG36 |  | Multi-Purpose Hall: Ga-Rankuwa Campus. | 0 | [9 empty] | 30000000 | [8 empty] | In Planning Stage | Awaiting feed-back from the Finance Committee on Capital Allocation Plan and the Feasibility Study Outcome.
47 | PA44 |  | Administration Block and Offices - Arts Campus | [10 empty] | 2000000 | IOP Budget | [5 empty] | 2010-01-01 | 2010-06-01 | In Planning Stage | A meeting arranged for Thursday, 15 October 2009.
[14 empty] | 120800000 | 352654661
Key | √ |  | Commenced
| Ж |  | In Progress
| ☺☻ |  | Completed
| x |  | Not commenced
SECTION C: Request for approval from RTT to Transfer Funds to appropriate Entity and Account Numbers (Request for Orders)
| P.No. | Tender No. | PROJECT DESCRIPTION | [10 empty] | Amount + VAT | Cost Status | [5 empty] | Date of Request | Date of Approval | Total Amount to be transferred | Comments
1
3
.

## Compatibility Report
Compatibility Report for TUT Managed Projects - Programme RTT-16-10-2009 (MHM).xls
Run on 2009/10/15 10:17
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 14