## Sheet1
TSHWANE UNIVERSITY OF TECHNOLOGY
CAPITAL EXPENDITURE PROGRAMME - IMPLEMENTATION OF ADOPTED INSTITUTIONAL OPERATING PLAN
IOP PROGRAMME MANAGEMENT PROGRESS REPORT RTT: 29-05-2009
| PROJECT NO | TENDER NO | PROJECT DESCRIPTION | DOE ALLOCATION | Appt. of Consultants | Project Brief | DESIGN PROCESS | Concept Design | Design Layout sign-off by TUT | Design Development | MUNICIPAL APPROVALS | PROJECT BUDGET | Pre- Tender Estimate | Total Project Costs Inc VAT, Fees | Cost Status | PROCURMENT | Tender Documentation | Tender Process | Appt. of Contractor | CONSTRUCTION | Commencement Date | Completion Date | Construction Status Report | Comments | `
Updated on Thursday, 26 November 2009.
[14 empty] | ESTIMATED | [7 empty] | PLANNED
SECTION B:TUT B&E MANAGED PROJECTS
31 | PT27 |  | Teaching and Learning with Tech Phase 1 | 5.3 | ☺☻ | Ж |  | Ж | Ж | Ж |  |  |  | 10000000 | IOP Budgets | [5 empty] | Jan 2007 | Dec 2009 | Project Execution commences as per IOP Projects Progress. | Funds Transferred, Installations in progress as per IOP Projects.
32 | PT27 |  | Teaching and Learning with Tech Phase II | 5.3 | ☺☻ | Ж |  | Ж | Ж | Ж |  |  |  | 6000000 | IOP Budgets | [5 empty] | Jan 2008 | Dec 2010 | In Planning Stage for 2010. | Funds Transferred
33 | PG62 | TR51/2006 | Student Affairs Building Ga-Rankuwa | 1.4 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | ☺☻ |  | ☺☻ | 500000 | IOP Budgets |  | ☺☻ | ☺☻ | ☺☻ |  | Jan 2008 | Sept. 2009 | 100% Completed | 100% Completed.
34 | PS17 | TR25/2008 | Fencing at Soshanguve South and Ga-Rankuwa | 1.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 4500000 | IOP Budgets |  | ☺☻ | ☺☻ | ☺☻ |  | Nov 2008 | 2009-09-01 | Soshanguve South 100% Complete and Erf 9126 Zone 2 Ga-Rankuwa 100% Complete and Erf 9122 Zone 2 is 100% Complete. | 100% Completed.
35 | PS20 | TR26/2008 | Upgrading of Residences Soshanguve South | 2.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 4000000 | IOP Budgets |  | ☺☻ | ☺☻ | ☺☻ |  | Nov 2008 | Sept. 2009 | 100% Completed | 100% Completed.
36 | PT23 |  | Upgrade Residences Soshanguve North | 2.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 20000000 | IOP Budget |  | ☺☻ | ☺☻ | ☺☻ |  | Jan 2008 | May 2009 | 100% Completed | 100% Completed.
37 | PU01 |  | Upgrade Lift Kosmos guesthouse | 5.2 | ☺☻ | Ж |  | Ж | Ж | Ж | Ж |  | Ж | 600000 | IOP Budget | [5 empty] | May 2009 | 30 Nov. 2009 | 100% Completed | 99.5% Complete.
38 | PU01 |  | Upgrade lift Towers Residence | 5.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 100000 | IOP Budget |  | ☺☻ | ☺☻ | ☺☻ |  | Nov 2008 | Jan 2009 | 100% Completed | 100% Completed.
39 | PP04 | TR2/2009-IOP | Premos Laboratories | 3.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 1500000 | IOP Budget |  | ☺☻ | ☺☻ | ☺☻ |  | Oct 2008 | August 2009 | 100% Completed | 100% Completed.
40 | PP04 | TR3/2009-IOP | Old Mutual Industrial Park: Relocate Procurement | 3.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 2000000 | IOP Budget |  | ☺☻ | ☺☻ | ☺☻ |  | Oct 2008 | Nov. 2009 | 25% Completed | Contractor appointed, Site Handed-Over -27-10-2009, Commencement date - 02-11-2009.
41 | PS17 |  | Upgrading Security | 2.3 | ☺☻ | ☺☻ |  | ☺☻ | Ж | Ж | Ж |  | Ж | 21000000 | IOP Budget | [5 empty] | April 2008 | Dec 2010 | In tender Stage | Consultant appointed, Security implementation in progress.
42 | PM53 |  | CPM Fees | 5.5 | [9 empty] | 8000000 | IOP Budget | [7 empty] | DPA Managed Projects as per Section A. | For Notification.
43 | PG31 |  | Ga-Rarankuwa allocation | 1.1 | [9 empty] | 3000000 | IOP Budget | [8 empty] | Allocation awaiting Feasibility Study Outcome (Guidance).
44 |  |  | Distance Campuses | 5.1 |  | x | [7 empty] | 3600000 | IOP Budget | [7 empty] | Available funds are for TLT to be installed and commissioned at Polokwane, eMalahleni and Mbombela Campuses. | Available funds are for TLT to be installed and commissioned at Polokwane, eMalahleni and Mbombela Campuses.
45 |  |  | Project Buffer for ICT installations, VO's | 5.6 | [9 empty] | 4000000 | IOP Budget | [5 empty] | Jan 2008 | Dec 2010 | Ongoing - Connectivity Per Project | Funds to be allocate to ICT Department, Connectivity Project.
46 | PG36 |  | Multi-Purpose Hall: Ga-Rankuwa Campus. | 0 | [9 empty] | 30000000 | [8 empty] | In Planning Stage through the Feasibility Study. | Awaiting feed-back from the Finance Committee on Capital Allocation Plan and the Feasibility Study Outcome.
47 | PA44 |  | Administration Block and Offices - Arts Campus | [10 empty] | 2000000 | IOP Budget | [5 empty] | 2010-01-01 | 2010-06-01 | In Planning Stage | Awaiting confirmation of Funds for the Project.
[14 empty] | 120800000 | 352654661
Key | √ |  | Commenced
| Ж |  | In Progress
| ☺☻ |  | Completed
| x |  | Not commenced
SECTION C: Request for approval from RTT to Transfer Funds to appropriate Entity and Account Numbers (Request for Orders)
| P. No. | Tender No. | PROJECT DESCRIPTION | [10 empty] | Amount + VAT | Cost Status | [5 empty] | Date of Request | Date of Approval | Total Amount to be transferred | Comments
1 | PP04 | TR3/2009 IOP | Old Mutual Industrial Park-Procurement Relocation Upgrading. | [10 empty] | 2700000 | IOP Budget | [5 empty] | 27/11/2009 |  | 2700000 | R2,321,378.01 - is for the Contractor as per Tender. R202,583.92 - Quantity Surveyor & Project Manager's Fee. R14,748.80 - Structural Engineer's Fee. R46,427.56 - Mechanical Engineer's Fee. TOTAL = R2,585,137.99 (Awaiting ICT and Security Quotations).
.

## Compatibility Report
Compatibility Report for TUT Managed Projects - Programme RTT-16-10-2009 (MHM).xls
Run on 2009/10/15 10:17
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 14