## RTT
TSHWANE UNIVERSITY OF TECHNOLOGY
CAPITAL EXPENDITURE PROGRAMME - IMPLEMENTATION OF ADOPTED INSTITUTIONAL OPERATING PLAN
IOP PROGRAMME MANAGEMENT PROGRESS REPORT RTT: 23-10-2009
| PROJECT NO | TENDER NO | PROJECT DESCRIPTION | DOE ALLOCATION | Appt. of Consultants | Project Brief | DESIGN PROCESS | Concept Design | Design Layout sign-off by TUT | Design Development | MUNICIPAL APPROVALS | PROJECT BUDGET | Pre- Tender Estimate | Total Project Costs Inc VAT, Fees | Cost Status | PROCURMENT | Tender Documentation | Tender Process | Appt. of Contractor | CONSTRUCTION | Commencement Date | Completion Date | Construction Status Report | Comments
SECTION A:DPA MANAGED PROJECTS:
[14 empty] | ESTIMATED | [7 empty] | PLANNED
1 | PP02 | TR1/2008 | Printing Works - Alma du Toit Building | 3.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 12100244 | Contract price |  | ☺☻ | ☺☻ | ☺☻ |  | 04-04-2008 | 05/09/2008 | Inside:Completed ,Additions:Completed .Close-out documentation.Final Accounts. | Handover mtg held; 10-09-2008
2 | PP03 | TR12/2008 | Building 20 - Hospitality Pretoria | 3.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 14111594 | Contract price |  | ☺☻ | ☺☻ | ☺☻ |  | 15-09-2008 | 22/05/2009 | 100% Completion. | Handover meeting held: 26-06-2009, 10.00 am
3 | PA43 | TR9/2008 | Building 25 - Arts Campus Arcadia | 4.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 8271940 | Contract price |  | ☺☻ | ☺☻ | ☺☻ |  | 24/06/2008 | 09/02/2009 | Section 1 Additions : Completed. Section 2 Renovations:100% Completion | Hand-over Sec. 2:16-02-2009. Handover Sec 1:29-10-08
4 | PA 44 | TR20/2008 | Power Upgrade- Arts Campus Arcadia | 4.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | ☺☻ |  | ☺☻ | 2142852 | Contract price |  | ☺☻ | ☺☻ | ☺☻ |  | 23/10/2008 | 26/03/2009 | 100% Completion. | Hand-over Mtg held:26-01-2009
5 | PA42 | TR28/2008 | New Building - Arts Campus Arcadia | 4.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | ☺☻ |  | ☺☻ | 29479977 | Preliminary cost estimate |  | ☺☻ | ☺☻ | ☺☻ |  | 20/04/2009 | 26/03/2010 | 44% Completion. | Site Meeting: 26-10-2009, 14.00
6 | PP01 | TR13/2008 | Business School - Metro Skinner | 3.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | ☺☻ |  | ☺☻ | 14585375 | Contract Price |  | ☺☻ | ☺☻ | ☺☻ |  | 16/09/2008 | 29/05/2009 | 100% Completion. Excl. fascade | SiteInspection & Hand-over meeting: 07-08-2009, 11am
7 | PB54 | TR11/2008 | Arcadia - Research Labs & Offices in Bld 3 | 4.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | ☺☻ |  | ☺☻ | 4047560 | Contract price |  | ☺☻ | ☺☻ | ☺☻ |  | 20-06-2008 | 28/11/2008 | 100% Completion. Gas installation completed. | Hand-over offices:28-11-2008. Site Hand-over Mtg Lab..:30-01-2009
8 | PB51 | TR1/2009 | Second Year Labs Arcadia Science Bld 4 | 4.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 6487700 | Preliminary cost estimates |  | ☺☻ | ☺☻ | ☺☻ |  | 2009-07-09 | 2010-12-03 | 12% Completion. | Site Meeting :30-10-2009 @11.00am
9 | PB52 | TR22/2008 | Arcadia Hall Building 5 | 4.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 1246120 | Contract price |  | ☺☻ | ☺☻ | ☺☻ |  | 03-11-2008 | 30/01/2009 | 100% Completion. | Hand-over meeting:30-01-2009 at 13.00 hrs.
10 | PT21-30 | TR17/2008 | Shosanguve North | 2.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 32100000 | IOP Budgets |  | ☺☻ | ☺☻ | ☺☻ |  | 24-11-2008 | 11/12/2009 | 53% Completion.Bld 4,10,19,13. PC:Bld.6,7,55, 50 | Site Meeting:27-10-2009 at 12.00pm
11 | PT31 | TR17/2008 | Air-Conditioning Sosh North | 2.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 14000000 | IOP Budgets | [6 empty] | 11/11/2009 | Variation Order on TR17/2008 process.20% Completed. | Implemented.
12 | PT 22 | TR27/2008 | Power Upgrade- Soshanguve-North | 2.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 9794006 | Contract price |  | ☺☻ | ☺☻ | ☺☻ |  | 24-11-2008 | 11/12/2009 | 98% Completion. | Site Meeting: 27-10-2009 at 11.00am
13 | PS11-63 | TR16/2008 | Soshanguve South | 2.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 7195436.63 | Final Account Excl. Fees |  | ☺☻ | ☺☻ | ☺☻ |  | 03-11-2008 | 26/01/2010 | 34% Completion.Bld 13, 12, 20,19. Extension time | Contract terminated. Final Account done.
14 | PS11-63 | TR24/2009 | Soshanguve South | 2.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | Ж | 32404563.37 | IOP Budgets |  | ☺☻ | Ж |  |  |  | 30/11/2010 | Gone out to tender:-15-10-2009 | Tender closes: Tues: 27-10-2009 @ 12.00
15 | PG31-38 | TR18/2008 | Garankuwa | 1.1 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 22899699 | RTT Rev. Cost Estimate. |  | ☺☻ | ☺☻ | ☺☻ |  | 20/04/2009 | 11/02/2010 | 33% Completion. | Site Meeting:22-10-2009 at 0.90 am
16 | PG36 | TR15/2009 | Upgrading of Residences in Ga-Rankuwa | 1.3 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | Ж | Ж |  | Ж | 15000000 | IOP Budgets |  | ☺☻ | Ж |  |  |  | 16/09/2010 | Gone out to tender:-17-09-2009 | Tender closed: Tues: 20-10-2009 @ 12.00. 12 Tenders.
17 | PG34 | TR10/2009 | Landscaping Ga-Rankuwa, | 1.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 2500000 | IOP Budgets |  | Ж |  |  |  |  | 2010-01-07 | Go out to tender:-14-01-2010 | Planning meeting:TBA
18 | PP04 | TR23/2008 | Pretoria West (Engineering) Phase 1 | 3.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 3029216 | Contract price |  | ☺☻ | ☺☻ | ☺☻ |  | 03-11-2008 | 30/01/2009 | 100% Completion. | Hand-over Meeting:04-03-2009
19 | PP04 | TR23/2008 | Pretoria West (Engineering) Phase 2 | 3.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 7558378 | Preliminary cost estimates |  | ☺☻ | ☺☻ | ☺☻ |  | 23/03/2009 | 21/08/2009 | 100% Completion. | PC: 3 Venues: 12-08-2009 PC Ext Lab:04-09-2009
20 | PP04 | TR12/2009-IOP | Pretoria West (Engineering) Phase 3 | 3.2 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | ☺☻ | Ж |  | ☺☻ | 10000000 | IOP Budgets |  | ☺☻ | ☺☻ | ☺☻ |  | 2009-09-09 | 17/02/2010 | 10% Completion. | Site Meeting: 21-10-2009 @ 12.00 noon.
21 | PS67 |  | HEDS Offices and Labs | 5.3 | ☺☻ | ☺☻ |  | ☺☻ | ☺☻ | Ж | Ж |  | Ж | 5000000 | IOP Budgets | [6 empty] | 27/11/2009 | Proceed with original venues. | Preliminary cost estimates submitted.
Key | √ |  | Commenced
| Ж |  | In Progress
| ☺☻ |  | Completed
| x |  | Not commenced | [10 empty] | 253954661
SECTION A: TRANSFERED TO DPA - SEPT 2009
22 | PS12 |  | MAN Power Phase1 | 5.4 | Ж | Ж | [7 empty] | 4500000 | IOP Budgets | [7 empty] | Planning Meeting: TBA | Pending: Apppointment of Consultants
23 | PS12 |  | MAN Power Phase 2 | 5.4 | [9 empty] | 11000000 | IOP Budgets
24 | PS13 |  | Gencor Hall Soshanguve-South |  | ☺☻ | Ж | [7 empty] | 6000000 | IOP Budgets | [7 empty] | Planning Meeting: TBA
25 | PG35 |  | Aula Auditorium Ga-Rankuwa |  | ☺☻ | ☺☻ |  | ☺☻ | Ж | Ж | Ж |  | Ж | 6000000 | IOP Budgets |  | Ж | [5 empty] | Go out to tender-Jan 2010 | Tender Documentation.
27500000
Key | √ |  | Commenced
| Ж |  | In Progress
| ☺☻ |  | Completed
| x |  | Not commenced