Faculty of Science Programme and Service Subjects Review Schedule

Semester 1, 2011

| Milestone | Date | Responsible Stakeholder | Output |
| --- | --- | --- | --- |
| - Faculty EXCO Presentation and finalization of the Project Plan - Project Launch | 15 November 2010 | Exec Dean, Faculty Review coordinator & DQP Director | Minutes/Report |
| - All Faculty academic Staff orientation workshop | 18, 19 & 20 January 2011 (3 X repeat sessions)19th session will take place in the Arcadia campus | Exec Dean, Faculty Review coordinator & DQP | Workshop Report Attendance Register |
| - Self Evaluation Exercise Commence in the Faculty | February -March 2011 | Executive Dean & HoDs Faculty Coordinator | Self Evaluation Report and Portfolio (SER) |
| - Panel Establishment | 21 February 2011 | HoDs & Faculty Coordinator & DQP | List of panel members for all programmes |
| - SER Submission by faculty to DQP | 25 March 2011 | HoDs & Faculty Exec Dean & Faculty Coordinator | SER |
| - Distribution of Student satisfaction survey questionnaires | 11-21 April 2011 | DQP | Student Satisfaction questionnaires |
| - Administration of student satisfaction surveys | 11-21 April 2011 | DQP | Student Satisfaction questionnaires |
| - Panel Training | 23 & 24 March 2011 (2X repeat sessions) | DQP | Workshop Report Attendance Register |
| - Site Visit (Urban campus) | 12 April – 26 May 2011 | DQP and Faculty Dean & HoDs | Interviews, class inspections and reports |
| - Send draft review reports to panel members | 31 August 2011 | DQP | Draft Review Reports |
| - Input from panel members | 10 September 2011 | Panel members | Draft reports |
| - Send draft reports to faculty | September 2011 | DQP | Draft reports |
| - Input from faculty | 30 September 2011 | Faculty deans & HoDs | Final Reports |
| - Final Review Reports to faculty | 30 October 2011 | DQP | Electronic reports |
| - Review Reports to EMC | 30 November 2011 | DQP | Bound faculty Report |
| - Quality Improvement Plans submission by faculty | 31 March 2012 | Exec dean and HoDs | QIPs |